## Procurement Data-Jul
Date | Workpackage No. | Design Docs Complete Planned | Design Docs Complete Forecast | Design Docs Complete Actual | Complete RFI Planned | Complete RFI Forecast | Complete RFI Actual | Issue RFP Planned | Issue RFP Forecast | Issue RFP Actual | Bid Return Planned | Bid Return Forecast | Bid Return Actual | Technical Evaluation Planned | Technical Evaluation Forecast | Technical Evaluation Actual | Commercial Evaluation Planned | Commercial Evaluation Forecast | Commercial Evaluation Actual | RFQ Issue Planned | RFQ Issue Forecast | RFQ Issue Actual | RFQ Approved Planned | RFQ Approved Forecast | RFQ Approved Actual | Complete RFT Planned | Complete RFT Forecast | Complete RFT Actual | Issue PO Planned | Issue PO Forecast | Issue PO Actual | ROS | ETA
2019-07-01 | LY38A-BS-XX | 2018-05-13 |  | 2018-06-21 | 2018-04-24 |  | 2018-06-08 | 2018-05-16 |  | 2018-07-05 | 2018-06-19 |  | 2018-06-05 | 2018-08-28 |  | 2018-06-21 | 2018-07-07 |  | 2018-07-08 | 2018-08-27 |  | 2018-11-22 | 2018-08-01 |  | 2018-09-21 | 2018-08-25 |  | 2018-08-28 | 2018-09-22 |  | 2018-09-20 | 2019-08-11 | 2019-07-25
2019-07-01 | NH07A-BS-XX | 2018-03-11 |  | 2018-04-13 | 2018-04-17 |  | 2018-04-28 | 2018-03-30 |  | 2018-05-22 | 2018-05-25 |  | 2018-05-03 | 2018-05-23 |  | 2018-07-30 | 2018-05-21 |  | 2018-05-29 | 2018-04-13 |  | 2018-07-19 | 2018-06-14 |  | 2018-08-22 | 2018-06-05 |  | 2018-07-04 | 2018-07-15 |  | 2018-09-25 | 2019-12-23 | 2019-12-14
2019-07-01 | LY03A-BS-YY | 2019-04-06 |  | 2019-03-21 | 2019-05-17 |  | 2019-03-20 | 2019-04-14 |  | 2019-04-28 | 2019-04-25 |  | 2019-07-02 | 2019-06-28 | 2019-06-07 |  | 2019-05-01 | 2019-05-21 |  | 2019-06-08 | 2019-07-25 |  | 2019-05-20 | 2019-08-22 |  | 2019-07-13 | 2019-08-23 |  | 2019-07-22 | 2019-08-05 |  | 2019-12-23 | 2020-01-10
2019-07-01 | LY03A-BS-YY | 2019-04-02 |  | 2019-03-05 | 2019-04-28 |  | 2019-03-18 | 2019-05-26 |  | 2019-05-14 | 2019-05-03 |  | 2019-07-06 | 2019-06-11 | 2019-06-24 |  | 2019-05-23 | 2019-07-22 |  | 2019-08-03 | 2019-07-09 |  | 2019-07-27 | 2019-07-10 |  | 2019-08-03 | 2019-07-17 |  | 2019-05-27 | 2019-08-24 |  | 2019-12-22 | 2019-12-10
2019-07-01 | LY03A-BS-YY | 2019-04-06 |  | 2019-04-24 | 2019-04-06 |  | 2019-04-16 | 2019-04-11 |  | 2019-04-25 | 2019-05-02 |  | 2019-05-27 | 2019-07-02 | 2019-08-09 |  | 2019-05-14 | 2019-07-30 |  | 2019-07-10 | 2019-05-17 |  | 2019-07-02 | 2019-08-03 |  | 2019-06-17 | 2019-07-25 |  | 2019-06-24 | 2019-06-08 |  | 2019-09-13 | 2019-08-26
2019-07-01 | LY03A-BS-YY | 2019-05-17 |  | 2019-03-24 | 2019-04-25 |  | 2019-03-05 | 2019-04-22 |  | 2019-03-20 | 2019-05-09 |  | 2019-05-02 | 2019-05-16 | 2019-08-08 |  | 2019-06-16 | 2019-08-08 |  | 2019-06-03 | 2019-06-30 |  | 2019-07-04 | 2019-06-12 |  | 2019-06-28 | 2019-08-10 |  | 2019-07-18 | 2019-06-18 |  | 2019-07-22 | 2019-08-13
2019-07-01 | LY26A-BS-YY | 2018-07-14 |  | 2018-07-01 | 2018-07-29 |  | 2018-05-26 | 2018-06-11 |  | 2018-07-12 | 2018-08-14 |  | 2018-07-08 | 2018-06-27 |  | 2018-11-03 | 2018-07-24 |  | 2018-07-19 | 2018-09-22 |  | 2018-08-15 | 2018-08-29 |  | 2018-10-09 | 2018-09-01 |  | 2018-11-23 | 2018-08-09 |  | 2019-01-02 | 2019-12-01 | 2019-12-12
2019-07-01 | LY26A-BS-YY | 2018-07-06 |  | 2018-06-22 | 2018-07-22 |  | 2018-05-28 | 2018-07-09 |  | 2018-06-06 | 2018-06-16 |  | 2018-08-15 | 2018-08-13 |  | 2018-11-29 | 2018-06-26 |  | 2018-07-09 | 2018-08-13 |  | 2018-08-24 | 2018-08-20 |  | 2018-09-25 | 2018-10-08 |  | 2018-12-14 | 2018-09-21 |  | 2019-01-07 | 2019-10-25 | 2019-09-24
2019-07-01 | LY33A-BS-YY | 2019-01-26 |  | 2019-01-14 | 2018-11-23 |  | 2019-01-13 | 2018-12-06 |  | 2019-03-02 | 2019-01-03 |  | 2019-02-06 | 2019-03-13 |  | 2019-05-09 | 2019-03-17 |  | 2019-05-28 | 2019-03-21 |  | 2019-03-30 | 2019-02-16 |  | 2019-08-07 | 2019-03-12 |  | 2019-04-27 | 2019-03-10 | 2019-07-31 |  | 2019-08-05 | 2019-07-14
2019-07-01 | LY35A-BS-YY | 2018-12-12 |  | 2019-01-10 | 2018-11-11 |  | 2019-01-16 | 2019-01-11 |  | 2018-11-17 | 2019-01-07 |  | 2019-02-17 | 2019-01-03 |  | 2019-02-24 | 2018-12-21 |  | 2019-01-29 | 2019-01-04 |  | 2019-02-05 | 2019-01-19 |  | 2019-03-09 | 2019-01-27 |  | 2019-03-06 | 2019-03-10 |  | 2019-04-07 | 2019-10-20 | 2019-10-02
2019-07-01 | LY38B-BS-YY | 2019-05-03 |  | 2019-04-11 | 2019-06-23 |  | 2019-06-05 | 2019-04-11 |  | 2019-05-07 | 2019-07-06 | 2019-06-04 |  | 2019-06-30 | 2019-08-28 |  | 2019-07-31 | 2019-08-13 |  | 2019-06-11 | 2019-08-28 |  | 2019-08-17 | 2019-07-09 |  | 2019-06-29 | 2019-06-22 |  | 2019-07-31 | 2019-08-02 |  | 2019-10-06 | 2019-09-27
2019-07-01 | LY41A-BS-YY | [30 empty] | 2019-08-25 | 2019-07-16
2019-07-01 | LY42A-BS-YY | 2019-04-07 |  | 2019-02-24 | 2019-05-04 |  | 2019-03-31 | 2019-04-29 |  | 2019-05-11 | 2019-04-21 |  | 2019-04-30 | 2019-06-21 | 2019-08-08 |  | 2019-06-29 | 2019-07-29 |  | 2019-05-12 | 2019-08-11 |  | 2019-05-28 | 2019-06-01 |  | 2019-06-08 | 2019-07-24 |  | 2019-06-10 | 2019-08-12 |  | 2019-06-04 | 2019-05-21
2019-07-01 | LY45A-BS-YY | 2018-06-06 |  | 2018-08-26 | 2018-05-26 |  | 2018-08-08 | 2018-08-05 |  | 2018-07-07 | 2018-06-24 |  | 2018-08-02 | 2018-08-20 |  | 2018-09-19 | 2018-09-18 |  | 2018-10-20 | 2018-10-03 |  | 2018-10-07 | 2018-08-24 |  | 2018-11-02 | 2018-09-03 |  | 2018-09-18 | 2018-10-22 |  | 2018-12-23 | 2019-10-13 | 2019-10-19
2019-07-01 | LY45A-BS-YY | 2018-07-04 |  | 2018-09-08 | 2018-07-12 |  | 2018-08-13 | 2018-07-04 |  | 2018-08-25 | 2018-09-19 |  | 2018-07-29 | 2018-09-22 |  | 2018-09-15 | 2018-09-13 |  | 2018-09-29 | 2018-09-27 |  | 2018-10-29 | 2018-08-19 |  | 2018-11-20 | 2018-09-25 |  | 2018-09-10 | 2018-09-12 |  | 2018-12-14 | 2019-07-08 | 2019-06-20
2019-07-01 | LY49A-BS-YY | 2019-02-02 |  | 2019-01-19 | 2019-02-25 |  | 2019-01-09 | 2019-01-31 |  | 2019-01-28 | 2019-04-15 |  | 2019-04-14 |  |  | 2019-04-18 | 2019-05-12 |  | 2019-05-05 | 2019-04-19 |  | 2019-02-18 | 2019-04-17 |  | 2019-07-07 | 2019-03-16 |  | 2019-05-28 | 2019-04-03 | 2019-07-03 |  | 2019-09-30 | 2019-09-03
2019-07-01 | LY50B-BS-YY | 2019-02-28 |  | 2019-01-26 | 2018-12-29 |  | 2019-02-28 | 2019-03-15 |  | 2019-01-06 | 2019-04-11 |  | 2019-01-31 | 2019-03-09 |  | 2019-03-28 | 2019-04-06 |  | 2019-03-31 | 2019-05-26 |  | 2019-04-27 | 2019-04-21 |  | 2019-06-01 | 2019-06-08 |  | 2019-06-24 | 2019-04-14 | 2019-08-09 |  | 2019-07-06 | 2019-05-29
2019-07-01 | LY66B-BS-YY | 2019-12-19 |  | 2019-04-22 | 2019-12-04 | 2020-01-26 |  | 2019-12-03 | 2020-01-18 |  | 2020-01-24 | 2020-03-11 |  | 2020-03-24 | 2020-03-26 |  | 2020-03-09 | 2020-03-05 |  | 2020-04-25 | 2020-04-26 |  | 2020-04-06 | 2020-03-17 |  | 2020-04-08 | 2020-05-23 |  | 2020-04-05 | 2020-04-28 |  | 2019-10-29 | 2019-12-02
2019-07-01 | LY66B-BS-YY | 2020-01-09 |  | 2019-03-12 | 2019-12-19 | 2019-12-23 |  | 2019-12-07 | 2020-01-30 |  | 2020-01-17 | 2020-02-03 |  | 2020-03-04 | 2020-03-10 |  | 2020-04-10 | 2020-04-22 |  | 2020-05-23 | 2020-03-31 |  | 2020-06-11 | 2020-04-14 |  | 2020-03-24 | 2020-06-10 |  | 2020-04-03 | 2020-06-13 |  | 2019-10-15 | 2019-10-24
2019-07-01 | LY66C-BS-YY | 2018-10-02 |  | 2018-12-30 | 2018-12-13 |  | 2019-01-09 | 2018-12-23 |  | 2019-01-10 | 2019-01-03 |  | 2018-11-14 | 2019-01-21 |  | 2019-02-12 | 2018-11-18 |  | 2018-12-30 | 2018-12-25 |  | 2019-01-31 | 2019-02-23 |  | 2019-01-04 | 2019-01-28 |  | 2018-12-25 | 2018-12-18 |  | 2019-02-17 | 2019-09-14 | 2019-10-06
2019-07-01 | AL88A-BS-YY | 2019-04-08 |  | 2018-12-04 | 2019-02-23 |  | 2018-11-30 | 2019-03-21 |  | 2018-11-27 | 2019-05-01 |  | 2019-02-20 | 2019-04-02 |  | 2019-06-20 | 2019-06-12 |  | 2019-06-21 | 2019-04-24 |  | 2019-05-20 | 2019-05-16 |  | 2019-07-12 | 2019-04-14 |  | 2019-04-16 | 2019-07-03 | 2019-06-13 |  | 2019-06-27 | 2019-07-07
2019-07-01 | NH07B-BS-YY | 2018-03-13 |  | 2018-10-01 | 2018-03-05 |  | 2018-10-04 | 2018-04-13 |  | 2018-08-30 | 2018-05-26 |  | 2018-07-31 |  |  | 2019-07-05 | 2018-05-02 |  | 2019-05-28 | 2018-12-05 | 2019-07-04 |  | 2018-12-22 | 2019-08-23 |  | 2019-01-09 | 2019-08-30 |  | 2018-12-31 | 2019-07-11 |  | 2019-12-12 | 2019-12-29
2019-07-01 | NH07B-BS-YY | 2018-05-06 |  | 2018-08-30 | 2018-04-01 |  | 2018-08-29 | 2018-05-02 |  | 2018-08-26 | 2018-06-03 |  | 2018-08-25 |  |  | 2019-06-30 | 2018-06-18 |  | 2019-06-15 | 2018-12-14 | 2019-06-30 |  | 2019-01-08 | 2019-09-22 |  | 2019-01-20 | 2019-07-04 |  | 2019-01-05 | 2019-08-21 |  | 2019-10-15 | 2019-09-25
2019-07-01 | NH07B-BS-YY | 2018-03-04 |  | 2018-09-08 | 2018-04-22 |  | 2018-08-22 | 2018-04-04 |  | 2018-09-20 | 2018-05-26 |  | 2018-08-08 |  |  | 2019-05-15 | 2018-06-28 |  | 2019-06-14 | 2018-11-16 | 2019-07-26 |  | 2019-01-15 | 2019-07-31 |  | 2018-12-08 | 2019-08-28 |  | 2019-02-01 | 2019-09-30 |  | 2019-07-11 | 2019-06-05
2019-07-01 | NH07B-BS-YY | 2018-04-08 |  | 2018-07-25 | 2018-04-29 |  | 2018-08-30 | 2018-03-10 |  | 2018-08-18 | 2018-05-20 |  | 2018-10-09 |  |  | 2019-05-10 | 2018-06-12 |  | 2019-05-03 | 2019-02-01 | 2019-08-03 |  | 2018-11-26 | 2019-07-18 |  | 2019-01-01 | 2019-08-20 |  | 2019-01-15 | 2019-08-22 |  | 2019-07-30 | 2019-07-07
2019-07-01 | NH07C-BS-YY | 2019-03-03 |  | 2019-04-14 | 2019-02-17 |  | 2019-02-14 | 2019-02-21 |  | 2019-05-02 | 2019-03-23 |  | 2019-05-16 | 2019-05-12 |  | 2019-06-27 | 2019-04-09 |  | 2019-05-17 | 2019-05-09 | 2019-07-04 |  | 2019-05-19 | 2019-06-18 |  | 2019-07-10 | 2019-07-10 |  | 2019-07-03 | 2019-07-30 |  | 2019-08-29 | 2019-09-26
2019-07-01 | NH18A-BS-YY | 2018-06-15 |  | 2018-07-09 | 2018-07-02 |  | 2018-08-01 | 2018-06-27 |  | 2018-08-06 | 2018-08-13 |  | 2018-08-09 | 2018-08-14 |  | 2018-08-29 | 2018-09-01 |  | 2018-10-29 | 2018-07-19 |  | 2018-09-30 | 2018-08-15 |  | 2018-12-18 | 2018-08-12 |  | 2018-11-06 | 2018-08-11 |  | 2018-11-05 | 2019-08-19 | 2019-08-18
2019-07-01 | NH18B-BS-YY |  |  | 2019-05-27 |  |  | 2019-06-03 |  |  | 2019-04-30 |  |  | 2019-05-25 |  |  |  |  | 2019-08-20 | [8 empty] | 2019-08-21 |  |  | 2019-08-23 |  | 2019-08-03 | 2019-08-04
2019-07-01 | NH18B-BS-YY |  |  | 2019-03-29 |  |  | 2019-05-13 |  |  | 2019-04-26 |  |  | 2019-04-25 |  |  |  |  | 2019-07-21 | [8 empty] | 2019-06-18 |  |  | 2019-07-17 |  | 2019-06-19 | 2019-05-14
2019-07-01 | NH49A-BS-YY | 2019-01-09 |  | 2019-01-20 | 2018-12-26 |  | 2019-01-31 | 2018-12-31 |  | 2019-01-23 | 2019-02-13 |  | 2019-03-29 | 2019-04-12 | 2019-06-26 |  | 2019-03-15 | 2019-06-15 |  | 2019-04-05 | 2019-08-13 |  | 2019-05-14 | 2019-05-28 |  | 2019-05-26 | 2019-08-21 |  | 2019-06-19 | 2019-06-26 |  | 2019-09-01 | 2019-08-12
2019-07-01 | MI01A-BS-YY | 2018-12-18 |  | 2018-12-14 | 2018-10-29 |  | 2019-02-27 | 2018-12-30 |  | 2018-11-19 | 2019-02-11 |  | 2019-01-16 | 2019-02-17 |  | 2019-03-05 | 2019-01-09 |  | 2019-02-18 | 2019-01-11 |  | 2019-05-30 | 2018-12-18 | 2019-07-14 |  | 2018-12-30 |  | 2019-06-13 | 2019-03-05 | 2019-07-07 |  | 2019-06-10 | 2019-07-03
2019-07-01 | MI01A-BS-YY | 2019-01-07 |  | 2019-02-10 | 2018-12-20 |  | 2019-01-01 | 2018-11-29 |  | 2018-11-18 | 2019-01-27 |  | 2018-12-18 | 2019-02-01 |  | 2019-03-24 | 2019-02-18 |  | 2019-03-19 | 2018-12-30 |  | 2019-03-22 | 2019-02-21 | 2019-05-31 |  | 2019-01-01 |  | 2019-05-06 | 2019-02-19 | 2019-08-18 |  | 2019-09-21 | 2019-08-25
2019-07-01 | MI01A-BS-YY | 2018-12-18 |  | 2018-12-23 | 2018-11-01 |  | 2019-02-04 | 2018-12-19 |  | 2019-01-08 | 2019-01-12 |  | 2018-12-13 | 2018-12-12 |  | 2019-04-14 | 2019-02-18 |  | 2019-02-19 | 2019-03-07 |  | 2019-05-09 | 2019-01-08 | 2019-06-16 |  | 2019-02-06 |  | 2019-05-19 | 2019-03-11 | 2019-06-22 |  | 2019-06-30 | 2019-08-03
2019-07-01 | MI01A-BS-YY | 2018-11-17 |  | 2018-12-20 | 2018-12-28 |  | 2019-02-19 | 2018-11-21 |  | 2018-10-27 | 2019-01-10 |  | 2018-12-28 | 2019-01-26 |  | 2019-04-27 | 2019-02-11 |  | 2019-03-11 | 2019-01-18 |  | 2019-03-18 | 2018-12-23 | 2019-07-18 |  | 2018-12-28 |  | 2019-06-17 | 2019-02-15 | 2019-08-01 |  | 2019-07-07 | 2019-08-13
2019-07-01 | MI16A-BS-YY | 2019-01-05 |  | 2018-12-20 | 2018-11-14 |  | 2018-11-21 | 2018-11-10 |  | 2019-01-02 | 2019-01-08 |  | 2018-12-28 | 2019-01-26 |  | 2019-07-09 | 2019-03-08 |  | 2019-07-25 | 2019-02-02 | 2019-06-30 |  | 2019-04-26 | 2019-06-13 |  | 2019-04-21 | 2019-07-11 |  | 2019-04-26 | 2019-07-26 |  | 2019-06-14 | 2019-05-26
2019-07-01 | MI16A-BS-YY | 2018-11-24 |  | 2018-12-02 | 2018-11-11 |  | 2018-11-18 | 2018-11-08 |  | 2019-01-25 | 2019-01-21 |  | 2018-12-28 | 2018-12-31 |  | 2019-07-01 | 2019-02-11 |  | 2019-08-09 | 2019-03-19 | 2019-07-31 |  | 2019-02-07 | 2019-08-23 |  | 2019-04-06 | 2019-07-29 |  | 2019-04-28 | 2019-06-26 |  | 2019-10-10 | 2019-09-12
2019-07-01 | MI20A-BS-YY | 2018-12-21 |  | 2018-12-18 | 2018-12-26 |  | 2018-12-17 | 2018-11-16 |  | 2018-11-24 | 2019-01-29 |  | 2019-01-11 | 2019-01-27 |  | 2019-02-24 | 2019-01-28 |  | 2019-04-14 | 2019-01-14 |  | 2019-02-28 | 2019-01-28 |  | 2019-04-27 | 2019-01-16 |  | 2019-06-24 | 2019-03-13 | 2019-08-16 |  | 2019-09-30 | 2019-09-23
2019-07-01 | MI21A-BS-YY | 2019-01-06 |  | 2018-12-16 | 2018-11-23 |  | 2018-12-16 | 2018-12-23 |  | 2019-01-16 | 2019-02-03 |  | 2018-11-27 | 2019-03-14 |  | 2019-02-22 | 2019-04-14 |  | 2019-03-04 | 2019-04-03 |  | 2019-04-30 | 2019-03-27 |  | 2019-07-01 | 2019-02-18 |  | 2019-04-30 | 2019-03-26 | 2019-07-11 |  | 2019-09-21 | 2019-09-13
2019-07-01 | MI23A-BS-YY | 2018-12-18 |  | 2018-11-12 | 2018-12-27 |  | 2019-01-18 | 2018-11-24 |  | 2018-12-22 | 2019-02-23 |  | 2018-12-31 | 2019-03-22 |  | 2019-06-24 | 2019-04-07 |  | 2019-04-16 | 2019-02-10 |  | 2019-02-12 | 2019-03-16 |  | 2019-05-07 | 2019-03-08 |  | 2019-06-20 | 2019-03-24 | 2019-06-20 |  | 2019-09-25 | 2019-10-13
2019-07-01 | MI23B-BS-YY |  |  | 2019-01-08 |  |  | 2018-12-19 |  |  | 2019-01-13 | 2018-12-28 |  | 2018-12-24 | 2019-01-09 |  | 2018-12-25 | 2019-03-05 |  | 2019-01-28 | 2019-03-18 |  | 2019-02-01 | 2019-02-16 |  | 2018-12-24 | 2019-01-23 |  | 2019-01-18 | 2019-04-03 |  | 2019-01-20 | 2019-08-21 | 2019-09-08
2019-07-01 | MI25A-BS-YY | 2019-06-22 |  | 2019-05-13 | 2019-06-13 |  | 2019-07-22 | 2019-06-26 | 2019-08-07 |  | 2019-07-27 | 2019-08-17 |  | 2019-07-20 | 2019-09-08 |  | 2019-06-11 | 2019-06-24 |  | 2019-08-12 | 2019-08-16 |  | 2019-06-15 | 2019-09-13 |  | 2019-08-19 | 2019-07-27 |  | 2019-09-09 | 2019-10-07 |  | 2019-12-30 | 2020-01-25
2019-07-01 | MI26A-BS-YY | 2019-05-11 |  | 2019-06-29 | 2019-04-22 |  | 2019-08-06 | 2019-07-18 | 2019-07-07 |  | 2019-05-19 | 2019-06-20 |  | 2019-06-23 | 2019-08-20 |  | 2019-06-17 | 2019-08-05 |  | 2019-08-27 | 2019-07-06 |  | 2019-08-09 | 2019-09-18 |  | 2019-08-30 | 2019-09-08 |  | 2019-09-22 | 2019-08-13 |  | 2019-06-09 | 2019-05-09
2019-07-01 | MI27A-BS-YY | [30 empty] | 2019-09-24 | 2019-10-23
2019-07-01 | MI32A-BS-YY | 2019-01-25 |  | 2019-01-19 | 2019-02-10 |  | 2019-03-23 | 2019-01-21 |  | 2019-03-10 | 2019-02-12 |  | 2019-02-13 | 2019-01-25 | 2019-05-19 |  | 2019-02-11 | 2019-05-22 |  | 2019-02-11 | 2019-07-21 |  | 2019-04-02 | 2019-08-11 |  | 2019-04-18 | 2019-08-20 |  | 2019-05-13 | 2019-08-17 |  | 2019-09-15 | 2019-09-27
2019-07-01 | MI35A-BS-YY | 2019-07-31 | 2019-08-14 |  | 2019-09-14 | 2019-07-21 |  | 2019-10-17 | 2019-08-29 |  | 2019-11-05 | 2019-08-14 |  | 2019-09-28 | 2019-09-16 |  | 2019-11-17 | 2019-09-06 |  | 2019-11-19 | 2019-11-14 |  | 2019-12-17 | 2019-10-30 |  | 2019-10-05 | 2019-09-21 |  | 2019-11-16 | 2019-10-03 |  | 2019-10-22 | 2019-11-27
2019-07-01 | MI37A-BS-YY | 2019-07-01 | 2019-07-02 |  | 2019-05-21 | 2019-07-13 |  | 2019-06-25 | 2019-07-09 |  | 2019-06-05 | 2019-08-19 |  | 2019-07-02 | 2019-07-17 |  | 2019-09-02 | 2019-09-12 |  | 2019-06-19 | 2019-08-17 |  | 2019-08-12 | 2019-09-24 |  | 2019-07-09 | 2019-10-21 |  | 2019-10-05 | 2019-08-25 |  | 2019-12-03 | 2020-01-05
2019-07-01 | MI45A-BS-YY | 2019-08-06 | 2019-07-19 |  | 2019-07-13 | 2019-08-22 |  | 2019-09-20 | 2019-08-30 |  | 2019-08-26 | 2019-10-14 |  | 2019-08-16 | 2019-10-05 |  | 2019-10-12 | 2019-10-29 |  | 2019-09-28 | 2019-09-03 |  | 2019-10-05 | 2019-10-22 |  | 2019-09-24 | 2019-11-20 |  | 2019-10-27 | 2019-12-17 |  | 2019-07-15 | 2019-07-30
2019-07-01 | MI67A-BS-YY | 2019-07-01 |  | 2018-12-06 | 2019-05-22 |  | 2018-12-05 | 2019-05-25 |  | 2018-12-22 | 2019-08-20 |  | 2018-11-28 | 2019-07-08 |  | 2019-01-21 | 2019-09-08 |  | 2018-12-21 | 2019-09-02 |  | 2019-02-12 | 2019-07-22 |  | 2019-01-29 | 2019-10-09 |  | 2019-02-06 | 2019-09-16 |  | 2019-04-30 | 2019-06-28 | 2019-06-17
2019-07-01 | LP99A-BS-1F | 2018-11-24 |  | 2018-10-13 | 2018-10-25 |  | 2018-09-15 | 2018-10-16 |  | 2018-09-25 | 2018-12-06 |  | 2019-01-03 | 2019-01-20 |  | 2018-12-17 | 2019-01-02 |  | 2018-11-23 | 2019-01-13 |  | 2018-12-08 | 2019-01-31 |  | 2019-02-09 | 2018-12-02 |  | 2019-01-13 | 2019-02-01 |  | 2019-03-01 | 2019-07-16 | 2019-07-16
2019-07-01 | LP99A-BS-1F | 2018-09-13 |  | 2018-11-19 | 2018-11-13 |  | 2018-10-26 | 2018-10-16 |  | 2018-10-07 | 2018-11-08 |  | 2018-12-10 | 2019-01-26 |  | 2018-11-19 | 2018-12-28 |  | 2018-12-04 | 2018-11-16 |  | 2018-12-30 | 2019-02-13 |  | 2019-03-01 | 2019-02-13 |  | 2019-03-03 | 2018-12-22 |  | 2019-01-13 | 2019-07-26 | 2019-08-08
2019-07-01 | LP99A-BS-1F | 2018-10-10 |  | 2018-10-16 | 2018-10-03 |  | 2018-10-24 | 2018-10-17 |  | 2018-11-26 | 2018-11-13 |  | 2018-12-13 | 2018-12-22 |  | 2019-02-01 | 2018-12-06 |  | 2019-01-20 | 2019-01-31 |  | 2019-02-12 | 2018-12-25 |  | 2019-02-07 | 2019-01-03 |  | 2019-01-24 | 2018-12-25 |  | 2019-03-21 | 2019-09-03 | 2019-09-27
2019-07-01 | LP99A-BS-1F | 2018-10-12 |  | 2018-10-13 | 2018-10-18 |  | 2018-10-20 | 2018-10-10 |  | 2018-10-15 | 2018-10-21 |  | 2019-01-02 | 2018-11-12 |  | 2018-12-13 | 2018-11-12 |  | 2019-01-12 | 2019-01-13 |  | 2018-12-09 | 2019-01-25 |  | 2019-01-31 | 2019-01-09 |  | 2019-02-15 | 2019-03-05 |  | 2019-02-02 | 2019-11-09 | 2019-10-04
2019-07-01 | LY03A-BS-2E | 2019-12-18 | 2019-10-14 |  | 2019-10-16 | 2019-10-08 |  | 2019-12-16 | 2019-10-13 |  | 2019-11-26 | 2019-11-30 |  | 2020-01-27 | 2020-02-03 |  | 2020-01-02 | 2019-12-18 |  | 2020-02-10 | 2020-01-05 |  | 2020-02-07 | 2020-01-20 |  | 2020-01-07 | 2020-01-12 |  | 2020-02-01 | 2020-02-03 |  | 2019-12-17 | 2019-11-19
2019-07-01 | LY03A-BS-2E | 2019-09-21 | 2019-12-07 |  | 2019-10-09 | 2019-10-09 |  | 2020-01-02 | 2019-11-09 |  | 2020-01-02 | 2019-12-20 |  | 2019-11-18 | 2019-11-22 |  | 2020-01-14 | 2020-01-02 |  | 2019-12-12 | 2019-12-12 |  | 2019-12-13 | 2020-01-23 |  | 2020-02-09 | 2020-02-11 |  | 2020-01-31 | 2020-01-14 |  | 2019-11-26 | 2019-12-30
2019-07-01 | LY03A-BS-2E | 2019-09-24 | 2019-10-06 |  | 2019-12-25 | 2019-09-28 |  | 2019-12-28 | 2019-10-22 |  | 2019-12-29 | 2019-12-31 |  | 2019-12-16 | 2020-01-29 |  | 2020-01-05 | 2019-12-13 |  | 2020-01-28 | 2020-01-25 |  | 2019-12-25 | 2020-02-13 |  | 2019-12-26 | 2020-01-26 |  | 2020-01-08 | 2020-03-03 |  | 2019-12-02 | 2020-01-03
2019-07-01 | LY26A-BS-2E | 2020-04-05 | 2020-04-03 |  | 2020-06-12 | 2020-03-25 |  | 2020-06-23 | 2020-04-03 |  | 2020-07-02 | 2020-05-18 |  | 2020-09-06 | 2020-07-22 |  | 2020-08-28 | 2020-08-23 |  | 2020-09-25 | 2020-09-11 |  | 2020-08-13 | 2020-08-16 |  | 2020-08-02 | 2020-09-06 |  | 2020-10-17 | 2020-09-09 |  | 2019-08-14 | 2019-07-19
2019-07-01 | AL19A-BS-2E | 2019-06-20 |  | 2018-07-15 | 2019-07-06 |  | 2018-06-26 | 2019-07-07 |  | 2018-07-16 | 2019-07-09 |  | 2018-10-16 | 2019-08-21 |  | 2019-05-13 | 2019-07-10 |  | 2019-03-22 | [6 empty] | 2019-10-01 | 2019-05-29 |  | 2019-08-20 | 2019-07-24 |  | 2019-10-12 | 2019-11-16
2019-07-01 | AL87A-BS-2E | 2019-09-08 | 2019-07-04 |  | 2019-08-15 | 2019-06-16 |  | 2019-10-14 | 2019-06-29 |  | 2019-10-14 | 2019-07-14 |  | 2019-09-20 | 2019-08-14 |  | 2019-12-01 | 2019-07-31 |  | 2019-11-03 | 2019-09-22 |  | 2019-11-25 | 2019-10-03 |  | 2019-10-14 | 2019-08-15 |  | 2019-11-24 | 2019-10-26 |  | 2019-10-11 | 2019-09-13
2019-07-01 | AL87A-BS-2E | 2019-09-25 | 2019-06-16 |  | 2019-08-22 | 2019-07-03 |  | 2019-08-08 | 2019-06-12 |  | 2019-10-09 | 2019-07-12 |  | 2019-10-15 | 2019-07-27 |  | 2019-12-10 | 2019-08-18 |  | 2019-11-01 | 2019-08-19 |  | 2019-12-04 | 2019-09-15 |  | 2019-10-25 | 2019-08-22 |  | 2019-12-20 | 2019-08-08 |  | 2019-07-18 | 2019-07-30
2019-07-01 | LP98A-BS-2E | 2021-03-29 | 2021-05-24 |  | 2021-05-16 | 2021-06-02 |  | 2021-05-11 | 2021-04-08 |  | 2021-05-11 | 2021-05-27 |  | 2021-07-18 | 2021-08-14 |  | 2021-08-05 | 2021-06-27 |  | 2021-07-29 | 2021-06-16 |  | 2021-09-08 | 2021-07-02 |  | 2021-09-03 | 2021-09-02 |  | 2021-09-17 | 2021-07-15 |  | 2019-11-05 | 2019-12-03
2019-07-01 | ZA01A-BW-6A | 2019-04-21 |  | 2019-03-31 | 2019-06-10 |  | 2019-06-02 | 2019-05-13 |  | 2019-04-10 | 2019-05-03 |  | 2019-06-20 | 2019-06-11 | 2019-08-04 |  | 2019-07-17 |  | 2019-07-08 | [6 empty] | 2019-07-27 | 2019-07-22 |  | 2019-08-12 | 2019-08-09 |  | 2019-11-04 | 2019-11-07
2019-07-01 | ZA01A-BW-6A | 2019-04-23 |  | 2019-06-04 | 2019-06-10 |  | 2019-06-09 | 2019-06-16 |  | 2019-06-08 | 2019-05-16 |  | 2019-05-30 | 2019-07-03 | 2019-08-17 |  | 2019-05-18 |  | 2019-06-15 | [6 empty] | 2019-06-28 | 2019-06-19 |  | 2019-07-21 | 2019-06-25 |  | 2019-06-06 | 2019-06-26
2019-07-01 | ZA01A-BW-6A | 2019-04-25 |  | 2019-04-05 | 2019-04-06 |  | 2019-04-14 | 2019-05-15 |  | 2019-05-24 | 2019-04-26 |  | 2019-06-16 | 2019-07-20 | 2019-06-28 |  | 2019-06-11 |  | 2019-07-12 | [6 empty] | 2019-08-08 | 2019-08-24 |  | 2019-07-06 | 2019-06-28 |  | 2019-06-27 | 2019-06-20
2019-07-01 | ZA01B-BW-6A | 2019-07-25 | 2019-06-28 |  | 2019-06-20 | 2019-07-19 |  | 2019-06-15 | 2019-08-01 |  | 2019-08-26 | 2019-10-03 |  | 2019-09-17 | 2019-07-22 |  | 2019-09-10 | 2019-10-21 |  |  |  |  | 2019-08-28 | 2019-10-31 |  | 2019-09-09 | 2019-09-23 |  | 2019-09-22 | 2019-11-20 |  | 2019-12-21 | 2020-01-06
2019-07-01 | ZA04A-BW-6A | 2019-05-03 |  | 2019-03-10 | 2019-03-26 |  | 2019-05-24 | 2019-06-07 |  | 2019-05-10 | 2019-06-30 |  | 2019-06-18 | 2019-06-19 | 2019-07-22 |  | 2019-06-08 |  | 2019-06-01 | [6 empty] | 2019-06-02 | 2019-06-09 |  | 2019-08-14 | 2019-07-16 |  | 2019-12-12 | 2019-11-22
2019-07-01 | ZA04A-BW-6A | 2019-03-14 |  | 2019-04-18 | 2019-04-17 |  | 2019-05-17 | 2019-04-01 |  | 2019-05-11 | 2019-06-07 |  | 2019-05-10 | 2019-05-03 | 2019-08-04 |  | 2019-08-03 |  | 2019-07-29 | [6 empty] | 2019-05-29 | 2019-06-18 |  | 2019-07-03 | 2019-06-19 |  | 2019-06-16 | 2019-06-07
2019-07-01 | ZA04A-BW-6A | 2019-06-04 |  | 2019-05-09 | 2019-05-15 |  | 2019-06-04 | 2019-04-17 |  | 2019-04-14 | 2019-06-08 |  | 2019-06-04 | 2019-07-25 | 2019-06-17 |  | 2019-07-01 |  | 2019-06-19 | [6 empty] | 2019-07-17 | 2019-08-07 |  | 2019-08-21 | 2019-07-01 |  | 2019-06-27 | 2019-07-22
2019-07-01 | ZA08A-BW-6A | 2020-03-10 | 2020-02-23 |  | 2020-04-15 | 2020-05-06 |  | 2020-04-28 | 2020-05-16 |  | 2020-04-26 | 2020-06-08 |  | 2020-04-09 | 2020-06-21 |  | 2020-06-06 | 2020-06-19 | [7 empty] | 2020-05-06 | 2020-06-12 |  | 2020-07-14 | 2020-06-05 |  | 2019-10-10 | 2019-08-31
2019-07-01 | ZA09A-BW-6A | 2019-12-22 | 2020-01-12 |  | 2019-12-29 | 2020-01-06 |  | 2019-11-11 | 2019-12-19 |  | 2020-01-30 | 2020-02-27 |  | 2019-12-17 | 2020-01-31 |  | 2020-02-20 | 2020-02-08 | [7 empty] | 2020-02-23 | 2020-01-23 |  | 2020-02-27 | 2020-02-16 |  | 2019-12-12 | 2019-11-16
2019-07-01 | ZA10A-BW-6A | 2019-09-04 | 2019-08-25 |  | 2019-07-01 | 2019-09-09 |  | 2019-09-29 | 2019-07-27 |  | 2019-08-12 | 2019-10-02 |  | 2019-09-08 | 2019-10-23 |  | 2019-09-22 | 2019-10-26 | [7 empty] | 2019-11-10 | 2019-12-02 |  | 2019-11-07 | 2019-11-05 |  | 2019-12-21 | 2019-12-21
2019-07-01 | ZA12A-BW-6A | 2019-05-07 |  | 2019-06-13 | 2019-07-12 |  | 2019-04-27 | 2019-07-14 |  | 2019-06-22 | 2019-05-30 | 2019-07-18 |  | 2019-07-02 | 2019-06-18 |  | 2019-07-23 | 2019-07-04 | [7 empty] | 2019-09-25 | 2019-09-16 |  | 2019-09-19 | 2019-10-01 |  | 2019-11-27 | 2019-12-22
2019-07-01 | LY02A-BW-6A | 2019-05-01 |  | 2019-06-20 | 2019-05-22 |  | 2019-07-02 | 2019-06-01 |  | 2019-05-19 | 2019-08-12 |  | 2019-05-11 | 2019-08-19 | 2019-07-27 |  | 2019-07-08 | 2019-08-15 |  |  | 2019-06-02 |  |  | 2019-08-15 |  | 2019-07-17 | 2019-08-06 |  | 2019-09-22 | 2019-09-16 |  | 2019-10-06 | 2019-09-25
2019-07-01 | LY02A-BW-6A | 2019-06-18 |  | 2019-05-26 | 2019-06-10 |  | 2019-06-03 | 2019-05-04 |  | 2019-06-25 | 2019-07-04 |  | 2019-06-17 | 2019-06-24 | 2019-07-07 |  | 2019-07-22 | 2019-07-15 |  |  | 2019-07-19 |  |  | 2019-07-11 |  | 2019-07-26 | 2019-09-29 |  | 2019-09-13 | 2019-08-05 |  | 2019-09-30 | 2019-09-15
2019-07-01 | LY03A-BW-6A | 2019-06-27 |  | 2019-05-26 | 2019-05-01 |  | 2019-04-27 | 2019-05-25 |  | 2019-06-17 | 2019-07-14 | 2019-08-08 |  | 2019-06-26 | 2019-06-22 |  | 2019-09-09 | 2019-07-09 | [7 empty] | 2019-09-04 | 2019-10-09 |  | 2019-08-29 | 2019-09-06 |  | 2019-12-22 | 2020-01-19
2019-07-01 | LY04A-BW-6A | 2019-05-06 |  | 2019-03-28 | 2019-05-18 |  | 2019-06-02 | 2019-04-15 |  | 2019-05-14 | 2019-04-28 |  | 2019-04-14 | 2019-04-18 |  | 2019-06-27 | 2019-05-17 |  | 2019-06-11 | [6 empty] | 2019-07-01 | 2019-06-28 |  | 2019-05-30 | 2019-07-01 |  | 2019-12-21 | 2020-01-06
2019-07-01 | LY05A-BW-6A | 2019-09-10 | 2019-07-14 |  | 2019-07-28 | 2019-09-02 |  | 2019-08-06 | 2019-09-13 |  | 2019-09-09 | 2019-10-19 |  | 2019-09-26 | 2019-09-27 |  | 2019-11-04 | 2019-10-12 | [7 empty] | 2019-12-07 | 2019-11-27 |  | 2019-11-17 | 2019-11-08 |  | 2019-08-15 | 2019-07-09
2019-07-01 | LY48A-BW-6A | 2019-05-21 |  | 2019-05-12 | 2019-04-22 |  | 2019-05-12 | 2019-06-16 |  | 2019-05-02 | 2019-05-29 | 2019-08-11 |  | 2019-07-07 | 2019-07-25 |  | 2019-08-20 | 2019-09-16 | [7 empty] | 2019-08-31 | 2019-08-26 |  | 2019-09-11 | 2019-09-22 |  | 2019-10-21 | 2019-09-23
2019-07-01 | LY48A-BW-6A | 2019-04-25 |  | 2019-06-17 | 2019-05-25 |  | 2019-06-20 | 2019-06-08 |  | 2019-05-02 | 2019-07-18 | 2019-07-21 |  | 2019-06-15 | 2019-07-01 |  | 2019-08-11 | 2019-08-21 | [7 empty] | 2019-08-29 | 2019-10-06 |  | 2019-08-29 | 2019-10-25 |  | 2019-10-05 | 2019-09-01
2019-07-01 | LY48A-BW-6A | 2019-04-10 |  | 2019-05-03 | 2019-07-12 |  | 2019-07-06 | 2019-05-24 |  | 2019-06-21 | 2019-08-16 | 2019-08-13 |  | 2019-07-18 | 2019-09-05 |  | 2019-08-04 | 2019-08-25 | [7 empty] | 2019-07-15 | 2019-09-09 |  | 2019-10-06 | 2019-08-05 |  | 2019-12-28 | 2019-11-28
2019-07-01 | LY48A-BW-6A | 2019-05-29 |  | 2019-05-21 | 2019-06-17 |  | 2019-06-08 | 2019-07-10 |  | 2019-06-20 | 2019-06-17 | 2019-07-26 |  | 2019-08-27 | 2019-08-20 |  | 2019-09-05 | 2019-07-20 | [7 empty] | 2019-10-05 | 2019-08-20 |  | 2019-07-26 | 2019-08-30 |  | 2019-11-05 | 2019-10-12
2019-07-01 | LY49A-BW-6A | 2019-02-28 |  | 2019-03-24 | 2019-04-17 |  | 2019-04-13 | 2019-05-26 |  | 2019-03-24 | 2019-06-16 |  | 2019-05-08 | 2019-04-12 | 2019-05-18 |  | 2019-04-20 | 2019-07-30 | [7 empty] | 2019-06-02 | 2019-07-15 |  | 2019-05-22 | 2019-08-06 |  | 2019-06-30 | 2019-06-20
2019-07-01 | LY78A-BW-6A |  | 2019-07-06 |  |  | 2019-07-03 |  |  | 2019-07-27 |  |  | 2019-08-28 |  |  | 2019-07-27 |  |  | 2019-10-03 | [8 empty] | 2019-11-07 |  |  | 2019-09-22 |  | 2019-07-26 | 2019-06-21
2019-07-01 | LY78B-BW-6A |  | 2019-08-03 |  |  | 2019-06-27 |  |  | 2019-09-06 |  |  | 2019-08-07 |  |  | 2019-07-30 |  |  | 2019-10-01 | [8 empty] | 2019-11-04 |  |  | 2019-10-14 |  | 2019-08-14 | 2019-07-21
2019-07-01 | LY78C-BW-6A |  | 2019-08-02 |  |  | 2019-08-10 |  |  | 2019-08-31 |  |  | 2019-09-29 |  |  | 2019-08-11 |  |  | 2019-10-27 | [8 empty] | 2019-10-03 |  |  | 2019-10-31 |  | 2019-10-24 | 2019-11-10
2019-07-01 | LY78C-BW-6A |  | 2019-05-31 |  |  | 2019-08-30 |  |  | 2019-08-20 |  |  | 2019-08-12 |  |  | 2019-09-03 |  |  | 2019-09-10 | [8 empty] | 2019-09-14 |  |  | 2019-11-06 |  | 2019-08-19 | 2019-09-05
2019-07-01 | LY78C-BW-6A |  | 2019-08-13 |  |  | 2019-08-14 |  |  | 2019-07-13 |  |  | 2019-07-31 |  |  | 2019-09-15 |  |  | 2019-09-16 | [8 empty] | 2019-09-19 |  |  | 2019-10-17 |  | 2019-08-09 | 2019-07-25
2019-07-01 | LY78D-BW-6A |  | 2019-08-12 |  |  | 2019-07-22 |  |  | 2019-08-28 |  |  | 2019-09-21 |  |  | 2019-08-23 |  |  | 2019-09-13 | [8 empty] | 2019-11-30 |  |  | 2019-10-31 |  | 2019-06-04 | 2019-06-10
2019-07-01 | LY78D-BW-6A |  | 2019-08-21 |  |  | 2019-08-23 |  |  | 2019-09-06 |  |  | 2019-08-22 |  |  | 2019-11-12 |  |  | 2019-11-09 | [8 empty] | 2019-09-28 |  |  | 2019-12-26 |  | 2019-06-26 | 2019-07-27
2019-07-01 | QW10A-QW-6A | [30 empty] | 2019-12-14 | 2020-01-13
2019-07-01 | QW60A-QW-6A | 2019-05-29 | 2019-09-17 |  | 2019-05-17 | 2019-07-17 |  | 2019-06-20 | 2019-08-17 |  | 2019-05-30 | 2019-11-16 |  | 2019-07-08 | 2019-11-29 |  | 2019-07-09 | 2019-10-07 | [7 empty] | 2019-10-10 | 2019-10-15 |  | 2019-09-20 | 2019-11-02 |  | 2019-08-08 | 2019-08-26
2019-07-01 | QW60A-QW-6A | 2019-06-07 | 2019-07-08 |  | 2019-05-16 | 2019-10-04 |  | 2019-07-13 | 2019-08-27 |  | 2019-06-07 | 2019-09-17 |  | 2019-07-11 | 2019-10-09 |  | 2019-09-14 | 2019-12-07 | [7 empty] | 2019-08-17 | 2019-10-18 |  | 2019-08-16 | 2019-12-14 |  | 2019-08-19 | 2019-09-01
2019-07-01 | QW65A-QW-6A | 2019-11-17 | 2019-09-03 |  | 2019-09-18 | 2019-09-26 |  | 2019-10-11 | 2019-10-06 |  | 2019-10-10 | 2019-10-23 |  | 2020-01-22 | 2020-01-04 |  | 2019-11-17 | 2019-11-23 | [7 empty] | 2020-02-21 | 2020-02-14 |  | 2019-12-26 | 2019-12-21 |  | 2019-11-28 | 2019-11-01
2019-07-01 | QW67A-QW-6A | 2019-07-15 | 2019-08-10 |  | 2019-08-20 | 2019-08-04 |  | 2019-09-06 | 2019-10-09 |  | 2019-08-15 | 2019-09-26 |  | 2019-11-15 | 2019-10-08 |  | 2019-11-20 | 2019-11-24 | [7 empty] | 2019-11-28 | 2019-11-16 |  | 2020-01-01 | 2019-12-31 |  | 2019-11-20 | 2019-11-02
2019-07-01 | QW70A-QW-6A | [30 empty] | 2019-09-25 | 2019-10-22
2019-07-01 | AL91A-BW-6A | [30 empty] | 2019-08-14 | 2019-07-13
2019-07-01 | VC02A-BW-6A | 2019-05-02 |  | 2019-07-04 | 2019-06-05 |  | 2019-06-05 | 2019-04-22 |  | 2019-05-24 | 2019-06-13 |  | 2019-05-06 | 2019-07-12 | 2019-05-11 |  | 2019-09-03 | 2019-06-06 | [7 empty] | 2019-07-30 | 2019-07-01 |  | 2019-09-13 | 2019-07-05 |  | 2019-11-22 | 2019-11-18
2019-07-01 | VC03A-BW-6A | 2019-04-23 | 2019-07-17 |  | 2019-05-15 | 2019-07-22 |  | 2019-05-23 | 2019-06-06 |  | 2019-06-20 | 2019-08-29 |  | 2019-08-05 | 2019-09-23 |  | 2019-08-21 | 2019-08-01 | [7 empty] | 2019-09-18 | 2019-09-11 |  | 2019-07-27 | 2019-09-01 |  | 2019-11-05 | 2019-10-25
2019-07-01 | VC03A-BW-6A | 2019-05-15 | 2019-07-20 |  | 2019-04-25 | 2019-06-26 |  | 2019-06-01 | 2019-07-10 |  | 2019-06-30 | 2019-08-14 |  | 2019-06-08 | 2019-09-19 |  | 2019-07-11 | 2019-10-26 | [7 empty] | 2019-09-02 | 2019-10-23 |  | 2019-08-24 | 2019-09-08 |  | 2019-11-28 | 2019-12-28
2019-07-01 | NH19A-BW-6A | 2019-11-21 | 2019-10-15 |  | 2019-10-28 | 2019-11-08 |  | 2019-11-27 | 2019-11-09 |  | 2019-12-19 | 2019-11-23 |  | 2019-12-06 | 2019-12-21 |  | 2020-02-28 | 2020-02-25 | [7 empty] | 2020-04-05 | 2020-04-12 |  | 2020-03-21 | 2020-04-15 |  | 2019-11-13 | 2019-11-12
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-04-21 | 2019-08-02 |  | 2019-06-13 | 2019-09-01 |  | 2019-10-07 | 2019-10-18
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-06-03 | 2019-08-04 |  | 2019-05-08 | 2019-06-15 |  | 2019-08-16 | 2019-08-23
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-05-09 | 2019-08-26 |  | 2019-07-13 | 2019-08-17 |  | 2019-09-28 | 2019-10-30
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-05-26 | 2019-07-16 |  | 2019-05-22 | 2019-07-11 |  | 2019-06-05 | 2019-05-28
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-05-28 | 2019-08-21 |  | 2019-06-13 | 2019-08-21 |  | 2019-07-17 | 2019-06-17
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-05-23 | 2019-06-14 |  | 2019-05-24 | 2019-07-05 |  | 2019-11-13 | 2019-11-20
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-06-28 | 2019-06-26 |  | 2019-06-03 | 2019-08-05 |  | 2019-09-27 | 2019-10-23
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-05-05 | 2019-06-22 |  | 2019-05-15 | 2019-07-12 |  | 2019-11-02 | 2019-10-23
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-06-24 | 2019-07-16 |  | 2019-06-17 | 2019-08-13 |  | 2019-12-22 | 2019-11-18
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-04-29 | 2019-07-26 |  | 2019-05-02 | 2019-08-24 |  | 2019-12-24 | 2020-01-16
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-05-06 | 2019-08-15 |  | 2019-05-16 | 2019-08-08 |  | 2019-06-16 | 2019-07-05
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-04-24 | 2019-08-27 |  | 2019-06-26 | 2019-08-14 |  | 2019-12-28 | 2019-11-30
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-07-12 | 2019-08-19 |  | 2019-05-11 | 2019-07-02 |  | 2019-08-22 | 2019-08-01
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-06-15 | 2019-08-02 |  | 2019-05-28 | 2019-08-31 |  | 2019-10-27 | 2019-09-25
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-07-02 | 2019-07-18 |  | 2019-05-01 | 2019-06-19 |  | 2019-11-27 | 2019-10-29
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-06-11 | 2019-08-21 |  | 2019-05-29 | 2019-06-14 |  | 2019-09-07 | 2019-08-01
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-05-07 | 2019-07-16 |  | 2019-07-04 | 2019-07-14 |  | 2019-11-01 | 2019-11-25
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-04-21 | 2019-08-02 |  | 2019-07-25 | 2019-06-17 |  | 2019-12-05 | 2019-12-06
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-04-28 | 2019-07-12 |  | 2019-07-23 | 2019-08-19 |  | 2019-07-29 | 2019-07-16
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-06-24 | 2019-07-16 |  | 2019-06-18 | 2019-06-20 |  | 2019-11-15 | 2019-10-10
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-04-28 | 2019-07-10 |  | 2019-06-18 | 2019-07-07 |  | 2019-10-17 | 2019-10-16
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-07-04 | 2019-08-13 |  | 2019-05-23 | 2019-07-29 |  | 2019-12-14 | 2019-12-09
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-05-26 | 2019-08-23 |  | 2019-07-19 | 2019-07-07 |  | 2019-12-05 | 2019-12-19
2019-07-01 | MI01A-BW-6A | [24 empty] | 2019-06-17 | 2019-08-14 |  | 2019-05-11 | 2019-07-21 |  | 2019-09-04 | 2019-09-13
2019-07-01 | MI01B-BW-6A | [24 empty] | 2019-07-17 | 2019-06-23 |  | 2019-06-14 | 2019-07-07 |  | 2019-11-11 | 2019-12-05
2019-07-01 | MI01B-BW-6A | [24 empty] | 2019-07-08 | 2019-07-01 |  | 2019-07-08 | 2019-08-07 |  | 2019-12-24 | 2019-12-01
2019-07-01 | MI01B-BW-6A | [24 empty] | 2019-06-21 | 2019-06-08 |  | 2019-05-24 | 2019-06-29 |  | 2019-09-01 | 2019-08-08
2019-07-01 | MI01B-BW-6A | [24 empty] | 2019-05-26 | 2019-08-08 |  | 2019-06-29 | 2019-07-06 |  | 2019-10-12 | 2019-11-19
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-07-10 | 2019-06-14 |  | 2019-05-28 | 2019-09-05 |  | 2019-10-26 | 2019-10-30
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-05-10 | 2019-08-19 |  | 2019-04-27 | 2019-07-17 |  | 2019-11-09 | 2019-10-09
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-05-02 | 2019-06-30 |  | 2019-06-06 | 2019-06-26 |  | 2019-11-09 | 2019-12-07
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-05-07 | 2019-06-23 |  | 2019-06-18 | 2019-06-25 |  | 2019-06-05 | 2019-07-13
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-07-18 | 2019-06-11 |  | 2019-07-11 | 2019-07-10 |  | 2019-07-16 | 2019-08-18
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-06-30 | 2019-06-26 |  | 2019-07-17 | 2019-07-12 |  | 2019-08-05 | 2019-08-06
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-06-11 | 2019-06-25 |  | 2019-06-28 | 2019-06-23 |  | 2019-08-27 | 2019-08-26
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-05-20 | 2019-07-21 |  | 2019-06-30 | 2019-07-13 |  | 2019-08-18 | 2019-09-22
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-07-02 | 2019-07-31 |  | 2019-05-18 | 2019-08-21 |  | 2019-10-01 | 2019-08-27
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-05-04 | 2019-07-04 |  | 2019-06-26 | 2019-06-28 |  | 2019-12-23 | 2020-01-23
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-07-11 | 2019-08-26 |  | 2019-06-03 | 2019-08-24 |  | 2019-07-22 | 2019-08-07
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-06-11 | 2019-08-16 |  | 2019-07-05 | 2019-08-27 |  | 2019-06-13 | 2019-07-23
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-07-08 | 2019-07-28 |  | 2019-07-15 | 2019-06-24 |  | 2019-11-08 | 2019-10-26
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-05-23 | 2019-06-25 |  | 2019-05-28 | 2019-08-16 |  | 2019-12-03 | 2019-12-04
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-07-07 | 2019-06-24 |  | 2019-06-19 | 2019-08-31 |  | 2019-11-04 | 2019-11-10
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-06-10 | 2019-08-13 |  | 2019-05-02 | 2019-06-29 |  | 2019-07-29 | 2019-08-30
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-05-11 | 2019-07-30 |  | 2019-06-06 | 2019-08-03 |  | 2019-06-19 | 2019-07-06
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-06-01 | 2019-07-20 |  | 2019-05-20 | 2019-06-14 |  | 2019-06-26 | 2019-06-18
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-06-28 | 2019-08-01 |  | 2019-06-13 | 2019-08-07 |  | 2019-11-01 | 2019-11-18
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-06-05 | 2019-07-27 |  | 2019-07-14 | 2019-07-06 |  | 2019-11-21 | 2019-12-22
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-06-19 | 2019-07-12 |  | 2019-05-15 | 2019-07-28 |  | 2019-06-15 | 2019-06-19
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-05-07 | 2019-06-23 |  | 2019-04-28 | 2019-07-16 |  | 2019-06-12 | 2019-07-19
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-04-20 | 2019-07-28 |  | 2019-05-23 | 2019-07-10 |  | 2019-12-18 | 2019-11-29
2019-07-01 | MI08A-BW-6A | [24 empty] | 2019-07-18 | 2019-07-16 |  | 2019-07-26 | 2019-07-30 |  | 2019-07-24 | 2019-06-16
2019-07-01 | MI08B-BW-6A | [24 empty] | 2019-07-13 | 2019-08-25 |  | 2019-05-24 | 2019-08-26 |  | 2019-09-13 | 2019-08-19
2019-07-01 | MI08B-BW-6A | [24 empty] | 2019-05-04 | 2019-08-15 |  | 2019-05-02 | 2019-09-05 |  | 2019-09-06 | 2019-08-09
2019-07-01 | MI11A-BW-6A | [30 empty] | 2019-08-23 | 2019-08-15
2019-07-01 | MI16A-BW-6A | 2019-05-25 |  | 2019-05-07 | 2019-04-27 |  | 2019-04-22 | 2019-06-12 |  | 2019-05-28 | 2019-06-14 |  | 2019-05-07 | 2019-07-04 | 2019-08-22 |  | 2019-05-11 | 2019-06-26 | [7 empty] | 2019-07-24 | 2019-07-29 |  | 2019-07-28 | 2019-08-15 |  | 2019-11-24 | 2019-11-20
2019-07-01 | MI16B-BW-6A | 2019-04-30 |  | 2019-04-08 | 2019-03-24 |  | 2019-05-29 | 2019-03-26 |  | 2019-04-28 | 2019-03-31 |  | 2019-05-07 | 2019-06-26 | 2019-08-05 |  | 2019-07-24 | 2019-08-08 | [7 empty] | 2019-07-07 | 2019-07-14 |  | 2019-07-28 | 2019-06-29 |  | 2019-10-29 | 2019-10-31
2019-07-01 | MI17A-BW-6A | 2019-04-15 |  | 2019-04-08 | 2019-06-01 |  | 2019-04-19 | 2019-03-24 |  | 2019-04-29 | 2019-05-15 |  | 2019-06-14 | 2019-05-01 | 2019-06-20 |  | 2019-07-15 | 2019-07-13 | [7 empty] | 2019-06-14 | 2019-07-01 |  | 2019-06-05 | 2019-06-29 |  | 2019-06-12 | 2019-05-17
2019-07-01 | MI17B-BW-6A | 2019-03-31 |  | 2019-04-29 | 2019-05-29 |  | 2019-03-26 | 2019-05-26 |  | 2019-03-17 | 2019-05-14 |  | 2019-04-09 | 2019-05-13 | 2019-08-07 |  | 2019-05-14 | 2019-06-22 | [7 empty] | 2019-07-11 | 2019-07-17 |  | 2019-08-17 | 2019-08-08 |  | 2019-10-25 | 2019-10-13
2019-07-01 | MI18A-BW-6A | [30 empty] | 2019-08-13 | 2019-08-26
2019-07-01 | MI18A-BW-6A | [30 empty] | 2019-11-22 | 2019-11-21
2019-07-01 | MI18B-BW-6A | 2019-05-20 |  | 2019-06-02 | 2019-04-08 |  | 2019-06-11 | 2019-04-19 |  | 2019-03-18 | 2019-04-06 |  | 2019-04-26 | 2019-04-30 | 2019-07-12 |  | 2019-07-09 | 2019-06-16 | [7 empty] | 2019-05-27 | 2019-06-06 |  | 2019-07-18 | 2019-09-01 |  | 2019-08-05 | 2019-07-03
2019-07-01 | MI19A-BW-6A | 2019-05-16 |  |  | 2019-04-17 |  |  | 2019-04-11 |  |  | 2019-04-23 |  |  | 2019-05-15 |  |  | 2019-07-21 | [8 empty] | 2019-08-10 |  |  | 2019-07-06 |  |  | 2019-08-17 | 2019-08-27
2019-07-01 | MI19B-BW-6A | 2019-06-03 |  | 2019-06-07 | 2019-04-14 |  | 2019-05-28 | 2019-04-25 |  | 2019-05-29 | 2019-06-19 |  | 2019-04-26 | 2019-05-04 | 2019-07-17 |  | 2019-05-04 | 2019-06-27 | [7 empty] | 2019-07-15 | 2019-08-01 |  | 2019-05-31 | 2019-06-25 |  | 2019-12-28 | 2019-12-18
2019-07-01 | MI20A-BW-6A | 2019-03-14 |  | 2019-04-22 | 2019-03-21 |  | 2019-05-24 | 2019-04-29 |  | 2019-03-20 | 2019-04-08 |  | 2019-04-09 | 2019-05-17 | 2019-08-18 |  | 2019-07-22 | 2019-08-23 | [7 empty] | 2019-08-05 | 2019-07-18 |  | 2019-07-19 | 2019-07-02 |  | 2019-07-02 | 2019-08-01
2019-07-01 | MI20B-BW-6A | 2019-05-30 |  | 2019-03-25 | 2019-06-04 |  | 2019-05-13 | 2019-05-12 |  | 2019-05-17 | 2019-05-08 |  | 2019-05-26 | 2019-05-20 | 2019-07-30 |  | 2019-05-21 | 2019-07-02 | [7 empty] | 2019-07-06 | 2019-06-18 |  | 2019-07-20 | 2019-06-18 |  | 2019-07-22 | 2019-08-27
2019-07-01 | MI21A-BW-6A | 2019-04-16 |  | 2019-05-12 | 2019-06-07 |  | 2019-05-26 | 2019-05-24 |  | 2019-05-22 | 2019-06-07 |  | 2019-05-21 | 2019-05-02 | 2019-07-27 |  | 2019-06-25 | 2019-06-14 | [7 empty] | 2019-06-20 | 2019-06-05 |  | 2019-06-22 | 2019-08-28 |  | 2019-08-02 | 2019-08-07
2019-07-01 | MI21B-BW-6A | 2019-04-03 |  | 2019-06-02 | 2019-03-26 |  | 2019-04-07 | 2019-05-30 |  | 2019-05-16 | 2019-04-11 |  | 2019-05-23 | 2019-05-28 | 2019-08-17 |  | 2019-05-03 | 2019-06-02 | [7 empty] | 2019-07-05 | 2019-06-20 |  | 2019-06-04 | 2019-07-11 |  | 2019-12-08 | 2019-12-24
2019-07-01 | MI23A-BW-6A | 2019-05-19 |  |  | 2019-03-30 |  |  | 2019-05-03 |  |  | 2019-06-28 |  |  | 2019-06-13 |  |  | 2019-06-20 | [8 empty] | 2019-06-13 |  |  | 2019-06-09 |  |  | 2019-11-27 | 2019-12-25
2019-07-01 | MI23B-BW-6A | 2019-03-19 |  |  | 2019-04-16 |  |  | 2019-05-25 |  |  | 2019-04-03 |  |  | 2019-06-30 |  |  | 2019-05-03 | [8 empty] | 2019-07-03 |  |  | 2019-07-28 |  |  | 2019-09-26 | 2019-10-22
2019-07-01 | MI25A-BW-6A | 2019-04-29 |  | 2019-06-19 | 2019-04-21 |  | 2019-07-05 | 2019-07-19 | 2019-06-15 |  | 2019-06-05 | 2019-07-21 |  | 2019-06-09 | 2019-07-17 |  | 2019-06-28 | 2019-08-17 | [7 empty] | 2019-09-05 | 2019-09-06 |  | 2019-07-25 | 2019-11-10 |  | 2019-07-21 | 2019-06-22
2019-07-01 | MI25B-BW-6A | 2019-05-09 | 2019-05-22 |  | 2019-06-28 | 2019-08-14 |  | 2019-06-30 | 2019-08-28 |  | 2019-06-20 | 2019-09-18 |  | 2019-07-07 | 2019-08-16 |  | 2019-06-16 | 2019-08-17 | [7 empty] | 2019-09-05 | 2019-10-25 |  | 2019-07-20 | 2019-08-21 |  | 2019-07-02 | 2019-07-26
2019-07-01 | MI25C-BW-6A | 2019-07-28 |  |  | 2019-07-08 |  |  | 2019-08-09 |  |  | 2019-09-07 |  |  | 2019-08-21 |  |  | 2019-10-01 | [8 empty] | 2019-09-16 |  |  | 2019-10-28 |  |  | 2019-10-30 | 2019-11-21
2019-07-01 | MI26A-BW-6A | 2019-06-10 |  | 2019-05-22 | 2019-05-20 |  | 2019-05-23 | 2019-06-08 |  | 2019-05-22 | 2019-06-12 |  | 2019-07-03 | 2019-08-23 | 2019-08-22 |  | 2019-07-24 | 2019-08-16 | [7 empty] | 2019-08-08 | 2019-07-24 |  | 2019-10-02 | 2019-09-20 |  | 2019-07-25 | 2019-07-26
2019-07-01 | MI26B-BW-6A | 2019-06-02 |  | 2019-05-08 | 2019-05-16 |  | 2019-05-08 | 2019-05-28 |  | 2019-07-10 | 2019-08-10 |  | 2019-05-26 | 2019-09-01 | 2019-07-27 |  | 2019-08-03 | 2019-07-30 | [7 empty] | 2019-07-21 | 2019-07-28 |  | 2019-08-04 | 2019-08-22 |  | 2019-12-28 | 2019-12-29
2019-07-01 | MI27A-BW-6A | 2019-03-19 | 2019-05-21 |  | 2019-04-20 | 2019-07-26 |  | 2019-04-21 | 2019-06-10 |  | 2019-05-14 | 2019-09-09 |  | 2019-07-22 | 2019-07-14 |  | 2019-06-04 | 2019-08-26 | [7 empty] | 2019-09-19 | 2019-10-20 |  | 2019-08-24 | 2019-09-27 |  | 2019-06-17 | 2019-07-11
2019-07-01 | MI27B-BW-6A | 2019-04-04 | 2019-08-07 |  | 2019-06-09 | 2019-06-25 |  | 2019-06-21 | 2019-06-05 |  | 2019-05-21 | 2019-08-19 |  | 2019-08-10 | 2019-09-09 |  | 2019-07-09 | 2019-07-25 | [7 empty] | 2019-07-09 | 2019-09-12 |  | 2019-08-16 | 2019-09-26 |  | 2019-07-18 | 2019-06-22
2019-07-01 | MI35A-BW-6A | 2019-09-24 |  |  | 2019-10-31 |  |  | 2019-11-21 |  |  | 2019-11-18 |  |  | 2019-11-30 |  |  | 2019-12-23 | [8 empty] | 2019-12-26 |  |  | 2019-12-24 |  |  | 2019-10-03 | 2019-08-27
2019-07-01 | MI48A-BW-6A | [30 empty] | 2019-08-28 | 2019-09-07
2019-07-01 | MI61A-BW-6A |  | 2019-07-05 |  |  | 2019-06-24 |  |  | 2019-08-16 |  |  | 2019-09-06 |  |  | 2019-09-07 |  |  | 2019-10-26 |  |  | 2019-11-16 |  |  | 2019-11-04 |  |  | 2019-11-20 |  |  | 2019-12-15 |  | 2019-09-30 | 2019-09-11
2019-07-01 | MI62A-BW-6A |  | 2019-06-15 |  |  | 2019-07-28 |  |  | 2019-07-06 |  |  | 2019-09-09 |  |  | 2019-07-28 |  |  | 2019-08-11 |  |  | 2019-08-30 |  |  | 2019-08-15 |  |  | 2019-11-08 |  |  | 2019-11-14 |  | 2019-12-06 | 2019-11-27
2019-07-01 | LP01A-BW-6A | 2019-04-08 |  | 2019-03-19 | 2019-04-16 |  | 2019-03-05 | 2019-04-16 |  | 2019-02-06 | 2019-02-22 |  | 2019-05-04 | 2019-05-29 |  | 2019-04-03 | 2019-04-29 |  | 2019-04-14 | 2019-05-03 |  | 2019-05-16 | 2019-06-14 |  | 2019-05-11 | 2019-06-20 |  | 2019-04-20 | 2019-04-01 |  | 2019-06-03 | 2019-08-07 | 2019-08-08
2019-07-01 | LP01A-BW-6A | 2019-04-06 |  | 2019-04-16 | 2019-04-11 |  | 2019-02-24 | 2019-03-08 |  | 2019-03-23 | 2019-03-16 |  | 2019-04-20 | 2019-05-29 |  | 2019-03-25 | 2019-04-18 |  | 2019-04-09 | 2019-06-19 |  | 2019-04-23 | 2019-05-21 |  | 2019-05-17 | 2019-05-30 |  | 2019-04-29 | 2019-04-03 |  | 2019-06-23 | 2019-08-28 | 2019-07-28
2019-07-01 | LP01A-BW-6A | 2019-04-16 |  | 2019-03-07 | 2019-04-13 |  | 2019-02-22 | 2019-02-15 |  | 2019-02-12 | 2019-05-16 |  | 2019-03-10 | 2019-04-14 |  | 2019-05-04 | 2019-05-04 |  | 2019-03-13 | 2019-06-06 |  | 2019-05-22 | 2019-03-29 |  | 2019-05-18 | 2019-04-01 |  | 2019-04-22 | 2019-05-24 |  | 2019-07-02 | 2019-12-05 | 2019-12-06
2019-07-01 | LP01A-BW-6A | 2019-03-19 |  | 2019-04-13 | 2019-03-08 |  | 2019-04-19 | 2019-02-20 |  | 2019-02-16 | 2019-03-02 |  | 2019-03-18 | 2019-04-30 |  | 2019-03-15 | 2019-03-30 |  | 2019-05-14 | 2019-06-14 |  | 2019-06-14 | 2019-03-30 |  | 2019-05-23 | 2019-03-27 |  | 2019-05-13 | 2019-05-14 |  | 2019-06-01 | 2019-07-06 | 2019-06-19
2019-07-01 | LP01A-BW-6A | 2019-02-25 |  | 2019-02-23 | 2019-01-27 |  | 2019-01-31 | 2019-02-09 |  | 2019-04-07 | 2019-03-27 |  | 2019-04-03 | 2019-03-18 |  | 2019-04-08 | 2019-06-05 |  | 2019-05-27 | 2019-03-22 |  | 2019-05-16 | 2019-05-19 |  | 2019-06-13 | 2019-05-16 |  | 2019-04-09 | 2019-06-05 |  | 2019-06-02 | 2019-11-11 | 2019-11-19
2019-07-01 | LP01A-BW-6A | 2019-04-09 |  | 2019-02-07 | 2019-03-16 |  | 2019-04-11 | 2019-02-15 |  | 2019-03-30 | 2019-04-03 |  | 2019-04-13 | 2019-03-21 |  | 2019-03-08 | 2019-03-10 |  | 2019-04-10 | 2019-04-12 |  | 2019-06-02 | 2019-05-18 |  | 2019-03-28 | 2019-05-14 |  | 2019-04-02 | 2019-04-18 |  | 2019-05-03 | 2019-09-25 | 2019-09-11
2019-07-01 | LP02A-BW-6A | 2019-02-25 |  | 2019-01-31 | 2019-02-11 |  | 2019-02-12 | 2019-03-21 |  | 2019-04-26 | 2019-04-12 |  | 2019-05-08 |  |  | 2019-06-25 | 2019-06-26 |  | 2019-04-25 | 2019-06-05 |  | 2019-07-10 | 2019-06-19 |  | 2019-06-07 | 2019-06-28 |  | 2019-07-29 | 2019-06-29 |  | 2019-05-07 | 2019-11-05 | 2019-10-12
2019-07-01 | LP02A-BW-6A | 2019-02-12 |  | 2019-02-22 | 2019-02-06 |  | 2019-01-30 | 2019-02-21 |  | 2019-04-14 | 2019-05-23 |  | 2019-04-07 |  |  | 2019-05-18 | 2019-05-04 |  | 2019-07-04 | 2019-06-02 |  | 2019-06-29 | 2019-07-18 |  | 2019-07-06 | 2019-05-22 |  | 2019-06-30 | 2019-07-28 |  | 2019-06-08 | 2019-08-24 | 2019-07-24
2019-07-01 | LP02A-BW-6A | 2019-01-25 |  | 2019-04-05 | 2019-04-19 |  | 2019-02-11 | 2019-02-27 |  | 2019-02-21 | 2019-04-09 |  | 2019-05-21 |  |  | 2019-06-17 | 2019-04-14 |  | 2019-06-11 | 2019-06-14 |  | 2019-05-05 | 2019-05-20 |  | 2019-07-04 | 2019-06-28 |  | 2019-05-07 | 2019-06-22 |  | 2019-05-28 | 2019-12-18 | 2020-01-27
2019-07-01 | LP04A-BW-6A | 2019-04-09 |  | 2019-04-24 | 2019-03-12 |  | 2019-01-29 | 2019-02-11 |  | 2019-04-14 | 2019-03-27 |  | 2019-04-07 | 2019-05-26 |  | 2019-04-27 | 2019-04-13 |  | 2019-05-31 | 2019-05-20 |  | 2019-04-08 | 2019-05-27 |  | 2019-05-30 | 2019-05-12 |  | 2019-05-03 | 2019-06-08 |  | 2019-04-17 | 2019-12-18 | 2019-11-24
2019-07-01 | LP04A-BW-6A | 2019-03-23 |  | 2019-03-30 | 2019-02-25 |  | 2019-02-22 | 2019-03-16 |  | 2019-03-05 | 2019-04-03 |  | 2019-02-21 | 2019-05-13 |  | 2019-04-28 | 2019-03-24 |  | 2019-04-24 | 2019-05-16 |  | 2019-04-12 | 2019-05-05 |  | 2019-04-28 | 2019-05-25 |  | 2019-05-11 | 2019-04-23 |  | 2019-04-08 | 2019-06-02 | 2019-07-11
2019-07-01 | LP04A-BW-6A | 2019-02-23 |  | 2019-04-23 | 2019-02-26 |  | 2019-03-07 | 2019-04-04 |  | 2019-02-05 | 2019-02-25 |  | 2019-04-21 | 2019-05-11 |  | 2019-06-08 | 2019-06-07 |  | 2019-04-23 | 2019-06-19 |  | 2019-04-08 | 2019-04-14 |  | 2019-04-15 | 2019-03-30 |  | 2019-04-19 | 2019-04-18 |  | 2019-06-12 | 2019-09-28 | 2019-10-07
2019-07-01 | NT01A-BW-6A |  | 2019-07-11 |  |  | 2019-07-31 |  |  | 2019-07-19 |  |  | 2019-08-16 |  |  | 2019-10-04 |  |  | 2019-09-09 | [8 empty] | 2019-10-26 |  |  | 2019-11-15 |  | 2019-08-16 | 2019-08-14
2019-07-01 | NT01A-BW-6A |  | 2019-06-19 |  |  | 2019-08-17 |  |  | 2019-06-28 |  |  | 2019-08-24 |  |  | 2019-09-30 |  |  | 2019-09-06 | [8 empty] | 2019-09-26 |  |  | 2019-11-20 |  | 2019-11-13 | 2019-10-25
2019-07-01 | NT01A-BW-6A |  | 2019-06-14 |  |  | 2019-08-24 |  |  | 2019-06-23 |  |  | 2019-09-02 |  |  | 2019-08-21 |  |  | 2019-10-06 | [8 empty] | 2019-11-23 |  |  | 2019-11-06 |  | 2019-07-06 | 2019-07-12
2019-07-01 | NT01A-BW-6A |  | 2019-08-17 |  |  | 2019-06-06 |  |  | 2019-07-02 |  |  | 2019-10-08 |  |  | 2019-10-15 |  |  | 2019-10-23 | [8 empty] | 2019-11-25 |  |  | 2019-10-20 |  | 2019-11-10 | 2019-11-24
2019-07-01 | AX13A-EC-6A | 2018-02-21 |  | 2018-02-03 | 2018-01-31 |  | 2018-04-12 | 2018-03-09 |  | 2018-02-15 | 2018-04-29 |  | 2018-05-11 | 2018-06-16 |  | 2018-06-08 | 2018-05-11 |  | 2018-08-01 | 2018-10-24 |  | 2018-12-11 | 2019-01-31 |  | 2019-04-17 | 2019-01-10 |  | 2019-02-21 | 2019-01-31 |  | 2019-05-21 | 2019-10-01 | 2019-10-29
2019-07-01 | AX13A-EC-6A | 2018-04-12 |  | 2018-02-27 | 2018-04-05 |  | 2018-02-21 | 2018-02-05 |  | 2018-02-28 | 2018-04-20 |  | 2018-03-26 | 2018-07-28 |  | 2018-07-27 | 2018-06-30 |  | 2018-05-25 | 2019-01-12 |  | 2019-02-08 | 2019-01-06 |  | 2019-03-23 | 2019-02-22 |  | 2019-01-26 | 2018-12-19 |  | 2019-03-18 | 2019-06-26 | 2019-06-23
2019-07-01 | AX13A-EC-6A | 2018-02-04 |  | 2018-02-02 | 2018-04-07 |  | 2018-04-24 | 2018-02-21 |  | 2018-04-25 | 2018-03-19 |  | 2018-05-24 | 2018-07-18 |  | 2018-06-14 | 2018-05-14 |  | 2018-08-01 | 2019-01-01 |  | 2018-11-27 | 2018-12-22 |  | 2019-04-10 | 2019-02-24 |  | 2019-01-05 | 2019-01-25 |  | 2019-03-06 | 2019-08-06 | 2019-07-22
2019-07-01 | AX13A-EC-6A | 2018-04-14 |  | 2018-03-28 | 2018-01-27 |  | 2018-03-18 | 2018-02-20 |  | 2018-03-28 | 2018-05-22 |  | 2018-04-08 | 2018-07-09 |  | 2018-06-09 | 2018-07-02 |  | 2018-07-29 | 2018-11-05 |  | 2018-12-23 | 2019-02-22 |  | 2019-02-25 | 2019-01-09 |  | 2019-01-23 | 2019-02-19 |  | 2019-04-23 | 2019-06-06 | 2019-04-30
2019-07-01 | AX13A-EC-6A | 2018-03-27 |  | 2018-04-07 | 2018-02-15 |  | 2018-04-23 | 2018-03-24 |  | 2018-04-11 | 2018-04-24 |  | 2018-05-26 | 2018-06-15 |  | 2018-05-14 | 2018-07-23 |  | 2018-07-07 | 2018-11-15 |  | 2019-01-22 | 2019-02-24 |  | 2019-02-25 | 2019-02-20 |  | 2019-02-26 | 2019-02-08 |  | 2019-04-26 | 2019-11-06 | 2019-09-27
2019-07-01 | AX36A-EC-6A | 2019-01-26 |  | 2018-11-22 | 2018-11-03 |  | 2019-02-01 | 2018-11-04 |  | 2018-11-10 | 2019-02-22 |  | 2019-01-20 | 2019-02-25 |  | 2019-04-07 | 2019-03-29 |  | 2019-04-23 | 2019-02-20 |  | 2019-06-22 | 2019-05-02 |  | 2019-07-08 | 2019-05-20 |  | 2019-05-20 | 2019-03-14 |  | 2019-06-11 | 2019-08-22 | 2019-09-16
2019-07-01 | AX36A-EC-6A | 2019-01-15 |  | 2018-12-15 | 2019-01-23 |  | 2018-12-03 | 2019-01-05 |  | 2018-11-19 | 2019-01-31 |  | 2019-03-19 | 2019-02-05 |  | 2019-03-30 | 2019-02-18 |  | 2019-03-31 | 2019-04-12 |  | 2019-04-15 | 2019-05-10 |  | 2019-06-28 | 2019-05-26 |  | 2019-05-08 | 2019-05-30 |  | 2019-07-02 | 2019-07-19 | 2019-07-12
2019-07-01 | MI01A-EC-6A | 2019-01-07 |  | 2018-11-26 | 2018-11-30 |  | 2019-01-11 | 2019-02-18 |  | 2018-12-19 | 2019-03-07 |  | 2018-12-31 | [18 empty] | 2019-07-09 | 2019-07-15
2019-07-01 | MI01A-EC-6A | 2019-02-08 |  | 2018-12-12 | 2019-02-02 |  | 2018-11-05 | 2019-02-11 |  | 2018-12-03 | 2019-03-21 |  | 2019-02-23 | [18 empty] | 2019-08-27 | 2019-10-02
2019-07-01 | MI08A-EC-6A | [30 empty] | 2019-08-19 | 2019-09-02
2019-07-01 | MI25A-EC-6A | 2019-01-23 |  | 2018-12-29 | 2019-02-26 |  | 2019-02-05 | 2019-01-31 |  | 2019-04-12 | 2019-03-20 |  | 2019-02-17 | 2019-03-28 |  | 2019-06-02 | 2019-05-25 |  | 2019-04-14 | 2019-04-19 |  | 2019-05-25 | 2019-05-24 |  | 2019-06-13 | 2019-06-26 |  | 2019-05-13 | 2019-06-29 |  | 2019-05-05 | 2019-08-28 | 2019-07-27
2019-07-01 | MI26A-EC-6A | 2019-01-22 |  | 2019-03-12 | 2019-02-06 |  | 2019-01-04 | 2019-03-07 |  | 2019-02-12 | 2019-04-11 |  | 2019-03-01 | 2019-03-15 |  | 2019-03-28 | 2019-03-19 |  | 2019-04-22 | 2019-04-28 |  | 2019-05-18 | 2019-04-04 |  | 2019-06-24 | 2019-04-30 |  | 2019-05-31 | 2019-07-13 |  | 2019-05-04 | 2019-07-15 | 2019-07-31
2019-07-01 | MI48A-EC-6A | [30 empty] | 2019-06-27 | 2019-06-04
2019-07-01 | MI48A-EC-6A | [30 empty] | 2019-07-04 | 2019-06-13
2019-07-01 | RR01A-EC-6A | 2018-05-11 |  | 2018-06-05 | 2018-04-29 |  | 2018-05-31 | 2018-09-18 |  | 2018-08-20 | 2018-11-25 |  | 2018-10-07 | 2019-01-29 |  | 2018-12-25 | 2018-11-30 |  | 2019-03-12 | 2018-11-24 |  | 2019-04-19 | 2018-11-30 |  | 2019-03-23 | 2019-01-06 |  | 2019-05-16 | 2019-01-16 |  | 2019-03-26 | 2019-06-07 | 2019-05-26
2019-07-01 | RR01A-EC-6A | 2018-06-17 |  | 2018-05-15 | 2018-06-24 |  | 2018-04-17 | 2018-09-27 |  | 2018-08-15 | 2018-09-24 |  | 2018-11-22 | 2019-01-07 |  | 2019-03-12 | 2018-11-24 |  | 2019-02-24 | 2018-12-14 |  | 2019-04-09 | 2018-12-01 |  | 2019-03-22 | 2019-01-27 |  | 2019-05-17 | 2019-01-25 |  | 2019-04-18 | 2019-11-09 | 2019-12-19
2019-07-01 | RR01A-EC-6A | 2018-06-11 |  | 2018-05-27 | 2018-05-22 |  | 2018-04-21 | 2018-08-23 |  | 2018-09-14 | 2018-11-26 |  | 2018-09-14 | 2019-01-24 |  | 2019-03-04 | 2018-12-26 |  | 2019-02-08 | 2019-01-16 |  | 2019-03-07 | 2019-01-29 |  | 2019-05-13 | 2018-12-13 |  | 2019-05-22 | 2019-03-02 |  | 2019-06-02 | 2019-11-13 | 2019-11-09
2019-07-01 | RR20B-EC-6A | 2018-09-11 |  | 2018-10-03 | 2018-08-26 |  | 2018-08-20 | 2018-09-03 |  | 2018-10-02 | 2018-10-15 |  | 2018-11-10 | 2018-11-12 |  | 2019-02-05 | 2019-01-03 |  | 2019-02-08 | 2019-04-18 |  | 2019-03-26 | 2019-05-20 |  | 2019-05-21 | 2019-03-29 |  | 2019-06-03 | 2019-05-09 |  | 2019-04-08 | 2019-12-09 | 2020-01-05
2019-07-01 | RR20B-EC-6A | 2018-09-01 |  | 2018-10-13 | 2018-10-09 |  | 2018-09-06 | 2018-07-26 |  | 2018-08-24 | 2018-09-08 |  | 2018-09-15 | 2019-01-25 |  | 2019-02-19 | 2018-11-30 |  | 2019-02-02 | 2019-04-09 |  | 2019-04-08 | 2019-05-20 |  | 2019-05-07 | 2019-05-18 |  | 2019-05-13 | 2019-06-21 |  | 2019-05-12 | 2019-11-19 | 2019-12-06
2019-07-01 | LP01A-EC-6A | 2018-06-28 |  | 2018-07-08 | 2018-06-26 |  | 2018-07-11 | 2018-09-28 |  | 2018-08-13 | 2018-11-11 |  | 2018-10-30 | 2018-12-03 |  | 2018-10-06 | 2018-12-06 |  | 2018-11-26 | 2018-12-06 |  | 2019-01-16 | 2018-12-22 |  | 2019-03-07 | 2019-01-07 |  | 2019-03-03 | 2019-01-03 |  | 2019-04-08 | 2019-10-22 | 2019-11-07
2019-07-01 | LP01A-EC-6A | 2018-06-28 |  | 2018-07-09 | 2018-06-27 |  | 2018-07-31 | 2018-07-22 |  | 2018-08-19 | 2018-10-16 |  | 2018-11-08 | 2018-10-22 |  | 2018-11-08 | 2018-11-24 |  | 2018-10-30 | 2018-12-12 |  | 2018-12-08 | 2019-02-05 |  | 2019-03-19 | 2018-12-07 |  | 2019-01-22 | 2019-02-18 |  | 2019-04-20 | 2019-09-24 | 2019-10-11
2019-07-01 | LP01A-EC-6A | 2018-06-03 |  | 2018-07-17 | 2018-07-28 |  | 2018-07-23 | 2018-09-17 |  | 2018-09-01 | 2018-10-13 |  | 2018-08-18 | 2018-09-28 |  | 2018-11-29 | 2018-12-09 |  | 2018-10-31 | 2018-11-24 |  | 2018-12-04 | 2018-12-24 |  | 2019-03-26 | 2019-01-25 |  | 2019-03-12 | 2018-12-11 |  | 2019-05-21 | 2019-11-12 | 2019-12-12
2019-07-01 | LP01A-EC-6A | 2018-08-17 |  | 2018-06-22 | 2018-06-03 |  | 2018-08-22 | 2018-08-28 |  | 2018-08-26 | 2018-09-27 |  | 2018-09-26 | 2018-11-06 |  | 2018-11-20 | 2019-01-17 |  | 2019-01-08 | 2018-11-24 |  | 2018-11-18 | 2019-01-17 |  | 2019-02-12 | 2019-01-15 |  | 2019-03-17 | 2018-12-28 |  | 2019-03-23 | 2019-09-22 | 2019-09-14
2019-07-01 | LP01A-EC-6A | 2018-08-08 |  | 2018-06-20 | 2018-07-19 |  | 2018-06-17 | 2018-09-04 |  | 2018-10-02 | 2018-10-23 |  | 2018-09-16 | 2018-11-17 |  | 2018-10-12 | 2018-12-25 |  | 2019-01-01 | 2019-01-22 |  | 2018-12-06 | 2019-02-20 |  | 2019-04-04 | 2019-02-10 |  | 2019-01-21 | 2019-03-02 |  | 2019-03-25 | 2019-11-02 | 2019-10-15
2019-07-01 | LP01A-EC-6A | 2018-08-04 |  | 2018-07-18 | 2018-06-10 |  | 2018-07-12 | 2018-10-11 |  | 2018-08-19 | 2018-11-08 |  | 2018-09-19 | 2018-12-05 |  | 2018-10-19 | 2019-01-14 |  | 2018-11-19 | 2019-01-01 |  | 2019-01-22 | 2019-02-20 |  | 2019-04-08 | 2019-01-23 |  | 2019-03-07 | 2018-12-19 |  | 2019-04-22 | 2019-11-17 | 2019-12-22
2019-07-01 | LP01A-EC-6A | 2018-07-12 |  | 2018-08-17 | 2018-06-11 |  | 2018-07-29 | 2018-08-19 |  | 2018-10-04 | 2018-10-02 |  | 2018-10-22 | 2018-10-03 |  | 2018-10-19 | 2018-11-08 |  | 2018-10-20 | 2018-12-13 |  | 2019-02-03 | 2019-02-03 |  | 2019-03-23 | 2019-02-01 |  | 2019-02-07 | 2018-12-18 |  | 2019-05-18 | 2019-08-02 | 2019-07-02
2019-07-01 | LP01A-EC-6A | 2018-05-22 |  | 2018-06-29 | 2018-07-18 |  | 2018-08-02 | 2018-07-24 |  | 2018-08-04 | 2018-10-17 |  | 2018-08-13 | 2018-11-29 |  | 2018-10-20 | 2018-11-27 |  | 2018-11-23 | 2018-11-21 |  | 2018-12-16 | 2019-01-16 |  | 2019-03-13 | 2018-12-12 |  | 2019-01-07 | 2019-01-14 |  | 2019-04-05 | 2019-10-18 | 2019-09-12
2019-07-01 | LP01A-EC-6A | 2018-07-04 |  | 2018-05-30 | 2018-06-03 |  | 2018-07-27 | 2018-09-29 |  | 2018-08-10 | 2018-09-12 |  | 2018-09-17 | 2018-11-17 |  | 2018-12-18 | 2018-12-04 |  | 2018-11-28 | 2018-12-16 |  | 2018-12-26 | 2019-02-04 |  | 2019-03-16 | 2019-01-23 |  | 2019-03-17 | 2019-02-17 |  | 2019-03-09 | 2019-10-02 | 2019-10-19
2019-07-01 | LP01A-EC-6A | 2018-05-23 |  | 2018-06-26 | 2018-06-29 |  | 2018-06-08 | 2018-09-18 |  | 2018-09-14 | 2018-09-22 |  | 2018-08-28 | 2018-12-08 |  | 2018-10-10 | 2019-01-05 |  | 2018-11-28 | 2018-11-02 |  | 2019-01-03 | 2019-02-14 |  | 2019-05-08 | 2019-01-12 |  | 2019-01-15 | 2019-01-16 |  | 2019-05-13 | 2019-10-09 | 2019-09-21
2019-07-01 | LP01A-EC-6A | 2018-08-15 |  | 2018-07-08 | 2018-08-13 |  | 2018-06-18 | 2018-09-19 |  | 2018-09-11 | 2018-10-11 |  | 2018-09-05 | 2018-12-18 |  | 2018-11-25 | 2018-12-01 |  | 2018-12-07 | 2018-10-26 |  | 2018-12-08 | 2019-02-12 |  | 2019-04-05 | 2019-02-16 |  | 2019-01-22 | 2019-01-08 |  | 2019-04-13 | 2019-12-13 | 2020-01-09
2019-07-01 | LP01A-EC-6A | 2018-07-29 |  | 2018-07-15 | 2018-06-04 |  | 2018-07-19 | 2018-07-24 |  | 2018-08-23 | 2018-09-22 |  | 2018-08-20 | 2018-12-22 |  | 2018-12-21 | 2018-12-15 |  | 2018-12-30 | 2018-11-30 |  | 2018-12-07 | 2018-12-14 |  | 2019-02-18 | 2019-01-12 |  | 2019-02-22 | 2019-01-04 |  | 2019-03-25 | 2019-08-10 | 2019-09-11
2019-07-01 | LP02A-EC-6A | 2018-08-06 |  | 2018-08-10 | 2018-07-20 |  | 2018-07-20 | 2018-08-05 |  | 2018-10-24 | 2018-10-20 |  | 2018-09-16 | 2018-11-28 |  | 2019-01-02 | 2019-01-19 |  | 2018-12-14 | 2019-01-15 |  | 2018-11-29 | 2019-01-05 |  | 2018-12-21 | 2019-03-02 |  | 2019-02-07 | 2019-03-15 |  | 2019-02-17 | 2019-06-15 | 2019-05-18
2019-07-01 | LP02A-EC-6A | 2018-06-23 |  | 2018-07-26 | 2018-06-25 |  | 2018-08-01 | 2018-09-29 |  | 2018-09-18 | 2018-10-06 |  | 2018-09-16 | 2018-12-24 |  | 2018-11-30 | 2018-11-14 |  | 2018-12-31 | 2019-01-13 |  | 2019-01-11 | 2018-12-03 |  | 2019-02-17 | 2019-03-08 |  | 2019-01-30 | 2019-01-09 |  | 2019-02-04 | 2019-08-27 | 2019-07-22
2019-07-01 | LP02A-EC-6A | 2018-06-05 |  | 2018-05-25 | 2018-07-14 |  | 2018-06-22 | 2018-08-23 |  | 2018-08-06 | 2018-11-05 |  | 2018-09-18 | 2018-12-01 |  | 2018-11-28 | 2018-11-17 |  | 2019-01-26 | 2018-12-17 |  | 2019-01-23 | 2019-01-05 |  | 2019-02-05 | 2019-01-20 |  | 2019-03-11 | 2018-12-31 |  | 2019-02-02 | 2019-08-04 | 2019-09-01
2019-07-01 | LP02A-EC-6A | 2018-05-25 |  | 2018-07-15 | 2018-07-11 |  | 2018-06-22 | 2018-09-14 |  | 2018-10-05 | 2018-09-16 |  | 2018-09-18 | 2018-12-19 |  | 2018-12-21 | 2018-11-10 |  | 2018-11-15 | 2018-11-16 |  | 2019-01-06 | 2019-02-08 |  | 2019-01-02 | 2019-01-05 |  | 2019-01-28 | 2019-01-27 |  | 2019-03-10 | 2019-06-26 | 2019-05-21
2019-07-01 | LP02A-EC-6A | 2018-08-12 |  | 2018-07-20 | 2018-06-11 |  | 2018-08-15 | 2018-08-03 |  | 2018-08-22 | 2018-12-07 |  | 2018-10-26 | 2019-01-09 |  | 2018-12-12 | 2019-01-12 |  | 2019-01-15 | 2018-12-17 |  | 2019-01-25 | 2019-01-10 |  | 2019-02-03 | 2019-03-05 |  | 2019-03-02 | 2019-03-06 |  | 2019-02-09 | 2019-06-10 | 2019-05-14
2019-07-01 | LP02A-EC-6A | 2018-06-22 |  | 2018-05-23 | 2018-07-15 |  | 2018-06-13 | 2018-10-21 |  | 2018-08-31 | 2018-10-10 |  | 2018-09-15 | 2018-11-27 |  | 2018-12-15 | 2018-11-04 |  | 2019-01-10 | 2018-11-17 |  | 2018-11-18 | 2018-12-09 |  | 2019-01-03 | 2019-02-19 |  | 2019-03-10 | 2019-02-13 |  | 2019-02-01 | 2019-08-06 | 2019-06-28
2019-07-01 | LP02A-EC-6A | 2018-06-10 |  | 2018-08-17 | 2018-06-14 |  | 2018-08-04 | 2018-08-17 |  | 2018-08-30 | 2018-11-15 |  | 2018-11-25 | 2019-01-30 |  | 2019-01-20 | 2018-11-28 |  | 2018-11-14 | 2018-12-31 |  | 2019-01-21 | 2019-02-04 |  | 2018-12-06 | 2018-12-18 |  | 2019-01-29 | 2019-03-03 |  | 2019-02-14 | 2019-09-23 | 2019-10-06
2019-07-01 | LP06A-EC-6A | 2018-11-07 |  | 2018-12-20 | 2018-10-19 |  | 2018-11-07 | 2018-10-12 |  | 2018-10-26 | 2019-01-13 |  | 2019-02-02 | 2018-12-24 |  | 2019-02-09 | 2019-02-09 |  | 2019-02-15 | 2019-01-06 |  | 2019-07-03 | 2019-02-11 |  | 2019-05-07 | 2019-02-19 |  | 2019-05-12 | 2019-03-06 |  | 2019-07-03 | 2019-07-10 | 2019-08-19
2019-07-01 | LP06A-EC-6A | 2018-11-23 |  | 2018-10-10 | 2018-11-21 |  | 2018-12-21 | 2018-12-05 |  | 2018-11-25 | 2018-11-16 |  | 2019-01-01 | 2018-12-22 |  | 2019-04-20 | 2019-01-22 |  | 2019-03-09 | 2019-03-26 |  | 2019-06-21 | 2019-04-06 |  | 2019-04-08 | 2019-04-16 |  | 2019-04-18 | 2019-02-14 |  | 2019-05-16 | 2019-10-23 | 2019-10-20
2019-07-01 | LP06A-EC-6A | 2018-11-23 |  | 2018-12-21 | 2019-01-01 |  | 2018-10-24 | 2018-10-18 |  | 2018-12-22 | 2019-01-30 |  | 2019-01-07 | 2019-02-21 |  | 2019-03-29 | 2019-02-01 |  | 2019-02-21 | 2019-01-27 |  | 2019-04-24 | 2019-03-31 |  | 2019-06-16 | 2019-01-23 |  | 2019-04-11 | 2019-04-06 |  | 2019-04-21 | 2019-08-01 | 2019-06-23
2019-07-01 | LP08A-EC-6A | 2019-06-03 |  | 2019-06-30 | 2019-05-09 |  | 2019-07-28 | 2019-07-13 |  | 2019-07-25 | 2019-06-06 | 2019-08-19 |  | 2019-09-28 | 2019-10-03 |  | 2019-09-28 | 2019-09-29 |  | 2019-07-29 | 2019-07-31 |  | 2019-09-21 | 2019-10-19 |  | 2019-08-24 | 2019-09-19 |  | 2019-10-25 | 2019-09-25 |  | 2019-07-17 | 2019-06-08
2019-07-01 | LP08A-EC-6A | 2019-06-01 |  | 2019-06-07 | 2019-07-10 |  | 2019-06-24 | 2019-07-09 |  | 2019-07-03 | 2019-07-25 | 2019-06-19 |  | 2019-09-12 | 2019-07-24 |  | 2019-07-22 | 2019-09-19 |  | 2019-09-21 | 2019-10-13 |  | 2019-10-15 | 2019-10-02 |  | 2019-08-21 | 2019-09-18 |  | 2019-11-03 | 2019-08-21 |  | 2019-06-05 | 2019-06-27
2019-07-01 | LP10A-EC-6A | 2018-12-31 |  | 2019-01-05 | 2018-12-09 |  | 2018-12-29 | 2019-01-18 |  | 2019-03-15 | 2019-03-27 |  | 2019-04-10 | 2019-05-12 |  | 2019-04-23 | 2019-05-12 |  | 2019-05-09 | 2019-04-23 | 2019-08-06 |  | 2019-03-30 | 2019-06-01 |  | 2019-05-14 |  | 2019-05-10 | 2019-05-25 | 2019-07-21 |  | 2019-12-28 | 2019-12-17
2019-07-01 | LP10A-EC-6A | 2019-01-27 |  | 2019-01-29 | 2019-01-06 |  | 2019-02-09 | 2018-12-30 |  | 2019-01-04 | 2019-03-19 |  | 2019-04-20 | 2019-05-11 |  | 2019-05-05 | 2019-04-03 |  | 2019-06-04 | 2019-05-07 | 2019-05-20 |  | 2019-05-13 | 2019-05-26 |  | 2019-05-05 |  | 2019-06-19 | 2019-06-02 | 2019-06-05 |  | 2019-06-19 | 2019-07-12
2019-07-01 | LP11A-EC-6A | 2019-01-15 |  | 2018-12-09 | 2019-02-21 |  | 2019-03-12 | 2019-01-10 |  | 2019-03-04 | 2019-04-01 |  | 2019-04-25 | 2019-06-01 |  | 2019-06-30 | 2019-04-18 |  | 2019-06-03 | 2019-07-06 |  | 2019-07-09 | 2019-07-06 |  | 2019-07-09 | 2019-06-08 |  | 2019-05-05 | 2019-05-21 |  | 2019-05-05 | 2019-06-27 | 2019-06-30
2019-07-01 | LP12A-EC-6A |  |  | 2019-03-21 |  |  | 2019-03-21 |  |  | 2019-02-16 |  |  | 2019-02-26 |  |  | 2019-04-27 |  |  | 2019-05-08 |  |  | 2019-05-12 |  |  | 2019-04-04 |  |  | 2019-06-25 |  |  | 2019-05-19 | 2019-10-15 | 2019-09-09
2019-07-01 | LP12A-EC-6A |  |  | 2019-03-03 |  |  | 2019-03-13 |  |  | 2019-02-22 |  |  | 2019-02-02 |  |  | 2019-04-14 |  |  | 2019-04-06 |  |  | 2019-05-13 |  |  | 2019-06-16 |  |  | 2019-05-12 |  |  | 2019-05-30 | 2019-11-22 | 2019-12-27
2019-07-01 | LP32A-EC-6A | 2019-06-03 |  | 2019-04-25 | 2019-06-05 |  | 2019-07-18 | 2019-07-29 |  | 2019-07-24 | 2019-07-15 | 2019-07-30 |  | 2019-10-01 | 2019-07-16 |  | 2019-09-08 | 2019-08-26 |  | 2019-08-29 | 2019-10-19 |  | 2019-09-20 | 2019-08-06 |  | 2019-08-12 | 2019-09-02 |  | 2019-10-02 | 2019-09-24 |  | 2019-10-10 | 2019-09-23
2019-07-01 | LP32A-EC-6A | 2019-05-22 |  | 2019-05-01 | 2019-07-19 |  | 2019-05-20 | 2019-06-24 |  | 2019-07-09 | 2019-08-24 | 2019-06-05 |  | 2019-10-03 | 2019-08-29 |  | 2019-08-30 | 2019-09-04 |  | 2019-08-19 | 2019-08-31 |  | 2019-08-19 | 2019-09-03 |  | 2019-08-22 | 2019-09-21 |  | 2019-08-26 | 2019-08-11 |  | 2019-07-21 | 2019-07-26
2019-07-01 | LP34A-EC-6A | 2019-08-05 | 2019-06-01 |  | 2019-05-21 | 2019-06-01 |  | 2019-08-05 | 2019-07-05 |  | 2019-07-14 | 2019-07-27 |  | 2019-08-23 | 2019-10-11 |  | 2019-10-27 | 2019-08-17 |  | 2019-10-22 | 2019-10-27 |  | 2019-11-11 | 2019-11-04 |  | 2019-11-02 | 2019-11-03 |  | 2019-10-31 | 2019-11-23 |  | 2019-12-12 | 2019-12-30
2019-07-01 | LP35A-EC-6A | 2019-04-25 |  | 2019-07-17 | 2019-06-26 |  | 2019-05-06 | 2019-07-24 |  | 2019-05-24 | 2019-08-21 | 2019-07-08 |  | 2019-09-27 | 2019-07-25 |  | 2019-08-31 | 2019-08-23 |  | 2019-10-08 | 2019-10-04 |  | 2019-07-24 | 2019-09-16 |  | 2019-10-22 | 2019-10-23 |  | 2019-11-02 | 2019-10-14 |  | 2019-06-15 | 2019-07-01
2019-07-01 | LP48A-EC-6A | 2019-05-20 |  | 2019-05-21 | 2019-07-13 |  | 2019-06-05 | 2019-04-30 |  | 2019-05-11 | 2019-08-20 | 2019-08-06 |  | 2019-08-30 | 2019-10-17 |  | 2019-10-09 | 2019-10-19 |  | 2019-09-25 | 2019-08-13 |  | 2019-10-13 | 2019-09-01 |  | 2019-09-29 | 2019-09-30 |  | 2019-10-04 | 2019-09-17 |  | 2019-06-17 | 2019-06-21
2019-07-01 | LP48A-EC-6A | 2019-06-07 |  | 2019-05-23 | 2019-06-03 |  | 2019-05-06 | 2019-06-05 |  | 2019-07-13 | 2019-08-18 | 2019-07-11 |  | 2019-09-14 | 2019-10-20 |  | 2019-10-28 | 2019-09-15 |  | 2019-09-06 | 2019-08-27 |  | 2019-09-24 | 2019-11-01 |  | 2019-09-15 | 2019-10-11 |  | 2019-11-07 | 2019-08-30 |  | 2019-07-06 | 2019-07-16
2019-07-01 | LP49A-EC-6A | 2019-04-29 |  | 2019-07-02 | 2019-07-16 | 2019-05-14 |  | 2019-07-16 | 2019-07-08 |  | 2019-06-28 | 2019-07-16 |  | 2019-10-17 | 2019-10-15 |  | 2019-08-31 | 2019-09-28 |  | 2019-09-24 | 2019-11-23 |  | 2019-08-19 | 2019-09-13 |  | 2019-09-29 | 2019-11-12 |  | 2019-09-16 | 2019-10-01 |  | 2019-06-07 | 2019-06-04
2019-07-01 | LP49A-EC-6A | 2019-05-03 |  | 2019-06-20 | 2019-04-24 | 2019-06-23 |  | 2019-04-27 | 2019-05-31 |  | 2019-07-15 | 2019-09-17 |  | 2019-10-20 | 2019-09-12 |  | 2019-09-25 | 2019-10-19 |  | 2019-10-14 | 2019-10-05 |  | 2019-10-25 | 2019-12-01 |  | 2019-08-27 | 2019-09-19 |  | 2019-11-02 | 2019-11-26 |  | 2019-08-09 | 2019-08-01
2019-07-01 | LP51A-EC-6A | 2019-08-17 | 2019-05-25 |  | 2019-10-10 | 2019-07-12 |  | 2019-09-23 | 2019-08-13 |  | 2019-11-08 | 2019-08-19 |  | 2020-01-02 | 2019-10-12 |  | 2020-01-06 | 2019-11-01 |  | 2020-02-28 | 2019-10-26 |  | 2020-02-22 | 2019-11-27 |  | 2020-03-16 | 2020-01-17 |  | 2020-03-01 | 2019-11-30 |  | 2019-11-08 | 2019-10-04
2019-07-01 | LP62A-EC-6A | 2019-01-01 |  | 2019-02-06 | 2019-03-02 |  | 2019-03-07 | 2019-01-15 |  | 2019-01-29 | 2019-02-17 |  | 2019-04-01 | 2019-03-29 |  | 2019-06-19 | 2019-04-15 |  | 2019-05-09 | 2019-04-13 |  | 2019-06-11 | 2019-04-03 |  | 2019-06-06 | 2019-05-25 |  | 2019-06-22 | 2019-05-24 |  | 2019-07-08 | 2019-06-30 | 2019-06-11
2019-07-01 | LP65A-EC-6A | 2019-04-15 |  | 2019-03-11 | 2019-03-17 |  | 2019-04-27 | 2019-05-06 |  | 2019-06-09 | 2019-05-24 |  | 2019-07-08 | 2019-05-29 | 2019-06-27 |  | 2019-08-05 | 2019-08-08 |  | 2019-08-20 | 2019-06-09 |  | 2019-06-18 | 2019-07-25 |  | 2019-08-25 | 2019-08-20 |  | 2019-07-08 | 2019-08-23 |  | 2019-09-04 | 2019-08-12
2019-07-01 | LP66A-EC-6A | 2019-08-21 | 2019-06-19 |  | 2019-09-13 | 2019-08-22 |  | 2019-09-06 | 2019-08-17 |  | 2019-09-07 | 2019-10-27 |  | 2019-12-21 | 2019-12-15 |  | 2019-10-03 | 2019-12-19 |  | 2019-10-21 | 2019-12-26 |  | 2019-10-31 | 2019-10-19 |  | 2019-12-23 | 2019-10-24 |  | 2019-11-05 | 2019-11-26 |  | 2019-12-02 | 2020-01-10
2019-07-01 | LP66A-EC-6A | 2019-08-31 | 2019-09-03 |  | 2019-09-01 | 2019-06-27 |  | 2019-07-18 | 2019-08-23 |  | 2019-08-31 | 2019-08-04 |  | 2019-11-15 | 2019-10-16 |  | 2019-10-29 | 2019-10-28 |  | 2019-10-15 | 2019-11-03 |  | 2019-12-06 | 2019-10-22 |  | 2019-12-13 | 2019-10-27 |  | 2019-12-09 | 2019-10-30 |  | 2019-11-11 | 2019-10-16
2019-07-01 | AL88A-PL-6A | 2018-03-06 |  | 2018-03-27 | 2018-03-13 |  | 2018-04-26 | 2018-02-28 |  | 2018-04-12 | 2018-06-03 |  | 2018-05-12 | 2018-09-17 |  | 2018-11-22 | 2019-01-17 |  | 2019-01-21 | 2019-01-14 |  | 2019-01-25 | 2019-01-07 |  | 2019-03-29 | 2019-02-15 | 2019-07-24 |  | 2019-01-18 | 2019-08-07 |  | 2019-08-22 | 2019-09-22
2019-07-01 | NT01A-PL-6A | 2018-03-24 |  | 2018-03-19 | 2018-04-14 |  | 2018-03-15 | 2018-04-30 |  | 2018-03-22 | 2018-06-28 |  | 2018-08-05 | 2018-09-24 |  | 2018-11-08 | 2018-10-31 |  | 2018-11-29 | 2018-09-22 |  | 2018-11-29 | 2018-12-03 |  | 2019-01-16 | 2019-03-04 |  | 2018-12-11 | 2019-01-24 |  | 2019-03-05 | 2019-09-09 | 2019-10-02
2019-07-01 | NT01A-PL-6A | 2018-03-07 |  | 2018-03-30 | 2018-05-23 |  | 2018-03-16 | 2018-03-08 |  | 2018-03-15 | 2018-06-01 |  | 2018-07-15 | 2018-10-29 |  | 2018-09-26 | 2018-11-17 |  | 2018-09-29 | 2018-10-05 |  | 2018-11-27 | 2018-12-13 |  | 2019-02-01 | 2019-02-12 |  | 2019-02-28 | 2019-01-29 |  | 2019-01-27 | 2019-10-03 | 2019-09-07
2019-07-01 | NT01A-PL-6A | 2018-03-15 |  | 2018-04-03 | 2018-05-02 |  | 2018-04-06 | 2018-05-26 |  | 2018-05-04 | 2018-06-21 |  | 2018-08-15 | 2018-09-23 |  | 2018-11-13 | 2018-10-06 |  | 2018-09-15 | 2018-09-28 |  | 2019-02-01 | 2019-01-04 |  | 2018-11-21 | 2019-03-10 |  | 2019-01-01 | 2019-01-01 |  | 2019-03-05 | 2019-10-03 | 2019-09-01
2019-07-01 | NT01A-PL-6A | 2018-02-26 |  | 2018-04-25 | 2018-03-31 |  | 2018-04-29 | 2018-03-25 |  | 2018-05-06 | 2018-08-13 |  | 2018-08-10 | 2018-08-29 |  | 2018-10-09 | 2018-09-18 |  | 2018-10-23 | 2018-09-29 |  | 2018-11-17 | 2018-12-31 |  | 2018-12-09 | 2019-02-21 |  | 2019-02-22 | 2019-01-20 |  | 2019-02-05 | 2019-11-07 | 2019-11-14
2019-07-01 | AX26A-IN-6A | 2018-01-23 |  | 2017-11-14 | 2017-12-27 |  | 2017-11-24 | 2017-12-29 |  | 2018-02-14 | 2018-04-01 |  | 2018-04-11 | 2018-04-26 |  | 2018-04-09 | 2018-04-25 |  | 2018-03-06 | 2018-05-31 |  | 2018-05-03 | 2018-04-13 |  | 2018-04-15 | 2018-06-28 |  | 2018-05-01 | 2018-07-21 |  | 2018-08-28 | 2019-06-16 | 2019-06-09
2019-07-01 | LP01A-IN-6A | 2017-11-29 |  | 2018-01-17 | 2018-02-02 |  | 2018-02-03 | 2018-02-02 |  | 2018-01-14 | 2018-03-09 |  | 2018-01-23 | 2018-04-28 |  | 2018-03-11 | 2018-05-31 |  | 2018-03-28 | 2018-06-04 |  | 2018-06-15 | 2018-04-01 |  | 2018-05-22 | 2018-06-28 |  | 2018-04-20 | 2018-05-09 |  | 2018-05-24 | 2019-12-24 | 2019-11-23
2019-07-01 | LP02A-IN-6A | 2018-02-12 |  | 2018-01-09 | 2017-12-25 |  | 2017-12-31 | 2018-01-09 |  | 2017-12-16 | 2018-04-03 |  | 2018-03-12 | 2018-05-24 |  | 2018-06-04 | 2018-04-22 |  | 2018-04-09 | 2018-06-13 |  | 2018-05-22 | 2018-03-25 |  | 2018-05-14 | 2018-05-02 |  | 2018-03-30 | 2018-06-23 |  | 2018-06-04 | 2019-10-19 | 2019-09-16
2019-07-01 | LP10A-IN-6A | 2018-01-06 |  | 2018-01-04 | 2018-02-07 |  | 2018-02-09 | 2018-01-21 |  | 2018-03-17 | 2018-05-01 |  | 2018-05-04 | 2018-04-14 |  | 2018-05-21 | 2018-07-06 |  | 2018-06-14 | 2018-06-26 |  | 2018-07-07 | 2018-07-17 |  | 2018-06-28 | 2018-07-06 |  | 2018-05-19 | 2018-08-14 |  | 2018-09-16 | 2019-08-29 | 2019-09-17
2019-07-01 | LP38A-IN-6A | 2018-01-15 |  | 2017-12-23 | 2018-02-13 |  | 2018-02-08 | 2018-03-07 |  | 2018-03-16 | 2018-02-05 |  | 2018-04-09 | 2018-05-03 |  | 2018-05-19 | 2018-05-09 |  | 2018-03-13 | 2018-06-06 |  | 2018-04-02 | 2018-05-07 |  | 2018-04-20 | 2018-05-17 |  | 2018-05-21 | 2018-08-29 |  | 2018-09-07 | 2019-12-08 | 2020-01-05
2019-07-01 | LP40A-IN-6A | 2018-04-24 |  | 2018-02-28 | 2018-02-22 |  | 2018-02-08 | 2018-04-01 |  | 2018-02-09 | 2018-05-13 |  | 2018-05-04 | 2018-06-17 |  | 2018-08-01 | 2018-06-30 |  | 2018-06-22 | 2018-07-24 |  | 2018-07-13 | 2018-09-23 |  | 2018-09-26 | 2018-08-15 |  | 2018-09-09 | 2018-08-31 |  | 2018-07-17 | 2019-11-05 | 2019-12-15
2019-07-01 | ZA01A-BS-6A | 2019-01-31 |  | 2019-02-12 | 2019-02-07 |  | 2019-02-15 | 2019-02-14 |  | 2019-02-15 | 2019-03-28 |  | 2019-04-02 | 2019-05-21 | 2019-05-08 |  | 2019-05-29 | 2019-05-08 |  | 2019-06-05 | 2019-05-15 |  | 2019-06-12 | 2019-05-22 |  | 2019-06-19 | 2019-05-30 |  | 2019-06-26 | 2019-06-06 |  | 2019-12-01 | 2020-01-02
2019-07-01 | ZA01B-BS-6A | 2019-02-15 |  | 2019-03-04 | 2019-02-22 |  | 2019-03-04 | 2019-03-01 |  | 2019-03-05 | 2019-04-12 |  | 2019-04-02 | 2019-06-06 | 2019-05-24 |  | 2019-06-13 | 2019-06-03 |  | 2019-06-20 | 2019-06-10 |  | 2019-06-27 | 2019-06-17 |  | 2019-07-04 | 2019-06-24 |  | 2019-07-11 | 2019-07-01 |  | 2019-07-14 | 2019-06-06
2019-07-01 | ZA04A-BS-6A | 2019-05-30 | 2019-05-30 |  | 2019-06-06 | 2019-06-06 |  | 2019-06-13 | 2019-06-13 |  | 2019-07-11 | 2019-07-11 |  | 2019-08-15 | 2019-08-15 |  | 2019-08-22 | 2019-08-22 |  | 2019-08-30 | 2019-08-29 |  | 2019-09-06 | 2019-09-05 |  | 2019-09-13 | 2019-09-12 |  | 2019-09-20 | 2019-09-19 |  | 2019-11-16 | 2019-10-19
2019-07-01 | ZA08A-BS-6A | 2019-10-24 | 2019-10-24 |  | 2019-10-31 | 2019-10-31 |  | 2019-11-07 | 2019-11-07 |  | 2019-12-05 | 2019-12-05 |  | 2020-01-17 | 2020-01-16 |  | 2020-01-24 | 2020-01-23 |  | 2020-01-31 | 2020-01-30 |  | 2020-02-07 | 2020-02-06 |  | 2020-02-14 | 2020-02-13 |  | 2020-02-21 | 2020-02-20 |  | 2019-09-18 | 2019-10-15
2019-07-01 | ZA09A-BS-6A | 2020-02-17 | 2020-02-17 |  | 2020-02-24 | 2020-02-24 |  | 2020-03-02 | 2020-03-02 |  | 2020-03-30 | 2020-03-30 |  | 2020-05-07 | 2020-05-07 |  | 2020-05-14 | 2020-05-14 |  | 2020-05-21 | 2020-05-21 |  | 2020-05-29 | 2020-05-28 |  | 2020-06-05 | 2020-06-04 |  | 2020-06-12 | 2020-06-11 |  | 2019-06-21 | 2019-06-24
2019-07-01 | ZA10A-BS-6A | 2020-03-26 | 2020-03-26 |  | 2020-04-02 | 2020-04-02 |  | 2020-04-09 | 2020-04-09 |  | 2020-05-12 | 2020-05-12 |  | 2020-06-17 | 2020-06-17 |  | 2020-06-24 | 2020-06-24 |  | 2020-07-01 | 2020-07-01 |  | 2020-07-08 | 2020-07-08 |  | 2020-07-15 | 2020-07-15 |  | 2020-07-22 | 2020-07-22 |  | 2019-11-24 | 2019-10-22
2019-07-01 | LY02A-BS-6A | 2019-02-01 |  | 2019-02-07 | 2019-02-08 |  | 2019-02-08 | 2019-02-15 |  | 2019-02-14 | 2019-03-15 |  | 2019-03-14 | 2019-04-23 | 2019-04-30 |  | 2019-04-30 | 2019-04-30 |  | 2019-05-08 | 2019-05-01 |  | 2019-05-15 | 2019-05-07 |  | 2019-05-22 | 2019-05-21 |  | 2019-05-30 | 2019-05-29 |  | 2019-08-20 | 2019-09-23
2019-07-01 | LY03A-BS-6A | 2019-01-10 |  | 2019-01-15 | 2019-01-17 |  | 2019-01-15 | 2019-01-24 |  | 2019-01-22 | 2019-03-07 |  | 2019-03-07 | 2019-04-29 | 2019-05-07 |  | 2019-05-07 | 2019-05-07 |  | 2019-05-14 | 2019-05-14 |  | 2019-05-21 | 2019-05-21 |  | 2019-05-29 | 2019-05-29 |  | 2019-06-05 | 2019-06-05 |  | 2019-10-03 | 2019-09-02
2019-07-01 | LY04A-BS-6A | 2018-11-13 |  | 2018-11-23 | 2018-11-20 |  | 2018-11-23 | 2018-11-27 |  | 2018-11-28 | 2019-01-02 |  | 2019-01-10 | 2019-02-06 |  | 2019-02-26 | 2019-02-13 |  | 2019-02-26 | 2019-02-20 |  | 2019-02-21 | 2019-04-03 | 2019-06-14 |  | 2019-04-03 | 2019-05-02 |  | 2019-04-10 | 2019-06-14 |  | 2019-09-13 | 2019-08-22
2019-07-01 | LY04B-BS-6A | 2018-11-13 |  | 2018-11-23 | 2018-11-20 |  | 2018-11-23 | 2018-11-27 |  | 2018-11-28 | 2019-01-02 |  | 2019-01-10 | 2019-02-06 |  | 2019-03-11 | 2019-02-13 |  | 2019-03-11 | 2019-02-20 |  | 2019-04-17 | 2019-02-27 | 2019-04-30 |  | 2019-03-06 |  | 2019-04-04 | 2019-03-13 | 2019-04-30 |  | 2019-08-07 | 2019-08-01
2019-07-01 | LY05A-BS-6A | 2019-10-16 | 2019-10-16 |  | 2019-10-23 | 2019-10-23 |  | 2019-10-30 | 2019-10-30 |  | 2019-12-11 | 2019-12-11 |  | 2020-02-06 | 2020-02-06 |  | 2020-02-13 | 2020-02-13 |  | 2020-02-20 | 2020-02-20 |  | 2020-02-27 | 2020-02-27 |  | 2020-03-05 | 2020-03-05 |  | 2020-03-12 | 2020-03-12 |  | 2019-11-11 | 2019-10-31
2019-07-01 | LY26A-BS-6A | 2017-12-12 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-12 | 2018-02-12 |  | 2018-02-12 | 2018-04-04 |  | 2018-04-04 | 2018-04-04 |  | 2018-04-04 | 2018-04-11 |  | 2018-04-11 | 2018-05-09 |  | 2018-05-09 | 2018-04-25 |  | 2018-04-25 | 2018-06-14 |  | 2018-06-14 | 2019-09-15 | 2019-10-16
2019-07-01 | LY26A-BS-6A | 2017-12-12 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-12 | 2018-02-12 |  | 2018-02-12 | 2018-04-04 |  | 2018-04-04 | 2018-04-04 |  | 2018-04-04 | 2018-04-11 |  | 2018-04-11 | 2018-05-09 |  | 2018-05-09 | 2018-04-25 |  | 2018-04-25 | 2018-06-14 |  | 2018-06-14 | 2019-11-04 | 2019-10-11
2019-07-01 | LY26A-BS-6A | 2017-12-12 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-12 | 2018-02-12 |  | 2018-02-12 | 2018-04-04 |  | 2018-04-04 | 2018-04-04 |  | 2018-04-04 | 2018-04-11 |  | 2018-04-11 | 2018-05-09 |  | 2018-05-09 | 2018-04-25 |  | 2018-04-25 | 2018-06-14 |  | 2018-06-14 | 2019-11-27 | 2019-12-23
2019-07-01 | LY26A-BS-6A | 2017-12-12 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-12 | 2018-02-12 |  | 2018-02-12 | 2018-04-04 |  | 2018-04-04 | 2018-04-04 |  | 2018-04-04 | 2018-04-11 |  | 2018-04-11 | 2018-05-09 |  | 2018-05-09 | 2018-04-25 |  | 2018-04-25 | 2018-06-14 |  | 2018-06-14 | 2019-06-15 | 2019-05-28
2019-07-01 | LY26A-BS-6A | 2017-12-12 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-12 | 2018-02-12 |  | 2018-02-12 | 2018-04-04 |  | 2018-04-04 | 2018-04-04 |  | 2018-04-04 | 2018-04-11 |  | 2018-04-11 | 2018-05-09 |  | 2018-05-09 | 2018-04-25 |  | 2018-04-25 | 2018-06-14 |  | 2018-06-14 | 2019-07-06 | 2019-07-23
2019-07-01 | LY26A-BS-6A | 2017-12-12 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-12 | 2018-02-12 |  | 2018-02-12 | 2018-04-04 |  | 2018-04-04 | 2018-04-04 |  | 2018-04-04 | 2018-04-11 |  | 2018-04-11 | 2018-05-09 |  | 2018-05-09 | 2018-04-25 |  | 2018-04-25 | 2018-06-14 |  | 2018-06-14 | 2019-08-21 | 2019-08-25
2019-07-01 | LY26A-BS-6A | 2017-12-12 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-12 | 2018-02-12 |  | 2018-02-12 | 2018-04-04 |  | 2018-04-04 | 2018-04-04 |  | 2018-04-04 | 2018-04-11 |  | 2018-04-11 | 2018-05-09 |  | 2018-05-09 | 2018-04-25 |  | 2018-04-25 | 2018-06-14 |  | 2018-06-14 | 2019-12-02 | 2019-12-19
2019-07-01 | LY29A-BS-6A | 2018-10-04 |  | 2018-10-04 | 2018-10-08 |  | 2018-10-08 | 2018-10-10 |  | 2018-10-10 | 2018-11-12 |  | 2018-11-30 | 2019-01-22 |  | 2019-03-09 | 2019-01-21 |  | 2019-03-09 | 2019-01-28 |  | 2019-03-06 | 2019-02-04 |  | 2019-04-01 | 2019-02-11 |  | 2019-03-27 | 2019-02-18 |  | 2019-04-03 | 2019-10-02 | 2019-09-13
2019-07-01 | LY29A-BS-6A | 2018-10-04 |  | 2018-10-04 | 2018-10-08 |  | 2018-10-08 | 2018-10-10 |  | 2018-10-10 | 2018-11-12 |  | 2018-11-30 | 2019-01-22 |  | 2019-03-09 | 2019-01-21 |  | 2019-03-09 | 2019-01-28 |  | 2019-03-06 | 2019-02-04 |  | 2019-04-01 | 2019-02-11 |  | 2019-03-27 | 2019-02-18 |  | 2019-04-03 | 2019-06-14 | 2019-07-11
2019-07-01 | LY29A-BS-6A | 2018-10-04 |  | 2018-10-04 | 2018-10-08 |  | 2018-10-08 | 2018-10-10 |  | 2018-10-10 | 2018-11-12 |  | 2018-11-30 | 2019-01-22 |  | 2019-03-09 | 2019-01-21 |  | 2019-03-09 | 2019-01-28 |  | 2019-03-06 | 2019-02-04 |  | 2019-04-01 | 2019-02-11 |  | 2019-03-27 | 2019-02-18 |  | 2019-04-03 | 2019-06-21 | 2019-05-16
2019-07-01 | LY30A-BS-6A | 2019-02-18 |  | 2019-03-29 | 2019-02-25 |  | 2019-04-09 | 2019-03-04 |  | 2019-04-11 | 2019-05-01 | 2019-05-24 |  | 2019-07-05 | 2019-07-05 |  | 2019-07-12 | 2019-07-05 |  | 2019-07-19 | 2019-07-05 |  | 2019-09-02 | 2019-08-16 |  | 2019-09-02 | 2019-08-16 |  | 2019-09-09 | 2019-08-23 |  | 2019-06-06 | 2019-05-01
2019-07-01 | LY31A-BS-6A | 2019-04-24 | 2019-05-22 |  | 2019-05-01 | 2019-05-30 |  | 2019-05-09 | 2019-06-06 |  | 2019-06-21 | 2019-07-18 |  | 2019-08-09 | 2019-09-06 |  | 2019-08-16 | 2019-09-13 |  | 2019-08-23 | 2019-09-20 |  | 2019-09-02 | 2019-09-27 |  | 2019-09-09 | 2019-10-04 |  | 2019-09-16 | 2019-10-11 |  | 2019-06-17 | 2019-05-10
2019-07-01 | LY32A-BS-6A | 2019-01-21 |  | 2019-03-27 | 2019-01-28 |  | 2019-03-28 | 2019-02-04 |  | 2019-03-29 | 2019-03-18 | 2019-05-07 |  | 2019-05-09 | 2019-06-26 |  | 2019-05-16 | 2019-07-03 |  | 2019-05-23 | 2019-07-10 |  | 2019-05-31 | 2019-07-17 |  | 2019-06-07 | 2019-07-24 |  | 2019-06-14 | 2019-07-31 |  | 2019-11-21 | 2019-11-15
2019-07-01 | LY33A-BS-6A | 2018-12-05 |  | 2019-01-24 | 2018-12-10 |  | 2019-01-24 | 2018-12-13 |  | 2019-01-28 | 2019-01-29 |  | 2019-02-22 | 2019-03-07 | 2019-05-09 |  | 2019-03-26 | 2019-05-09 |  | 2019-04-02 | 2019-05-16 |  | 2019-04-09 | 2019-05-23 |  | 2019-04-11 | 2019-05-17 |  | 2019-04-16 | 2019-05-24 |  | 2019-11-03 | 2019-12-01
2019-07-01 | LY33A-BS-6A | 2018-12-05 |  | 2019-01-24 | 2018-12-10 |  | 2019-01-24 | 2018-12-13 |  | 2019-01-28 | 2019-01-29 |  | 2019-02-22 | 2019-03-07 | 2019-05-09 |  | 2019-03-26 | 2019-05-09 |  | 2019-04-02 | 2019-05-16 |  | 2019-04-09 | 2019-05-23 |  | 2019-04-11 | 2019-05-17 |  | 2019-04-16 | 2019-05-24 |  | 2019-12-06 | 2019-12-04
2019-07-01 | LY33A-BS-6A | 2018-12-05 |  | 2019-01-24 | 2018-12-10 |  | 2019-01-24 | 2018-12-13 |  | 2019-01-28 | 2019-01-29 |  | 2019-02-22 | 2019-03-07 | 2019-05-09 |  | 2019-03-26 | 2019-05-09 |  | 2019-04-02 | 2019-05-16 |  | 2019-04-09 | 2019-05-23 |  | 2019-04-11 | 2019-05-17 |  | 2019-04-16 | 2019-05-24 |  | 2019-06-20 | 2019-06-03
2019-07-01 | LY33B-BS-6A | 2018-11-21 |  | 2018-12-21 | 2018-11-26 |  | 2018-12-24 | 2018-11-27 |  | 2018-12-24 | 2019-01-15 |  | 2019-01-29 | 2019-03-07 | 2019-04-29 |  | 2019-03-12 | 2019-04-29 |  | 2019-03-19 | 2019-05-07 |  | 2019-03-26 | 2019-05-14 |  | 2019-03-28 | 2019-05-07 |  | 2019-04-01 | 2019-05-14 |  | 2019-09-16 | 2019-10-16
2019-07-01 | LY33B-BS-6A | 2018-11-21 |  | 2018-12-21 | 2018-11-26 |  | 2018-12-24 | 2018-11-27 |  | 2018-12-24 | 2019-01-15 |  | 2019-01-29 | 2019-03-07 | 2019-04-29 |  | 2019-03-12 | 2019-04-29 |  | 2019-03-19 | 2019-05-07 |  | 2019-03-26 | 2019-05-14 |  | 2019-03-28 | 2019-05-07 |  | 2019-04-01 | 2019-05-14 |  | 2019-06-16 | 2019-06-21
2019-07-01 | LY33B-BS-6A | 2018-11-21 |  | 2018-12-21 | 2018-11-26 |  | 2018-12-24 | 2018-11-27 |  | 2018-12-24 | 2019-01-15 |  | 2019-01-29 | 2019-03-07 | 2019-04-29 |  | 2019-03-12 | 2019-04-29 |  | 2019-03-19 | 2019-05-07 |  | 2019-03-26 | 2019-05-14 |  | 2019-03-28 | 2019-05-07 |  | 2019-04-01 | 2019-05-14 |  | 2019-12-19 | 2019-12-04
2019-07-01 | LY35A-BS-6A | 2018-12-11 |  | 2019-02-05 | 2018-12-13 |  | 2019-02-06 | 2018-12-20 |  | 2019-02-11 | 2019-01-20 |  | 2019-03-06 | 2019-03-25 | 2019-05-10 |  | 2019-04-01 | 2019-05-10 |  | 2019-04-08 | 2019-05-17 |  | 2019-04-15 | 2019-05-24 |  | 2019-04-11 | 2019-05-22 |  | 2019-04-15 | 2019-05-30 |  | 2019-06-18 | 2019-06-17
2019-07-01 | LY35A-BS-6A | 2018-12-11 |  | 2019-02-05 | 2018-12-13 |  | 2019-02-06 | 2018-12-20 |  | 2019-02-11 | 2019-01-20 |  | 2019-03-06 | 2019-03-25 | 2019-05-10 |  | 2019-04-01 | 2019-05-10 |  | 2019-04-08 | 2019-05-17 |  | 2019-04-15 | 2019-05-24 |  | 2019-04-11 | 2019-05-22 |  | 2019-04-15 | 2019-05-30 |  | 2019-10-24 | 2019-11-09
2019-07-01 | LY36A-BS-6A | 2018-10-29 |  | 2018-11-15 | 2018-11-05 |  | 2018-11-15 | 2018-11-12 |  | 2018-11-15 | 2019-01-15 |  | 2019-01-16 | 2019-03-19 | 2019-05-10 |  | 2019-03-05 | 2019-05-10 |  | 2019-03-12 | 2019-05-10 |  | 2019-03-19 | 2019-05-17 |  | 2019-03-21 | 2019-05-24 |  | 2019-03-25 | 2019-06-03 |  | 2019-10-17 | 2019-11-13
2019-07-01 | LY38A-BS-6A | 2018-08-20 |  | 2018-08-20 | 2018-08-23 |  | 2018-08-23 | 2018-08-29 |  | 2018-08-29 | 2018-10-12 |  | 2018-10-12 | 2018-11-30 |  | 2019-03-15 | 2018-12-07 |  | 2019-03-15 | 2018-12-14 | 2019-05-02 |  | 2018-12-21 | 2019-05-10 |  | 2019-04-29 | 2019-06-04 |  | 2019-05-07 | 2019-06-11 |  | 2019-09-23 | 2019-09-12
2019-07-01 | LY41A-BS-6A | 2019-05-15 | 2019-06-06 |  | 2019-05-22 | 2019-06-13 |  | 2019-05-30 | 2019-06-20 |  | 2019-06-27 | 2019-07-18 |  | 2019-08-01 | 2019-08-22 |  | 2019-08-08 | 2019-08-30 |  | 2019-08-15 | 2019-09-06 |  | 2019-08-22 | 2019-09-13 |  | 2019-08-30 | 2019-09-20 |  | 2019-09-06 | 2019-09-27 |  | 2019-08-14 | 2019-08-13
2019-07-01 | LY42A-BS-6A | 2018-08-18 |  | 2018-08-18 | 2018-08-20 |  | 2018-08-20 | 2018-08-31 |  | 2018-08-31 | 2018-10-12 |  | 2018-10-12 | 2018-11-30 |  | 2019-03-06 | 2018-12-07 |  | 2019-03-06 | 2018-12-14 |  | 2019-04-26 | 2018-12-21 | 2019-05-07 |  | 2019-01-07 | 2019-06-04 |  | 2019-01-14 | 2019-06-11 |  | 2019-10-20 | 2019-09-28
2019-07-01 | LY42A-BS-6A | 2018-08-18 |  | 2018-08-18 | 2018-08-20 |  | 2018-08-20 | 2018-08-31 |  | 2018-08-31 | 2018-10-12 |  | 2018-10-12 | 2018-11-30 |  | 2019-03-06 | 2018-12-07 |  | 2019-03-06 | 2018-12-14 |  | 2019-04-26 | 2018-12-21 | 2019-05-07 |  | 2019-01-07 | 2019-06-04 |  | 2019-01-14 | 2019-06-11 |  | 2019-12-14 | 2020-01-17
2019-07-01 | LY44A-BS-6A | 2019-01-29 |  | 2019-04-17 | 2019-02-05 |  | 2019-04-22 | 2019-02-12 |  | 2019-04-25 | 2019-03-26 | 2019-05-24 |  | 2019-05-17 | 2019-07-02 |  | 2019-05-24 | 2019-07-09 |  | 2019-06-03 | 2019-07-16 |  | 2019-06-10 | 2019-07-23 |  | 2019-06-17 | 2019-07-30 |  | 2019-06-24 | 2019-08-06 |  | 2019-10-28 | 2019-10-19
2019-07-01 | LY48A-BS-6A | 2019-02-14 |  | 2019-03-29 | 2019-02-21 |  | 2019-04-02 | 2019-02-28 |  | 2019-04-09 | 2019-04-11 | 2019-05-23 |  | 2019-06-05 | 2019-07-12 |  | 2019-06-12 | 2019-07-19 |  | 2019-06-19 | 2019-07-26 |  | 2019-06-26 | 2019-08-02 |  | 2019-07-03 | 2019-08-09 |  | 2019-07-10 | 2019-08-16 |  | 2019-08-15 | 2019-07-21
2019-07-01 | LY49A-BS-6A | 2019-01-24 |  | 2019-02-11 | 2019-01-31 |  | 2019-02-14 | 2019-02-07 |  | 2019-02-14 | 2019-03-21 |  | 2019-03-12 | 2019-05-14 | 2019-05-02 |  | 2019-05-21 | 2019-05-09 |  | 2019-05-29 | 2019-05-16 |  | 2019-07-10 | 2019-06-28 |  | 2019-07-10 | 2019-06-28 |  | 2019-07-17 | 2019-07-05 |  | 2019-09-23 | 2019-09-17
2019-07-01 | LY50A-BS-6A | 2018-11-28 |  | 2019-02-25 | 2018-12-05 |  | 2019-03-07 | 2018-12-12 |  | 2019-03-08 | 2019-01-31 | 2019-04-29 |  | 2019-03-21 | 2019-06-19 |  | 2019-03-28 | 2019-06-19 |  | 2019-04-04 | 2019-06-26 |  | 2019-04-11 | 2019-07-03 |  | 2019-04-18 | 2019-07-10 |  | 2019-04-29 | 2019-07-17 |  | 2019-09-30 | 2019-08-28
2019-07-01 | LY52A-BS-6A | 2019-03-06 | 2019-05-09 |  | 2019-03-13 | 2019-05-13 |  | 2019-03-20 | 2019-05-16 |  | 2019-05-03 | 2019-06-28 |  | 2019-06-25 | 2019-08-16 |  | 2019-07-02 | 2019-08-23 |  | 2019-07-09 | 2019-09-02 |  | 2019-07-16 | 2019-09-09 |  | 2019-07-23 | 2019-09-16 |  | 2019-07-30 | 2019-09-23 |  | 2019-06-11 | 2019-07-05
2019-07-01 | LY66A-BS-6A | 2018-06-29 |  | 2018-06-29 | 2018-07-05 |  | 2018-07-05 | 2018-07-12 |  | 2018-07-12 | 2018-08-13 |  | 2018-08-13 | 2018-10-25 |  | 2019-01-23 | 2018-11-01 |  | 2019-01-23 | 2018-11-08 |  | 2018-12-19 | 2018-11-15 |  | 2019-01-09 | 2018-11-22 |  | 2019-03-05 | 2018-11-29 |  | 2019-03-11 | 2019-10-19 | 2019-11-27
2019-07-01 | LY66A-BS-6A | 2018-06-29 |  | 2018-06-29 | 2018-07-05 |  | 2018-07-05 | 2018-07-12 |  | 2018-07-12 | 2018-08-13 |  | 2018-08-13 | 2018-10-25 |  | 2019-01-23 | 2018-11-01 |  | 2019-01-23 | 2018-11-08 |  | 2018-12-19 | 2018-11-15 |  | 2019-01-09 | 2018-11-22 |  | 2019-03-05 | 2018-11-29 |  | 2019-03-11 | 2019-08-22 | 2019-08-16
2019-07-01 | LY66B-BS-6A | 2018-07-02 |  | 2018-07-02 | 2018-07-05 |  | 2018-07-05 | 2018-07-12 |  | 2018-07-12 | 2018-08-13 |  | 2018-08-13 | 2018-10-25 |  | 2018-12-10 | 2018-11-01 |  | 2018-12-10 | 2018-11-08 |  | 2018-12-05 | 2018-11-15 |  | 2018-12-06 | 2018-11-22 |  | 2019-02-19 | 2018-11-29 |  | 2019-02-27 | 2019-11-10 | 2019-10-22
2019-07-01 | LY66B-BS-6A | 2018-07-02 |  | 2018-07-02 | 2018-07-05 |  | 2018-07-05 | 2018-07-12 |  | 2018-07-12 | 2018-08-13 |  | 2018-08-13 | 2018-10-25 |  | 2018-12-10 | 2018-11-01 |  | 2018-12-10 | 2018-11-08 |  | 2018-12-05 | 2018-11-15 |  | 2018-12-06 | 2018-11-22 |  | 2019-02-19 | 2018-11-29 |  | 2019-02-27 | 2019-06-07 | 2019-06-05
2019-07-01 | LY66B-BS-6A | 2018-07-02 |  | 2018-07-02 | 2018-07-05 |  | 2018-07-05 | 2018-07-12 |  | 2018-07-12 | 2018-08-13 |  | 2018-08-13 | 2018-10-25 |  | 2018-12-10 | 2018-11-01 |  | 2018-12-10 | 2018-11-08 |  | 2018-12-05 | 2018-11-15 |  | 2018-12-06 | 2018-11-22 |  | 2019-02-19 | 2018-11-29 |  | 2019-02-27 | 2019-12-10 | 2019-11-03
2019-07-01 | LY78A-BS-6A | 2018-06-11 |  | 2018-06-11 | 2018-06-27 |  | 2018-06-27 | 2018-07-03 |  | 2018-07-03 | 2018-08-02 |  | 2018-08-02 | 2018-10-18 |  | 2018-10-24 | 2018-10-11 |  | 2018-10-24 | 2018-11-22 |  | 2019-03-05 | 2018-11-29 |  | 2019-04-17 | 2019-07-12 | 2019-07-11 |  | 2019-07-19 | 2019-07-18 |  | 2019-08-20 | 2019-08-02
2019-07-01 | LY78B-BS-6A | 2018-06-11 |  | 2018-06-11 | 2018-06-12 |  | 2018-06-12 | 2018-07-03 |  | 2018-07-03 | 2018-07-27 |  | 2018-07-27 | 2018-10-11 |  | 2018-10-24 | 2018-10-11 |  | 2018-10-24 | 2018-11-22 |  | 2019-03-08 | 2018-11-29 |  | 2019-04-17 | 2019-07-12 | 2019-07-11 |  | 2019-07-19 | 2019-07-18 |  | 2019-06-24 | 2019-06-17
2019-07-01 | LY78C-BS-6A | 2019-02-28 | 2019-06-05 |  | 2019-03-07 | 2019-06-10 |  | 2019-03-14 | 2019-06-12 |  | 2019-04-29 | 2019-07-03 |  | 2019-06-19 | 2019-08-15 |  | 2019-06-26 | 2019-08-15 |  | 2019-07-03 | 2019-08-22 |  | 2019-07-10 | 2019-08-30 |  | 2019-07-17 | 2019-09-06 |  | 2019-07-24 | 2019-09-13 |  | 2019-08-03 | 2019-09-10
2019-07-01 | LY78C-BS-6A | 2019-02-28 | 2019-06-05 |  | 2019-03-07 | 2019-06-10 |  | 2019-03-14 | 2019-06-12 |  | 2019-04-29 | 2019-07-03 |  | 2019-06-19 | 2019-08-15 |  | 2019-06-26 | 2019-08-15 |  | 2019-07-03 | 2019-08-22 |  | 2019-07-10 | 2019-08-30 |  | 2019-07-17 | 2019-09-06 |  | 2019-07-24 | 2019-09-13 |  | 2019-06-22 | 2019-06-28
2019-07-01 | LY78D-BS-6A | 2019-02-28 | 2019-05-20 |  | 2019-03-07 | 2019-05-23 |  | 2019-03-14 | 2019-05-28 |  | 2019-04-29 | 2019-07-03 |  | 2019-06-19 | 2019-08-08 |  | 2019-06-26 | 2019-08-15 |  | 2019-07-03 | 2019-08-22 |  | 2019-07-10 | 2019-08-30 |  | 2019-07-17 | 2019-09-06 |  | 2019-07-24 | 2019-09-13 |  | 2019-09-27 | 2019-09-03
2019-07-01 | LY85A-BS-6A | 2019-10-08 | 2019-10-08 |  | 2019-10-15 | 2019-10-15 |  | 2019-10-22 | 2019-10-22 |  | 2019-12-03 | 2019-12-03 |  | 2020-01-29 | 2020-01-29 |  | 2020-02-05 | 2020-02-05 |  | 2020-02-12 | 2020-02-12 |  | 2020-02-19 | 2020-02-19 |  | 2020-02-26 | 2020-02-26 |  | 2020-03-04 | 2020-03-04 |  | 2019-12-25 | 2020-01-05
2019-07-01 | LY95A-BS-6A | 2018-11-30 |  | 2019-03-27 | 2018-12-07 |  | 2019-04-04 | 2018-12-14 |  | 2019-04-10 | 2019-01-21 | 2019-05-03 |  | 2019-02-25 | 2019-05-22 |  | 2019-03-04 | 2019-05-22 |  | 2019-03-11 | 2019-05-30 |  | 2019-04-24 | 2019-07-11 |  | 2019-04-24 | 2019-07-11 |  | 2019-05-01 | 2019-07-18 |  | 2019-09-22 | 2019-08-24
2019-07-01 | LY97A-BS-6A | 2019-02-04 | 2020-02-03 |  | 2019-02-11 | 2020-02-10 |  | 2019-02-18 | 2020-02-17 |  | 2019-04-01 | 2020-03-30 |  | 2019-05-23 | 2020-05-21 |  | 2019-05-31 | 2020-05-29 |  | 2019-06-07 | 2020-06-05 |  | 2019-06-14 | 2020-06-12 |  | 2019-06-21 | 2020-06-19 |  | 2019-06-28 | 2020-06-26 |  | 2019-10-03 | 2019-08-28
2019-07-01 | LY99A-BS-6A | 2019-08-09 | 2019-08-09 |  | 2019-08-16 | 2019-08-16 |  | 2019-08-23 | 2019-08-23 |  | 2019-10-07 | 2019-10-07 |  | 2019-11-25 | 2019-11-25 |  | 2019-12-02 | 2019-12-02 |  | 2019-12-09 | 2019-12-09 |  | 2019-12-16 | 2019-12-16 |  | 2019-12-23 | 2019-12-23 |  | 2020-01-07 | 2020-01-07 |  | 2019-08-20 | 2019-09-02
2019-07-01 | AL01A-BS-6A | 2018-05-29 |  | 2018-05-29 | 2018-05-31 |  | 2018-05-31 | 2018-06-07 |  | 2018-06-07 | 2018-08-13 |  | 2018-08-13 | 2018-11-14 |  | 2019-01-22 | 2018-11-21 |  | 2019-01-22 | 2018-11-28 |  | 2019-01-09 | 2018-12-05 |  | 2019-01-25 | 2018-12-12 |  | 2019-01-28 | 2018-12-19 |  | 2019-02-05 | 2019-10-09 | 2019-11-06
2019-07-01 | AL01A-BS-6A | 2018-05-29 |  | 2018-05-29 | 2018-05-31 |  | 2018-05-31 | 2018-06-07 |  | 2018-06-07 | 2018-08-13 |  | 2018-08-13 | 2018-11-14 |  | 2019-01-22 | 2018-11-21 |  | 2019-01-22 | 2018-11-28 |  | 2019-01-09 | 2018-12-05 |  | 2019-01-25 | 2018-12-12 |  | 2019-01-28 | 2018-12-19 |  | 2019-02-05 | 2019-06-24 | 2019-05-25
2019-07-01 | AL01A-BS-6A | 2018-05-29 |  | 2018-05-29 | 2018-05-31 |  | 2018-05-31 | 2018-06-07 |  | 2018-06-07 | 2018-08-13 |  | 2018-08-13 | 2018-11-14 |  | 2019-01-22 | 2018-11-21 |  | 2019-01-22 | 2018-11-28 |  | 2019-01-09 | 2018-12-05 |  | 2019-01-25 | 2018-12-12 |  | 2019-01-28 | 2018-12-19 |  | 2019-02-05 | 2019-10-17 | 2019-11-26
2019-07-01 | AL01A-BS-6A | 2018-05-29 |  | 2018-05-29 | 2018-05-31 |  | 2018-05-31 | 2018-06-07 |  | 2018-06-07 | 2018-08-13 |  | 2018-08-13 | 2018-11-14 |  | 2019-01-22 | 2018-11-21 |  | 2019-01-22 | 2018-11-28 |  | 2019-01-09 | 2018-12-05 |  | 2019-01-25 | 2018-12-12 |  | 2019-01-28 | 2018-12-19 |  | 2019-02-05 | 2019-11-29 | 2019-12-08
2019-07-01 | AL01A-BS-6A | 2018-05-29 |  | 2018-05-29 | 2018-05-31 |  | 2018-05-31 | 2018-06-07 |  | 2018-06-07 | 2018-08-13 |  | 2018-08-13 | 2018-11-14 |  | 2019-01-22 | 2018-11-21 |  | 2019-01-22 | 2018-11-28 |  | 2019-01-09 | 2018-12-05 |  | 2019-01-25 | 2018-12-12 |  | 2019-01-28 | 2018-12-19 |  | 2019-02-05 | 2019-12-16 | 2019-12-15
2019-07-01 | AL06A-BS-6A | 2018-04-04 |  | 2018-04-04 | 2018-04-04 |  | 2018-04-04 | 2018-05-17 |  | 2018-05-17 | 2018-07-19 |  | 2018-07-19 | 2018-10-24 |  | 2018-11-01 | 2018-10-31 |  | 2018-10-31 | 2018-11-07 |  | 2018-11-01 | 2018-11-14 |  | 2019-03-06 | 2018-11-21 |  | 2018-12-17 | 2019-01-09 |  | 2019-03-21 | 2019-08-03 | 2019-08-25
2019-07-01 | AL07A-BS-6A | 2019-10-09 | 2019-10-09 |  | 2019-10-16 | 2019-10-16 |  | 2019-10-23 | 2019-10-23 |  | 2019-12-04 | 2019-12-04 |  | 2020-01-30 | 2020-01-30 |  | 2020-02-06 | 2020-02-06 |  | 2020-02-13 | 2020-02-13 |  | 2020-02-20 | 2020-02-20 |  | 2020-02-27 | 2020-02-27 |  | 2020-03-05 | 2020-03-05 |  | 2019-08-28 | 2019-07-25
2019-07-01 | AL07A-BS-6A | 2019-10-09 | 2019-10-09 |  | 2019-10-16 | 2019-10-16 |  | 2019-10-23 | 2019-10-23 |  | 2019-12-04 | 2019-12-04 |  | 2020-01-30 | 2020-01-30 |  | 2020-02-06 | 2020-02-06 |  | 2020-02-13 | 2020-02-13 |  | 2020-02-20 | 2020-02-20 |  | 2020-02-27 | 2020-02-27 |  | 2020-03-05 | 2020-03-05 |  | 2019-06-12 | 2019-07-14
2019-07-01 | AL11A-BS-6A | 2018-07-11 |  | 2018-07-11 | 2018-07-12 |  | 2018-07-12 | 2018-07-18 |  | 2018-07-18 | 2018-08-22 |  | 2018-08-22 | 2018-11-16 |  | 2018-11-22 | 2018-11-28 |  | 2018-11-28 | 2018-12-05 |  | 2019-01-07 | 2018-12-12 |  | 2019-01-25 | 2019-01-16 |  | 2019-01-23 | 2019-01-23 |  | 2019-02-15 | 2019-08-21 | 2019-09-06
2019-07-01 | AL11A-BS-6A | 2018-07-11 |  | 2018-07-11 | 2018-07-12 |  | 2018-07-12 | 2018-07-18 |  | 2018-07-18 | 2018-08-22 |  | 2018-08-22 | 2018-11-16 |  | 2018-11-22 | 2018-11-28 |  | 2018-11-28 | 2018-12-05 |  | 2019-01-07 | 2018-12-12 |  | 2019-01-25 | 2019-01-16 |  | 2019-01-23 | 2019-01-23 |  | 2019-02-15 | 2019-06-14 | 2019-05-06
2019-07-01 | AL11A-BS-6A | 2018-07-11 |  | 2018-07-11 | 2018-07-12 |  | 2018-07-12 | 2018-07-18 |  | 2018-07-18 | 2018-08-22 |  | 2018-08-22 | 2018-11-16 |  | 2018-11-22 | 2018-11-28 |  | 2018-11-28 | 2018-12-05 |  | 2019-01-07 | 2018-12-12 |  | 2019-01-25 | 2019-01-16 |  | 2019-01-23 | 2019-01-23 |  | 2019-02-15 | 2019-11-22 | 2019-12-07
2019-07-01 | AL11A-BS-6A | 2018-07-11 |  | 2018-07-11 | 2018-07-12 |  | 2018-07-12 | 2018-07-18 |  | 2018-07-18 | 2018-08-22 |  | 2018-08-22 | 2018-11-16 |  | 2018-11-22 | 2018-11-28 |  | 2018-11-28 | 2018-12-05 |  | 2019-01-07 | 2018-12-12 |  | 2019-01-25 | 2019-01-16 |  | 2019-01-23 | 2019-01-23 |  | 2019-02-15 | 2019-09-18 | 2019-10-04
2019-07-01 | AL87A-BS-6A | 2018-11-13 |  | 2018-12-21 | 2018-11-16 |  | 2018-12-23 | 2018-11-20 |  | 2019-01-07 | 2018-12-04 |  | 2019-01-14 | 2018-12-13 |  | 2019-01-22 | 2018-12-18 |  | 2019-01-22 | [6 empty] | 2019-01-04 |  | 2019-02-21 | 2019-01-11 |  | 2019-02-26 | 2019-12-07 | 2019-12-10
2019-07-01 | AL88A-BS-6A | 2019-02-04 |  | 2019-02-25 | 2019-02-11 |  | 2019-02-27 | 2019-02-18 |  | 2019-02-28 | 2019-03-04 |  | 2019-03-18 | 2019-03-25 |  | 2019-03-22 | 2019-04-01 |  | 2019-03-25 | [6 empty] | 2019-04-08 | 2019-05-16 |  | 2019-04-15 | 2019-05-23 |  | 2019-11-02 | 2019-11-30
2019-07-01 | AL88A-BS-6A | 2019-02-04 |  | 2019-02-25 | 2019-02-11 |  | 2019-02-27 | 2019-02-18 |  | 2019-02-28 | 2019-03-04 |  | 2019-03-18 | 2019-03-25 |  | 2019-03-22 | 2019-04-01 |  | 2019-03-25 | [6 empty] | 2019-04-08 | 2019-05-16 |  | 2019-04-15 | 2019-05-23 |  | 2019-06-06 | 2019-05-22
2019-07-01 | AL89A-BS-6A | 2019-01-22 |  | 2019-02-26 | 2019-01-29 |  | 2019-02-27 | 2019-02-05 |  | 2019-02-28 | 2019-02-19 |  | 2019-03-08 | 2019-03-12 |  | 2019-03-15 | 2019-03-19 |  | 2019-03-15 | [6 empty] | 2019-03-26 |  | 2019-03-29 | 2019-04-02 |  | 2019-04-12 | 2019-10-09 | 2019-11-02
2019-07-01 | AL90A-BS-6A | 2018-11-23 |  | 2018-12-05 | 2018-11-30 |  | 2018-12-05 | 2018-12-07 |  | 2018-12-11 | 2019-02-11 |  | 2019-02-11 | 2019-04-15 | 2019-04-30 |  | 2019-04-24 | 2019-04-30 |  | 2019-05-01 | 2019-05-01 |  | 2019-05-09 | 2019-05-09 |  | 2019-05-16 | 2019-05-16 |  | 2019-05-23 | 2019-05-23 |  | 2019-11-22 | 2019-11-11
2019-07-01 | AL90A-BS-6A | 2018-11-23 |  | 2018-12-05 | 2018-11-30 |  | 2018-12-05 | 2018-12-07 |  | 2018-12-11 | 2019-02-11 |  | 2019-02-11 | 2019-04-15 | 2019-04-30 |  | 2019-04-24 | 2019-04-30 |  | 2019-05-01 | 2019-05-01 |  | 2019-05-09 | 2019-05-09 |  | 2019-05-16 | 2019-05-16 |  | 2019-05-23 | 2019-05-23 |  | 2019-09-27 | 2019-11-04
2019-07-01 | AL90A-BS-6A | 2018-11-23 |  | 2018-12-05 | 2018-11-30 |  | 2018-12-05 | 2018-12-07 |  | 2018-12-11 | 2019-02-11 |  | 2019-02-11 | 2019-04-15 | 2019-04-30 |  | 2019-04-24 | 2019-04-30 |  | 2019-05-01 | 2019-05-01 |  | 2019-05-09 | 2019-05-09 |  | 2019-05-16 | 2019-05-16 |  | 2019-05-23 | 2019-05-23 |  | 2019-11-02 | 2019-11-23
2019-07-01 | AL91A-BS-6A | 2018-05-21 |  | 2018-05-21 | 2018-05-31 |  | 2018-05-31 | 2018-06-07 |  | 2018-06-07 | 2018-08-13 |  | 2018-08-13 | 2018-11-14 |  | 2019-01-22 | 2018-11-21 |  | 2019-01-22 | [6 empty] | 2018-12-12 |  | 2019-01-29 | 2018-12-19 |  | 2019-02-07 | 2019-07-16 | 2019-08-12
2019-07-01 | AL91A-BS-6A | 2018-05-21 |  | 2018-05-21 | 2018-05-31 |  | 2018-05-31 | 2018-06-07 |  | 2018-06-07 | 2018-08-13 |  | 2018-08-13 | 2018-11-14 |  | 2019-01-22 | 2018-11-21 |  | 2019-01-22 | [6 empty] | 2018-12-12 |  | 2019-01-29 | 2018-12-19 |  | 2019-02-07 | 2019-10-01 | 2019-09-08
2019-07-01 | AL91A-BS-6A | 2018-05-21 |  | 2018-05-21 | 2018-05-31 |  | 2018-05-31 | 2018-06-07 |  | 2018-06-07 | 2018-08-13 |  | 2018-08-13 | 2018-11-14 |  | 2019-01-22 | 2018-11-21 |  | 2019-01-22 | [6 empty] | 2018-12-12 |  | 2019-01-29 | 2018-12-19 |  | 2019-02-07 | 2019-11-27 | 2019-10-20
2019-07-01 | PP01A-BS-6A | 2018-05-30 |  | 2018-05-30 | 2018-05-31 |  | 2018-05-31 | 2018-08-09 |  | 2018-08-09 | 2018-09-28 |  | 2018-09-28 | 2018-11-16 |  | 2019-01-22 | 2018-11-23 |  | 2019-01-24 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-21 | 2018-12-14 |  | 2019-03-13 | 2019-02-01 |  | 2019-03-29 | 2019-10-10 | 2019-10-08
2019-07-01 | PP01B-BS-6A | 2019-02-12 |  | 2019-02-22 | 2019-02-19 |  | 2019-03-12 | 2019-02-26 |  | 2019-03-21 | 2019-04-09 |  | 2019-04-24 | 2019-06-03 | 2019-05-31 |  | 2019-06-10 | 2019-06-05 |  | 2019-06-17 | 2019-06-12 |  | 2019-06-24 | 2019-06-19 |  | 2019-07-01 | 2019-06-26 |  | 2019-07-08 | 2019-07-03 |  | 2019-07-08 | 2019-07-24
2019-07-01 | VC01A-BS-6A | 2018-05-25 |  | 2018-05-25 | 2018-05-29 |  | 2018-05-29 | 2018-08-15 |  | 2018-08-15 | 2018-09-27 |  | 2018-09-27 | 2018-12-13 |  | 2019-01-21 | 2018-12-20 |  | 2019-01-21 | 2019-01-04 |  | 2019-03-12 | 2019-01-11 |  | 2019-03-26 | 2019-01-18 |  | 2019-04-01 | 2019-03-29 |  | 2019-04-04 | 2019-07-17 | 2019-06-24
2019-07-01 | VC01A-BS-6A | 2018-05-25 |  | 2018-05-25 | 2018-05-29 |  | 2018-05-29 | 2018-08-15 |  | 2018-08-15 | 2018-09-27 |  | 2018-09-27 | 2018-12-13 |  | 2019-01-21 | 2018-12-20 |  | 2019-01-21 | 2019-01-04 |  | 2019-03-12 | 2019-01-11 |  | 2019-03-26 | 2019-01-18 |  | 2019-04-01 | 2019-03-29 |  | 2019-04-04 | 2019-07-18 | 2019-07-22
2019-07-01 | VC02A-BS-6A | 2018-05-21 |  | 2018-05-21 | 2018-05-22 |  | 2018-05-22 | 2018-06-06 |  | 2018-06-06 | 2018-07-06 |  | 2018-07-06 | 2018-11-16 |  | 2018-12-07 | 2018-11-23 |  | 2018-12-07 | 2018-11-30 |  | 2018-12-12 | 2018-12-07 |  | 2019-02-01 | 2018-12-14 |  | 2019-01-02 | 2018-12-21 |  | 2019-02-13 | 2019-10-17 | 2019-10-04
2019-07-01 | VC02A-BS-6A | 2018-05-21 |  | 2018-05-21 | 2018-05-22 |  | 2018-05-22 | 2018-06-06 |  | 2018-06-06 | 2018-07-06 |  | 2018-07-06 | 2018-11-16 |  | 2018-12-07 | 2018-11-23 |  | 2018-12-07 | 2018-11-30 |  | 2018-12-12 | 2018-12-07 |  | 2019-02-01 | 2018-12-14 |  | 2019-01-02 | 2018-12-21 |  | 2019-02-13 | 2019-07-04 | 2019-06-23
2019-07-01 | VC03A-BS-6A | 2019-07-29 | 2019-07-29 |  | 2019-08-05 | 2019-08-05 |  | 2019-08-12 | 2019-08-12 |  | 2019-09-24 | 2019-09-24 |  | 2019-11-12 | 2019-11-12 |  | 2019-11-19 | 2019-11-19 |  | 2019-11-26 | 2019-11-26 |  | 2019-12-03 | 2019-12-03 |  | 2019-12-10 | 2019-12-10 |  | 2019-12-17 | 2019-12-17 |  | 2019-07-02 | 2019-06-26
2019-07-01 | NH01A-BS-6A | 2018-01-15 |  | 2018-01-15 | 2018-01-18 |  | 2018-01-18 | 2018-06-08 |  | 2018-06-08 | 2018-08-03 |  | 2018-08-03 | 2018-11-23 |  | 2018-12-19 | 2018-11-27 |  | 2019-01-22 | 2018-11-30 |  | 2019-01-23 | 2019-01-25 |  | 2019-04-12 | 2019-01-23 |  | 2019-04-11 | 2019-01-25 | 2019-04-30 |  | 2019-10-23 | 2019-09-22
2019-07-01 | NH02A-BS-6A | 2018-02-13 |  | 2018-02-13 | 2018-02-13 |  | 2018-02-13 | 2018-06-08 |  | 2018-06-08 | 2018-08-03 |  | 2018-08-03 | 2018-11-23 |  | 2019-02-19 | 2018-11-27 |  | 2019-02-19 | 2018-11-30 |  | 2019-01-30 | 2019-01-25 |  | 2019-04-12 | 2019-01-23 |  | 2019-04-11 | 2019-01-25 | 2019-04-30 |  | 2019-10-01 | 2019-11-05
2019-07-01 | NH03A-BS-6A | 2018-02-20 |  | 2018-02-20 | 2018-02-20 |  | 2018-02-20 | 2018-06-14 |  | 2018-06-14 | 2018-09-07 |  | 2018-09-07 | 2018-12-07 |  | 2019-02-05 | 2018-12-14 |  | 2018-11-28 | 2018-12-19 |  | 2018-12-03 | 2018-12-21 |  | 2018-12-06 | 2019-01-15 |  | 2019-03-21 | 2019-01-17 |  | 2019-03-28 | 2019-11-07 | 2019-10-18
2019-07-01 | NH04A-BS-6A | 2018-03-13 |  | 2018-03-13 | 2018-03-15 |  | 2018-03-15 | 2018-06-14 |  | 2018-06-14 | 2018-08-13 |  | 2018-08-13 | 2018-12-07 |  | 2018-11-27 | 2018-12-14 |  | 2018-11-27 | 2018-12-19 |  | 2018-12-03 | 2018-12-21 |  | 2018-12-06 | 2019-01-15 |  | 2019-03-08 | 2019-01-17 |  | 2019-03-27 | 2019-06-20 | 2019-06-25
2019-07-01 | NH06A-BS-6A | 2018-02-28 |  | 2018-02-28 | 2018-02-28 |  | 2018-02-28 | 2018-07-30 |  | 2018-07-30 | 2018-09-11 |  | 2018-09-11 | 2018-11-27 |  | 2019-02-19 | 2018-12-14 |  | 2019-03-04 | 2018-12-21 |  | 2019-03-05 | 2019-01-07 |  | 2019-03-26 | 2019-01-14 |  | 2019-03-15 | 2019-01-21 |  | 2019-04-02 | 2019-12-14 | 2020-01-13
2019-07-01 | NH06A-BS-6A | 2018-02-28 |  | 2018-02-28 | 2018-02-28 |  | 2018-02-28 | 2018-07-30 |  | 2018-07-30 | 2018-09-11 |  | 2018-09-11 | 2018-11-27 |  | 2019-02-19 | 2018-12-14 |  | 2019-03-04 | 2018-12-21 |  | 2019-03-05 | 2019-01-07 |  | 2019-03-26 | 2019-01-14 |  | 2019-03-15 | 2019-01-21 |  | 2019-04-02 | 2019-12-11 | 2020-01-17
2019-07-01 | NH06A-BS-6A | 2018-02-28 |  | 2018-02-28 | 2018-02-28 |  | 2018-02-28 | 2018-07-30 |  | 2018-07-30 | 2018-09-11 |  | 2018-09-11 | 2018-11-27 |  | 2019-02-19 | 2018-12-14 |  | 2019-03-04 | 2018-12-21 |  | 2019-03-05 | 2019-01-07 |  | 2019-03-26 | 2019-01-14 |  | 2019-03-15 | 2019-01-21 |  | 2019-04-02 | 2019-09-25 | 2019-09-27
2019-07-01 | NH06A-BS-6A | 2018-02-28 |  | 2018-02-28 | 2018-02-28 |  | 2018-02-28 | 2018-07-30 |  | 2018-07-30 | 2018-09-11 |  | 2018-09-11 | 2018-11-27 |  | 2019-02-19 | 2018-12-14 |  | 2019-03-04 | 2018-12-21 |  | 2019-03-05 | 2019-01-07 |  | 2019-03-26 | 2019-01-14 |  | 2019-03-15 | 2019-01-21 |  | 2019-04-02 | 2019-08-01 | 2019-08-03
2019-07-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-05-31 | 2018-06-01 |  | 2018-06-01 | 2018-06-22 |  | 2018-06-22 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-07 | 2018-11-19 |  | 2019-02-01 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-21 | 2019-10-23 | 2019-10-31
2019-07-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-05-31 | 2018-06-01 |  | 2018-06-01 | 2018-06-22 |  | 2018-06-22 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-07 | 2018-11-19 |  | 2019-02-01 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-21 | 2019-10-15 | 2019-09-06
2019-07-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-05-31 | 2018-06-01 |  | 2018-06-01 | 2018-06-22 |  | 2018-06-22 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-07 | 2018-11-19 |  | 2019-02-01 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-21 | 2019-06-13 | 2019-05-05
2019-07-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-05-31 | 2018-06-01 |  | 2018-06-01 | 2018-06-22 |  | 2018-06-22 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-07 | 2018-11-19 |  | 2019-02-01 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-21 | 2019-08-01 | 2019-09-05
2019-07-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-05-31 | 2018-06-01 |  | 2018-06-01 | 2018-06-22 |  | 2018-06-22 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-07 | 2018-11-19 |  | 2019-02-01 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-21 | 2019-12-05 | 2020-01-08
2019-07-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-05-31 | 2018-06-01 |  | 2018-06-01 | 2018-06-22 |  | 2018-06-22 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-07 | 2018-11-19 |  | 2019-02-01 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-21 | 2019-06-08 | 2019-05-02
2019-07-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-05-31 | 2018-06-01 |  | 2018-06-01 | 2018-06-22 |  | 2018-06-22 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-07 | 2018-11-19 |  | 2019-02-01 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-21 | 2019-08-30 | 2019-08-11
2019-07-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-05-31 | 2018-06-01 |  | 2018-06-01 | 2018-06-22 |  | 2018-06-22 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-07 | 2018-11-19 |  | 2019-02-01 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-21 | 2019-06-27 | 2019-06-17
2019-07-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-05-31 | 2018-06-01 |  | 2018-06-01 | 2018-06-22 |  | 2018-06-22 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-07 | 2018-11-19 |  | 2019-02-01 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-21 | 2019-11-11 | 2019-11-03
2019-07-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-05-31 | 2018-06-01 |  | 2018-06-01 | 2018-06-22 |  | 2018-06-22 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-07 | 2018-11-19 |  | 2019-02-01 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-21 | 2019-12-24 | 2019-12-16
2019-07-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-05-31 | 2018-06-01 |  | 2018-06-01 | 2018-06-22 |  | 2018-06-22 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-07 | 2018-11-19 |  | 2019-02-01 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-21 | 2019-10-17 | 2019-11-18
2019-07-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-05-31 | 2018-06-01 |  | 2018-06-01 | 2018-06-22 |  | 2018-06-22 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-07 | 2018-11-19 |  | 2019-02-01 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-21 | 2019-08-21 | 2019-09-07
2019-07-01 | NH10A-BS-6A | 2018-05-15 |  | 2018-05-15 | 2018-05-15 |  | 2018-05-15 | 2018-06-22 |  | 2018-06-22 | 2018-07-30 |  | 2018-07-30 | 2018-11-22 |  | 2018-12-03 | 2018-11-29 |  | 2018-12-07 | 2018-12-06 |  | 2018-12-12 | 2018-12-13 |  | 2019-01-03 | 2018-12-20 |  | 2019-02-25 | 2019-01-04 |  | 2019-03-06 | 2019-11-17 | 2019-12-16
2019-07-01 | NH12A-BS-6A | 2018-03-07 |  | 2018-03-07 | 2018-03-08 |  | 2018-03-08 | 2018-04-17 |  | 2018-04-17 | 2018-08-10 |  | 2018-08-10 | 2018-10-26 |  | 2019-02-15 | 2018-10-26 |  | 2019-02-15 | 2018-11-01 |  | 2019-02-19 | 2018-11-08 |  | 2019-02-28 | 2018-11-13 |  | 2019-03-01 | 2018-11-14 |  | 2019-03-21 | 2019-09-21 | 2019-10-29
2019-07-01 | NH12A-BS-6A | 2018-03-07 |  | 2018-03-07 | 2018-03-08 |  | 2018-03-08 | 2018-04-17 |  | 2018-04-17 | 2018-08-10 |  | 2018-08-10 | 2018-10-26 |  | 2019-02-15 | 2018-10-26 |  | 2019-02-15 | 2018-11-01 |  | 2019-02-19 | 2018-11-08 |  | 2019-02-28 | 2018-11-13 |  | 2019-03-01 | 2018-11-14 |  | 2019-03-21 | 2019-09-01 | 2019-08-20
2019-07-01 | NH12A-BS-6A | 2018-03-07 |  | 2018-03-07 | 2018-03-08 |  | 2018-03-08 | 2018-04-17 |  | 2018-04-17 | 2018-08-10 |  | 2018-08-10 | 2018-10-26 |  | 2019-02-15 | 2018-10-26 |  | 2019-02-15 | 2018-11-01 |  | 2019-02-19 | 2018-11-08 |  | 2019-02-28 | 2018-11-13 |  | 2019-03-01 | 2018-11-14 |  | 2019-03-21 | 2019-06-04 | 2019-07-05
2019-07-01 | NH12A-BS-6A | 2018-03-07 |  | 2018-03-07 | 2018-03-08 |  | 2018-03-08 | 2018-04-17 |  | 2018-04-17 | 2018-08-10 |  | 2018-08-10 | 2018-10-26 |  | 2019-02-15 | 2018-10-26 |  | 2019-02-15 | 2018-11-01 |  | 2019-02-19 | 2018-11-08 |  | 2019-02-28 | 2018-11-13 |  | 2019-03-01 | 2018-11-14 |  | 2019-03-21 | 2019-11-09 | 2019-11-28
2019-07-01 | NH12A-BS-6A | 2018-03-07 |  | 2018-03-07 | 2018-03-08 |  | 2018-03-08 | 2018-04-17 |  | 2018-04-17 | 2018-08-10 |  | 2018-08-10 | 2018-10-26 |  | 2019-02-15 | 2018-10-26 |  | 2019-02-15 | 2018-11-01 |  | 2019-02-19 | 2018-11-08 |  | 2019-02-28 | 2018-11-13 |  | 2019-03-01 | 2018-11-14 |  | 2019-03-21 | 2019-11-16 | 2019-10-10
2019-07-01 | NH13A-BS-6A | 2018-08-10 |  | 2018-08-10 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2018-09-24 |  | 2018-09-24 | 2018-11-26 |  | 2019-03-29 | 2018-12-03 |  | 2019-03-29 | 2018-12-10 |  | 2019-04-01 | 2018-12-17 |  | 2019-04-12 | 2018-12-19 |  | 2019-04-30 | 2018-12-21 | 2019-05-08 |  | 2019-08-23 | 2019-08-02
2019-07-01 | NH13A-BS-6A | 2018-08-10 |  | 2018-08-10 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2018-09-24 |  | 2018-09-24 | 2018-11-26 |  | 2019-03-29 | 2018-12-03 |  | 2019-03-29 | 2018-12-10 |  | 2019-04-01 | 2018-12-17 |  | 2019-04-12 | 2018-12-19 |  | 2019-04-30 | 2018-12-21 | 2019-05-08 |  | 2019-10-22 | 2019-11-24
2019-07-01 | NH14A-BS-6A | 2018-11-09 |  | 2018-11-19 | 2018-11-16 |  | 2018-11-19 | 2018-11-23 |  | 2018-11-20 | 2019-01-18 |  | 2019-01-16 | 2019-03-07 | 2019-05-16 |  | 2019-03-15 | 2019-05-16 |  | 2019-03-22 | 2019-05-16 |  | 2019-03-29 | 2019-05-23 |  | 2019-04-02 | 2019-05-31 |  | 2019-04-04 | 2019-06-07 |  | 2019-10-14 | 2019-11-10
2019-07-01 | NH14A-BS-6A | 2018-11-09 |  | 2018-11-19 | 2018-11-16 |  | 2018-11-19 | 2018-11-23 |  | 2018-11-20 | 2019-01-18 |  | 2019-01-16 | 2019-03-07 | 2019-05-16 |  | 2019-03-15 | 2019-05-16 |  | 2019-03-22 | 2019-05-16 |  | 2019-03-29 | 2019-05-23 |  | 2019-04-02 | 2019-05-31 |  | 2019-04-04 | 2019-06-07 |  | 2019-08-01 | 2019-08-23
2019-07-01 | NH14A-BS-6A | 2018-11-09 |  | 2018-11-19 | 2018-11-16 |  | 2018-11-19 | 2018-11-23 |  | 2018-11-20 | 2019-01-18 |  | 2019-01-16 | 2019-03-07 | 2019-05-16 |  | 2019-03-15 | 2019-05-16 |  | 2019-03-22 | 2019-05-16 |  | 2019-03-29 | 2019-05-23 |  | 2019-04-02 | 2019-05-31 |  | 2019-04-04 | 2019-06-07 |  | 2019-11-30 | 2019-12-10
2019-07-01 | NH15A-BS-6A | 2018-08-10 |  | 2018-08-10 | 2018-08-13 |  | 2018-08-13 | 2018-08-14 |  | 2018-08-14 | 2018-09-25 |  | 2018-09-25 | 2018-11-27 |  | 2019-03-08 | 2018-11-30 |  | 2019-03-08 | 2018-12-07 |  | 2019-03-08 | 2018-12-14 |  | 2019-03-27 | 2018-12-21 |  | 2019-04-10 | 2019-01-07 |  | 2019-04-23 | 2019-09-09 | 2019-10-04
2019-07-01 | NH15A-BS-6A | 2018-08-10 |  | 2018-08-10 | 2018-08-13 |  | 2018-08-13 | 2018-08-14 |  | 2018-08-14 | 2018-09-25 |  | 2018-09-25 | 2018-11-27 |  | 2019-03-08 | 2018-11-30 |  | 2019-03-08 | 2018-12-07 |  | 2019-03-08 | 2018-12-14 |  | 2019-03-27 | 2018-12-21 |  | 2019-04-10 | 2019-01-07 |  | 2019-04-23 | 2019-12-03 | 2019-12-25
2019-07-01 | NH15A-BS-6A | 2018-08-10 |  | 2018-08-10 | 2018-08-13 |  | 2018-08-13 | 2018-08-14 |  | 2018-08-14 | 2018-09-25 |  | 2018-09-25 | 2018-11-27 |  | 2019-03-08 | 2018-11-30 |  | 2019-03-08 | 2018-12-07 |  | 2019-03-08 | 2018-12-14 |  | 2019-03-27 | 2018-12-21 |  | 2019-04-10 | 2019-01-07 |  | 2019-04-23 | 2019-11-15 | 2019-10-12
2019-07-01 | NH16A-BS-6A | 2018-03-15 |  | 2018-03-15 | 2018-03-16 |  | 2018-03-16 | 2018-07-04 |  | 2018-07-04 | 2018-08-30 |  | 2018-08-30 | 2018-11-15 |  | 2018-11-27 | 2018-11-29 |  | 2018-11-27 | 2018-12-06 |  | 2019-04-01 | 2018-12-13 |  | 2019-04-12 | 2018-12-20 |  | 2019-03-13 | 2019-03-08 |  | 2019-05-01 | 2019-10-06 | 2019-09-08
2019-07-01 | NH16A-BS-6A | 2018-03-15 |  | 2018-03-15 | 2018-03-16 |  | 2018-03-16 | 2018-07-04 |  | 2018-07-04 | 2018-08-30 |  | 2018-08-30 | 2018-11-15 |  | 2018-11-27 | 2018-11-29 |  | 2018-11-27 | 2018-12-06 |  | 2019-04-01 | 2018-12-13 |  | 2019-04-12 | 2018-12-20 |  | 2019-03-13 | 2019-03-08 |  | 2019-05-01 | 2019-11-12 | 2019-12-19
2019-07-01 | NH17A-BS-6A | 2018-06-21 |  | 2018-06-21 | 2018-06-25 |  | 2018-06-25 | 2018-07-31 |  | 2018-07-31 | 2018-09-27 |  | 2018-09-27 | 2018-11-22 |  | 2018-12-18 | 2018-11-29 |  | 2018-12-18 | 2018-12-06 |  | 2019-01-04 | 2018-12-13 |  | 2019-02-01 | 2018-12-20 |  | 2019-03-13 | 2019-01-04 |  | 2019-03-25 | 2019-10-18 | 2019-09-09
2019-07-01 | NH17A-BS-6A | 2018-06-21 |  | 2018-06-21 | 2018-06-25 |  | 2018-06-25 | 2018-07-31 |  | 2018-07-31 | 2018-09-27 |  | 2018-09-27 | 2018-11-22 |  | 2018-12-18 | 2018-11-29 |  | 2018-12-18 | 2018-12-06 |  | 2019-01-04 | 2018-12-13 |  | 2019-02-01 | 2018-12-20 |  | 2019-03-13 | 2019-01-04 |  | 2019-03-25 | 2019-10-07 | 2019-09-03
2019-07-01 | NH17A-BS-6A | 2018-06-21 |  | 2018-06-21 | 2018-06-25 |  | 2018-06-25 | 2018-07-31 |  | 2018-07-31 | 2018-09-27 |  | 2018-09-27 | 2018-11-22 |  | 2018-12-18 | 2018-11-29 |  | 2018-12-18 | 2018-12-06 |  | 2019-01-04 | 2018-12-13 |  | 2019-02-01 | 2018-12-20 |  | 2019-03-13 | 2019-01-04 |  | 2019-03-25 | 2019-07-27 | 2019-07-19
2019-07-01 | NH18A-BS-6A | 2018-08-15 |  | 2018-08-15 | 2018-08-16 |  | 2018-08-16 | 2018-08-17 |  | 2018-08-17 | 2018-10-16 |  | 2018-10-15 | 2018-12-14 |  | 2019-03-04 | 2018-12-14 |  | 2019-03-04 | 2019-01-07 |  | 2019-03-05 | 2019-01-14 |  | 2019-04-04 | 2019-01-16 |  | 2019-03-28 | 2019-01-17 |  | 2019-04-17 | 2019-08-01 | 2019-08-05
2019-07-01 | NH18A-BS-6A | 2018-08-15 |  | 2018-08-15 | 2018-08-16 |  | 2018-08-16 | 2018-08-17 |  | 2018-08-17 | 2018-10-16 |  | 2018-10-15 | 2018-12-14 |  | 2019-03-04 | 2018-12-14 |  | 2019-03-04 | 2019-01-07 |  | 2019-03-05 | 2019-01-14 |  | 2019-04-04 | 2019-01-16 |  | 2019-03-28 | 2019-01-17 |  | 2019-04-17 | 2019-09-03 | 2019-09-15
2019-07-01 | NH18A-BS-6A | 2018-08-15 |  | 2018-08-15 | 2018-08-16 |  | 2018-08-16 | 2018-08-17 |  | 2018-08-17 | 2018-10-16 |  | 2018-10-15 | 2018-12-14 |  | 2019-03-04 | 2018-12-14 |  | 2019-03-04 | 2019-01-07 |  | 2019-03-05 | 2019-01-14 |  | 2019-04-04 | 2019-01-16 |  | 2019-03-28 | 2019-01-17 |  | 2019-04-17 | 2019-11-11 | 2019-11-14
2019-07-01 | NH19A-BS-6A | 2019-08-15 | 2019-08-15 |  | 2019-08-22 | 2019-08-22 |  | 2019-08-30 | 2019-08-29 |  | 2019-10-11 | 2019-10-10 |  | 2019-11-29 | 2019-11-28 |  | 2019-12-06 | 2019-12-05 |  | 2019-12-13 | 2019-12-12 |  | 2019-12-20 | 2019-12-19 |  | 2020-01-06 | 2020-01-03 |  | 2020-01-13 | 2020-01-10 |  | 2019-12-05 | 2019-11-17
2019-07-01 | NH23A-BS-6A | 2018-05-18 |  | 2018-05-18 | 2018-05-21 |  | 2018-05-21 | 2018-06-21 |  | 2018-06-21 | 2018-09-07 |  | 2018-09-07 | 2018-11-29 |  | 2018-12-11 | 2018-12-06 |  | 2018-12-11 | 2018-12-13 |  | 2019-02-25 | 2018-12-20 |  | 2019-02-28 | 2019-01-04 |  | 2019-01-18 | 2019-01-11 |  | 2019-03-13 | 2019-06-24 | 2019-06-10
2019-07-01 | NH23A-BS-6A | 2018-05-18 |  | 2018-05-18 | 2018-05-21 |  | 2018-05-21 | 2018-06-21 |  | 2018-06-21 | 2018-09-07 |  | 2018-09-07 | 2018-11-29 |  | 2018-12-11 | 2018-12-06 |  | 2018-12-11 | 2018-12-13 |  | 2019-02-25 | 2018-12-20 |  | 2019-02-28 | 2019-01-04 |  | 2019-01-18 | 2019-01-11 |  | 2019-03-13 | 2019-12-21 | 2019-11-15
2019-07-01 | NH23A-BS-6A | 2018-05-18 |  | 2018-05-18 | 2018-05-21 |  | 2018-05-21 | 2018-06-21 |  | 2018-06-21 | 2018-09-07 |  | 2018-09-07 | 2018-11-29 |  | 2018-12-11 | 2018-12-06 |  | 2018-12-11 | 2018-12-13 |  | 2019-02-25 | 2018-12-20 |  | 2019-02-28 | 2019-01-04 |  | 2019-01-18 | 2019-01-11 |  | 2019-03-13 | 2019-07-13 | 2019-06-13
2019-07-01 | NH24A-BS-6A | 2018-03-19 |  | 2018-03-19 | 2018-03-19 |  | 2018-03-19 | 2018-05-31 |  | 2018-05-31 | 2018-07-06 |  | 2018-07-06 | 2018-11-01 |  | 2018-11-14 | 2018-11-09 |  | 2018-11-20 | 2018-11-16 |  | 2019-01-30 | 2018-11-23 |  | 2019-02-21 | 2018-11-30 |  | 2019-02-21 | 2018-12-07 |  | 2019-04-02 | 2019-12-22 | 2019-11-16
2019-07-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-06 | 2019-11-21 | 2019-10-16
2019-07-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-06 | 2019-07-19 | 2019-08-07
2019-07-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-06 | 2019-10-28 | 2019-11-17
2019-07-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-06 | 2019-12-13 | 2019-12-22
2019-07-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-06 | 2019-06-22 | 2019-06-27
2019-07-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-06 | 2019-07-30 | 2019-08-05
2019-07-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-06 | 2019-09-23 | 2019-09-03
2019-07-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-06 | 2019-11-04 | 2019-10-03
2019-07-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-06 | 2019-06-30 | 2019-07-09
2019-07-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-06 | 2019-12-17 | 2019-11-20
2019-07-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-06 | 2019-06-19 | 2019-06-13
2019-07-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-06 | 2019-11-23 | 2019-10-14
2019-07-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-06 | 2019-07-12 | 2019-08-20
2019-07-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-06 | 2019-10-05 | 2019-09-06
2019-07-01 | NH27B-BS-6A | 2019-02-27 |  | 2019-04-04 | 2019-03-06 |  | 2019-04-11 | 2019-03-13 |  | 2019-04-17 | 2019-05-13 | 2019-05-09 |  | 2019-07-16 | 2019-07-12 |  | 2019-07-23 | 2019-07-19 |  | 2019-07-30 | 2019-07-26 |  | 2019-08-06 | 2019-08-02 |  | 2019-08-13 | 2019-08-09 |  | 2019-08-20 | 2019-08-16 |  | 2019-12-30 | 2020-01-07
2019-07-01 | NH27C-BS-6A | 2019-06-06 | 2019-06-06 |  | 2019-06-13 | 2019-06-13 |  | 2019-06-20 | 2019-06-20 |  | 2019-07-18 | 2019-07-18 |  | 2019-08-22 | 2019-08-22 |  | 2019-08-30 | 2019-08-30 |  | 2019-09-06 | 2019-09-06 |  | 2019-09-13 | 2019-09-13 |  | 2019-09-20 | 2019-09-20 |  | 2019-09-27 | 2019-09-27 |  | 2019-07-21 | 2019-08-24
2019-07-01 | NH27C-BS-6A | 2019-06-06 | 2019-06-06 |  | 2019-06-13 | 2019-06-13 |  | 2019-06-20 | 2019-06-20 |  | 2019-07-18 | 2019-07-18 |  | 2019-08-22 | 2019-08-22 |  | 2019-08-30 | 2019-08-30 |  | 2019-09-06 | 2019-09-06 |  | 2019-09-13 | 2019-09-13 |  | 2019-09-20 | 2019-09-20 |  | 2019-09-27 | 2019-09-27 |  | 2019-07-05 | 2019-06-26
2019-07-01 | NH29A-BS-6A | 2018-11-30 |  | 2018-12-05 | 2018-12-07 |  | 2018-12-12 | 2018-12-14 |  | 2018-12-18 | 2019-01-21 |  | 2019-01-30 | 2019-02-25 |  | 2019-04-04 | 2019-03-04 |  | 2019-04-10 | 2019-03-11 |  | 2019-04-15 | 2019-03-18 | 2019-04-30 |  | 2019-03-25 | 2019-05-10 |  | 2019-04-01 | 2019-05-17 |  | 2019-07-25 | 2019-06-19
2019-07-01 | NH30A-BS-6A | 2019-03-14 |  | 2019-04-30 | 2019-03-21 |  | 2019-04-30 | 2019-03-28 | 2019-05-07 |  | 2019-05-14 | 2019-06-19 |  | 2019-07-03 | 2019-08-07 |  | 2019-07-10 | 2019-08-14 |  | 2019-07-17 | 2019-08-21 |  | 2019-07-24 | 2019-08-29 |  | 2019-07-31 | 2019-09-05 |  | 2019-08-07 | 2019-09-12 |  | 2019-12-26 | 2019-11-16
2019-07-01 | NH30A-BS-6A | 2019-03-14 |  | 2019-04-30 | 2019-03-21 |  | 2019-04-30 | 2019-03-28 | 2019-05-07 |  | 2019-05-14 | 2019-06-19 |  | 2019-07-03 | 2019-08-07 |  | 2019-07-10 | 2019-08-14 |  | 2019-07-17 | 2019-08-21 |  | 2019-07-24 | 2019-08-29 |  | 2019-07-31 | 2019-09-05 |  | 2019-08-07 | 2019-09-12 |  | 2019-07-18 | 2019-08-23
2019-07-01 | NH31A-BS-6A | 2018-02-08 |  | 2018-02-08 | 2018-02-12 |  | 2018-02-12 | 2018-03-07 |  | 2018-03-07 | 2018-04-17 |  | 2018-04-17 | 2018-08-17 |  | 2018-10-11 | 2018-10-16 |  | 2018-10-11 | 2018-10-23 |  | 2018-11-01 | 2018-10-30 |  | 2018-11-09 | 2018-11-06 |  | 2018-11-29 | 2018-11-13 |  | 2018-12-06 | 2019-09-15 | 2019-09-17
2019-07-01 | NH31A-BS-6A | 2018-02-08 |  | 2018-02-08 | 2018-02-12 |  | 2018-02-12 | 2018-03-07 |  | 2018-03-07 | 2018-04-17 |  | 2018-04-17 | 2018-08-17 |  | 2018-10-11 | 2018-10-16 |  | 2018-10-11 | 2018-10-23 |  | 2018-11-01 | 2018-10-30 |  | 2018-11-09 | 2018-11-06 |  | 2018-11-29 | 2018-11-13 |  | 2018-12-06 | 2019-09-22 | 2019-09-26
2019-07-01 | NH31A-BS-6A | 2018-02-08 |  | 2018-02-08 | 2018-02-12 |  | 2018-02-12 | 2018-03-07 |  | 2018-03-07 | 2018-04-17 |  | 2018-04-17 | 2018-08-17 |  | 2018-10-11 | 2018-10-16 |  | 2018-10-11 | 2018-10-23 |  | 2018-11-01 | 2018-10-30 |  | 2018-11-09 | 2018-11-06 |  | 2018-11-29 | 2018-11-13 |  | 2018-12-06 | 2019-09-15 | 2019-08-20
2019-07-01 | NH32A-BS-6A | 2018-02-22 |  | 2018-02-22 | 2018-02-26 |  | 2018-02-26 | 2018-03-20 |  | 2018-03-20 | 2018-05-30 |  | 2018-05-30 | 2018-10-10 |  | 2019-04-10 | 2018-10-17 |  | 2019-04-10 | 2018-10-24 |  | 2019-04-16 | 2018-10-31 |  | 2019-04-24 | 2018-11-07 |  | 2019-04-17 | 2018-11-14 | 2019-05-02 |  | 2019-11-27 | 2019-11-30
2019-07-01 | NH32A-BS-6A | 2018-02-22 |  | 2018-02-22 | 2018-02-26 |  | 2018-02-26 | 2018-03-20 |  | 2018-03-20 | 2018-05-30 |  | 2018-05-30 | 2018-10-10 |  | 2019-04-10 | 2018-10-17 |  | 2019-04-10 | 2018-10-24 |  | 2019-04-16 | 2018-10-31 |  | 2019-04-24 | 2018-11-07 |  | 2019-04-17 | 2018-11-14 | 2019-05-02 |  | 2019-09-08 | 2019-09-02
2019-07-01 | NH32A-BS-6A | 2018-02-22 |  | 2018-02-22 | 2018-02-26 |  | 2018-02-26 | 2018-03-20 |  | 2018-03-20 | 2018-05-30 |  | 2018-05-30 | 2018-10-10 |  | 2019-04-10 | 2018-10-17 |  | 2019-04-10 | 2018-10-24 |  | 2019-04-16 | 2018-10-31 |  | 2019-04-24 | 2018-11-07 |  | 2019-04-17 | 2018-11-14 | 2019-05-02 |  | 2019-09-22 | 2019-09-18
2019-07-01 | NH33A-BS-6A | 2018-09-10 |  | 2018-09-10 | 2018-09-11 |  | 2018-09-11 | 2018-09-11 |  | 2018-09-11 | 2018-10-08 |  | 2018-10-08 | 2018-12-10 |  | 2019-02-12 | 2018-12-17 |  | 2019-02-12 | 2018-12-24 |  | 2019-02-19 | 2019-01-08 |  | 2019-03-06 | 2019-01-15 |  | 2019-02-19 | 2019-01-22 |  | 2019-03-14 | 2019-09-18 | 2019-09-26
2019-07-01 | NH33A-BS-6A | 2018-09-10 |  | 2018-09-10 | 2018-09-11 |  | 2018-09-11 | 2018-09-11 |  | 2018-09-11 | 2018-10-08 |  | 2018-10-08 | 2018-12-10 |  | 2019-02-12 | 2018-12-17 |  | 2019-02-12 | 2018-12-24 |  | 2019-02-19 | 2019-01-08 |  | 2019-03-06 | 2019-01-15 |  | 2019-02-19 | 2019-01-22 |  | 2019-03-14 | 2019-08-24 | 2019-07-24
2019-07-01 | NH33A-BS-6A | 2018-09-10 |  | 2018-09-10 | 2018-09-11 |  | 2018-09-11 | 2018-09-11 |  | 2018-09-11 | 2018-10-08 |  | 2018-10-08 | 2018-12-10 |  | 2019-02-12 | 2018-12-17 |  | 2019-02-12 | 2018-12-24 |  | 2019-02-19 | 2019-01-08 |  | 2019-03-06 | 2019-01-15 |  | 2019-02-19 | 2019-01-22 |  | 2019-03-14 | 2019-10-17 | 2019-10-20
2019-07-01 | NH35A-BS-6A | 2018-09-12 |  | 2018-09-12 | 2018-09-12 |  | 2018-09-12 | 2018-09-14 |  | 2018-09-14 | 2018-10-18 |  | 2018-10-24 | 2018-12-06 |  | 2019-03-15 | 2018-12-13 |  | 2019-03-15 | 2018-12-20 |  | 2019-03-29 | 2019-01-04 |  | 2019-04-18 | 2019-01-10 |  | 2019-04-24 | 2019-01-11 | 2019-05-02 |  | 2019-08-14 | 2019-07-30
2019-07-01 | NH35A-BS-6A | 2018-09-12 |  | 2018-09-12 | 2018-09-12 |  | 2018-09-12 | 2018-09-14 |  | 2018-09-14 | 2018-10-18 |  | 2018-10-24 | 2018-12-06 |  | 2019-03-15 | 2018-12-13 |  | 2019-03-15 | 2018-12-20 |  | 2019-03-29 | 2019-01-04 |  | 2019-04-18 | 2019-01-10 |  | 2019-04-24 | 2019-01-11 | 2019-05-02 |  | 2019-09-26 | 2019-09-04
2019-07-01 | NH36A-BS-6A | 2019-02-21 | 2019-05-10 |  | 2019-02-28 | 2019-05-13 |  | 2019-03-07 | 2019-05-17 |  | 2019-04-04 | 2019-06-17 |  | 2019-05-14 | 2019-07-22 |  | 2019-05-21 | 2019-07-29 |  | 2019-05-29 | 2019-08-05 |  | 2019-07-10 | 2019-09-17 |  | 2019-07-10 | 2019-09-17 |  | 2019-07-17 | 2019-09-24 |  | 2019-09-19 | 2019-10-02
2019-07-01 | NH36A-BS-6A | 2019-02-21 | 2019-05-10 |  | 2019-02-28 | 2019-05-13 |  | 2019-03-07 | 2019-05-17 |  | 2019-04-04 | 2019-06-17 |  | 2019-05-14 | 2019-07-22 |  | 2019-05-21 | 2019-07-29 |  | 2019-05-29 | 2019-08-05 |  | 2019-07-10 | 2019-09-17 |  | 2019-07-10 | 2019-09-17 |  | 2019-07-17 | 2019-09-24 |  | 2019-06-16 | 2019-05-24
2019-07-01 | NH36A-BS-6A | 2019-02-21 | 2019-05-10 |  | 2019-02-28 | 2019-05-13 |  | 2019-03-07 | 2019-05-17 |  | 2019-04-04 | 2019-06-17 |  | 2019-05-14 | 2019-07-22 |  | 2019-05-21 | 2019-07-29 |  | 2019-05-29 | 2019-08-05 |  | 2019-07-10 | 2019-09-17 |  | 2019-07-10 | 2019-09-17 |  | 2019-07-17 | 2019-09-24 |  | 2019-10-02 | 2019-09-05
2019-07-01 | NH36A-BS-6A | 2019-02-21 | 2019-05-10 |  | 2019-02-28 | 2019-05-13 |  | 2019-03-07 | 2019-05-17 |  | 2019-04-04 | 2019-06-17 |  | 2019-05-14 | 2019-07-22 |  | 2019-05-21 | 2019-07-29 |  | 2019-05-29 | 2019-08-05 |  | 2019-07-10 | 2019-09-17 |  | 2019-07-10 | 2019-09-17 |  | 2019-07-17 | 2019-09-24 |  | 2019-10-11 | 2019-11-01
2019-07-01 | NH36B-BS-6A | 2019-01-31 | 2019-05-15 |  | 2019-02-07 | 2019-05-17 |  | 2019-02-14 | 2019-05-22 |  | 2019-03-14 | 2019-06-20 |  | 2019-04-18 | 2019-07-25 |  | 2019-04-29 | 2019-08-01 |  | 2019-05-07 | 2019-08-08 |  | 2019-06-19 | 2019-09-20 |  | 2019-06-19 | 2019-09-20 |  | 2019-06-26 | 2019-09-27 |  | 2019-11-30 | 2019-12-24
2019-07-01 | NH37A-BS-6A | 2018-08-04 |  | 2018-08-04 | 2018-08-06 |  | 2018-08-06 | 2018-08-07 |  | 2018-08-07 | 2018-11-06 |  | 2018-10-30 | 2019-01-07 |  | 2019-04-25 | 2019-01-10 |  | 2019-04-29 | 2019-01-17 | 2019-04-30 |  | 2019-01-24 | 2019-05-08 |  | 2019-02-07 |  | 2019-05-01 | 2019-02-21 | 2019-05-09 |  | 2019-07-07 | 2019-06-10
2019-07-01 | NH43A-BS-6A | 2018-05-23 |  | 2018-05-23 | 2018-05-24 |  | 2018-05-24 | 2018-06-22 |  | 2018-06-22 | 2018-09-09 |  | 2018-09-09 | 2018-11-23 |  | 2018-12-20 | 2018-12-07 |  | 2018-12-20 | 2018-12-14 |  | 2019-02-26 | 2018-12-21 |  | 2019-03-19 | 2019-01-07 |  | 2019-02-26 | 2019-01-14 |  | 2019-04-02 | 2019-09-12 | 2019-10-16
2019-07-01 | NH49A-BS-6A | 2018-06-12 |  | 2018-06-12 | 2018-06-12 |  | 2018-06-12 | 2018-06-13 |  | 2018-06-13 | 2018-08-03 |  | 2018-08-03 | 2018-10-01 |  | 2018-11-23 | 2018-10-08 |  | 2018-11-23 | 2018-10-15 |  | 2018-11-29 | 2018-11-26 |  | 2019-02-20 | 2018-11-26 |  | 2019-01-21 | 2018-12-03 |  | 2019-03-11 | 2019-12-05 | 2019-10-31
2019-07-01 | NH50A-BS-6A | 2018-02-23 |  | 2018-02-23 | 2018-02-27 |  | 2018-02-27 | 2018-03-14 |  | 2018-03-14 | 2018-04-17 |  | 2018-04-17 | 2018-09-26 |  | 2018-09-26 | 2018-09-13 |  | 2018-09-13 | 2018-09-26 |  | 2018-09-26 | 2018-10-12 |  | 2018-10-18 | 2018-10-19 |  | 2018-11-09 | 2018-10-22 |  | 2018-11-15 | 2019-08-29 | 2019-09-08
2019-07-01 | NH58A-BS-6A | 2018-07-05 |  | 2018-07-05 | 2018-07-05 |  | 2018-07-05 | 2018-08-01 |  | 2018-08-01 | 2018-09-12 |  | 2018-09-12 | 2018-12-05 |  | 2019-02-22 | 2018-12-12 |  | 2019-02-22 | 2018-12-19 |  | 2019-02-27 | 2019-01-03 |  | 2019-03-19 | 2019-01-10 |  | 2019-03-13 | 2019-01-10 |  | 2019-04-02 | 2019-06-15 | 2019-05-19
2019-07-01 | NH58A-BS-6A | 2018-07-05 |  | 2018-07-05 | 2018-07-05 |  | 2018-07-05 | 2018-08-01 |  | 2018-08-01 | 2018-09-12 |  | 2018-09-12 | 2018-12-05 |  | 2019-02-22 | 2018-12-12 |  | 2019-02-22 | 2018-12-19 |  | 2019-02-27 | 2019-01-03 |  | 2019-03-19 | 2019-01-10 |  | 2019-03-13 | 2019-01-10 |  | 2019-04-02 | 2019-11-11 | 2019-12-18
2019-07-01 | NH72A-BS-6A | 2018-09-25 |  | 2018-09-25 | 2018-09-25 |  | 2018-09-25 | 2018-09-28 |  | 2018-09-28 | 2018-10-31 |  | 2018-10-31 | 2018-12-19 |  | 2019-02-13 | 2019-01-03 |  | 2019-02-13 | 2019-01-10 |  | 2019-03-20 | 2019-01-17 |  | 2019-04-12 | 2019-01-24 |  | 2019-03-13 | 2019-01-31 |  | 2019-04-26 | 2019-10-09 | 2019-09-02
2019-07-01 | NH91A-BS-6A | 2018-03-21 |  | 2018-03-21 | 2018-03-22 |  | 2018-03-22 | 2018-05-17 |  | 2018-05-17 | 2018-07-18 |  | 2018-07-18 | 2018-10-27 |  | 2018-10-25 | 2018-10-27 |  | 2018-10-25 | 2018-11-05 |  | 2018-11-29 | 2018-11-12 |  | 2018-12-13 | 2018-11-19 |  | 2019-02-07 | 2018-11-26 |  | 2019-03-13 | 2019-10-26 | 2019-10-24
2019-07-01 | NH92A-BS-6A | 2020-02-25 | 2020-02-25 |  | 2020-03-03 | 2020-03-03 |  | 2020-03-10 | 2020-03-10 |  | 2020-04-23 | 2020-04-23 |  | 2020-06-15 | 2020-06-15 |  | 2020-06-22 | 2020-06-22 |  | 2020-06-29 | 2020-06-29 |  | 2020-07-06 | 2020-07-06 |  | 2020-07-13 | 2020-07-13 |  | 2020-07-20 | 2020-07-20 |  | 2019-11-07 | 2019-11-14
2019-07-01 | MI01A-BS-6A | 2018-10-04 |  | 2018-10-04 | 2018-10-04 |  | 2018-10-04 | 2018-10-11 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-04-08 | 2019-01-04 |  | 2019-04-08 | 2019-01-11 |  | 2019-02-26 | 2019-01-18 |  | 2019-04-01 | 2019-01-25 |  | 2019-04-15 | 2019-02-01 |  | 2019-05-02 | 2019-07-28 | 2019-08-27
2019-07-01 | MI01A-BS-6A | 2018-10-04 |  | 2018-10-04 | 2018-10-04 |  | 2018-10-04 | 2018-10-11 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-04-08 | 2019-01-04 |  | 2019-04-08 | 2019-01-11 |  | 2019-02-26 | 2019-01-18 |  | 2019-04-01 | 2019-01-25 |  | 2019-04-15 | 2019-02-01 |  | 2019-05-02 | 2019-07-01 | 2019-06-18
2019-07-01 | MI01A-BS-6A | 2018-10-04 |  | 2018-10-04 | 2018-10-04 |  | 2018-10-04 | 2018-10-11 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-04-08 | 2019-01-04 |  | 2019-04-08 | 2019-01-11 |  | 2019-02-26 | 2019-01-18 |  | 2019-04-01 | 2019-01-25 |  | 2019-04-15 | 2019-02-01 |  | 2019-05-02 | 2019-09-08 | 2019-08-10
2019-07-01 | MI01A-BS-6A | 2018-10-04 |  | 2018-10-04 | 2018-10-04 |  | 2018-10-04 | 2018-10-11 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-04-08 | 2019-01-04 |  | 2019-04-08 | 2019-01-11 |  | 2019-02-26 | 2019-01-18 |  | 2019-04-01 | 2019-01-25 |  | 2019-04-15 | 2019-02-01 |  | 2019-05-02 | 2019-10-30 | 2019-12-03
2019-07-01 | MI08A-BS-6A | 2018-10-10 |  | 2018-10-15 | 2018-10-10 |  | 2018-10-15 | 2018-10-17 |  | 2018-10-17 | 2018-11-14 |  | 2018-11-19 | 2018-12-19 | 2019-05-08 |  | 2019-01-03 | 2019-05-08 |  | 2019-01-10 | 2019-05-08 |  | 2019-02-21 | 2019-05-15 |  | 2019-02-21 | 2019-05-22 |  | 2019-02-28 | 2019-05-30 |  | 2019-12-23 | 2019-12-26
2019-07-01 | MI08A-BS-6A | 2018-10-10 |  | 2018-10-15 | 2018-10-10 |  | 2018-10-15 | 2018-10-17 |  | 2018-10-17 | 2018-11-14 |  | 2018-11-19 | 2018-12-19 | 2019-05-08 |  | 2019-01-03 | 2019-05-08 |  | 2019-01-10 | 2019-05-08 |  | 2019-02-21 | 2019-05-15 |  | 2019-02-21 | 2019-05-22 |  | 2019-02-28 | 2019-05-30 |  | 2019-06-22 | 2019-06-02
2019-07-01 | MI08A-BS-6A | 2018-10-10 |  | 2018-10-15 | 2018-10-10 |  | 2018-10-15 | 2018-10-17 |  | 2018-10-17 | 2018-11-14 |  | 2018-11-19 | 2018-12-19 | 2019-05-08 |  | 2019-01-03 | 2019-05-08 |  | 2019-01-10 | 2019-05-08 |  | 2019-02-21 | 2019-05-15 |  | 2019-02-21 | 2019-05-22 |  | 2019-02-28 | 2019-05-30 |  | 2019-07-17 | 2019-07-11
2019-07-01 | MI11A-BS-6A | 2018-10-12 |  | 2018-10-23 | 2018-10-18 |  | 2018-10-23 | 2018-10-25 |  | 2018-10-24 | 2018-11-01 |  | 2018-11-01 | 2018-12-06 |  | 2019-01-16 | 2018-11-29 |  | 2019-01-16 | 2018-12-06 |  | 2019-01-25 | 2019-01-25 | 2019-05-09 |  | 2019-01-25 |  | 2019-03-25 | 2019-02-01 | 2019-05-09 |  | 2019-06-30 | 2019-05-29
2019-07-01 | MI16A-BS-6A | 2018-10-26 |  | 2018-10-26 | 2018-10-26 |  | 2018-10-26 | 2018-10-29 |  | 2018-10-29 | 2018-11-22 |  | 2018-11-22 | 2019-01-31 |  | 2019-04-01 | 2019-01-31 |  | 2019-04-01 | 2019-01-28 |  | 2019-02-20 | 2019-02-04 |  | 2019-04-03 | 2019-02-14 |  | 2019-04-03 | 2019-02-21 |  | 2019-04-08 | 2019-08-22 | 2019-08-07
2019-07-01 | MI16A-BS-6A | 2018-10-26 |  | 2018-10-26 | 2018-10-26 |  | 2018-10-26 | 2018-10-29 |  | 2018-10-29 | 2018-11-22 |  | 2018-11-22 | 2019-01-31 |  | 2019-04-01 | 2019-01-31 |  | 2019-04-01 | 2019-01-28 |  | 2019-02-20 | 2019-02-04 |  | 2019-04-03 | 2019-02-14 |  | 2019-04-03 | 2019-02-21 |  | 2019-04-08 | 2019-12-21 | 2019-11-16
2019-07-01 | MI17A-BS-6A | 2018-11-05 |  | 2018-11-05 | 2018-11-05 |  | 2018-11-05 | 2018-11-05 |  | 2018-11-05 | 2018-12-06 |  | 2019-04-11 | 2019-02-15 |  | 2019-04-29 | 2019-02-22 |  | 2019-04-29 | 2019-03-01 |  | 2019-04-26 | 2019-03-08 | 2019-05-07 |  | 2019-03-15 | 2019-05-10 |  | 2019-03-22 | 2019-05-17 |  | 2019-11-27 | 2019-12-16
2019-07-01 | MI17A-BS-6A | 2018-11-05 |  | 2018-11-05 | 2018-11-05 |  | 2018-11-05 | 2018-11-05 |  | 2018-11-05 | 2018-12-06 |  | 2019-04-11 | 2019-02-15 |  | 2019-04-29 | 2019-02-22 |  | 2019-04-29 | 2019-03-01 |  | 2019-04-26 | 2019-03-08 | 2019-05-07 |  | 2019-03-15 | 2019-05-10 |  | 2019-03-22 | 2019-05-17 |  | 2019-11-28 | 2019-10-19
2019-07-01 | MI18A-BS-6A | 2018-10-29 |  | 2018-11-05 | 2018-10-29 |  | 2018-11-05 | 2018-10-29 |  | 2018-11-06 | 2018-11-19 |  | 2018-11-22 | 2018-12-14 |  | 2019-03-26 | 2018-12-17 |  | 2019-03-26 | 2018-12-24 |  | 2019-03-21 | 2019-01-08 |  | 2019-04-04 | 2019-01-15 |  | 2019-04-03 | 2019-01-22 |  | 2019-04-10 | 2019-08-01 | 2019-08-13
2019-07-01 | MI18A-BS-6A | 2018-10-29 |  | 2018-11-05 | 2018-10-29 |  | 2018-11-05 | 2018-10-29 |  | 2018-11-06 | 2018-11-19 |  | 2018-11-22 | 2018-12-14 |  | 2019-03-26 | 2018-12-17 |  | 2019-03-26 | 2018-12-24 |  | 2019-03-21 | 2019-01-08 |  | 2019-04-04 | 2019-01-15 |  | 2019-04-03 | 2019-01-22 |  | 2019-04-10 | 2019-08-01 | 2019-06-26
2019-07-01 | MI19A-BS-6A | 2018-09-14 |  | 2018-09-14 | 2018-09-14 |  | 2018-09-14 | 2018-09-17 |  | 2018-09-17 | 2018-11-26 |  | 2018-11-27 | 2019-02-05 |  | 2019-03-04 | 2019-02-12 |  | 2019-03-04 | 2019-02-19 |  | 2019-02-27 | 2019-02-26 |  | 2019-03-19 | 2019-03-05 |  | 2019-04-03 | 2019-03-12 |  | 2019-04-10 | 2019-09-09 | 2019-08-14
2019-07-01 | MI20A-BS-6A | 2018-09-20 |  | 2018-09-20 | 2018-09-20 |  | 2018-09-20 | 2018-09-24 |  | 2018-09-24 | 2018-12-17 |  | 2019-01-15 | 2019-02-26 |  | 2019-04-15 | 2019-03-05 |  | 2019-04-15 | 2019-03-12 | 2019-04-30 |  | 2019-03-19 | 2019-05-08 |  | 2019-03-26 |  | 2019-04-30 | 2019-04-02 | 2019-05-08 |  | 2019-08-03 | 2019-08-11
2019-07-01 | MI20A-BS-6A | 2018-09-20 |  | 2018-09-20 | 2018-09-20 |  | 2018-09-20 | 2018-09-24 |  | 2018-09-24 | 2018-12-17 |  | 2019-01-15 | 2019-02-26 |  | 2019-04-15 | 2019-03-05 |  | 2019-04-15 | 2019-03-12 | 2019-04-30 |  | 2019-03-19 | 2019-05-08 |  | 2019-03-26 |  | 2019-04-30 | 2019-04-02 | 2019-05-08 |  | 2019-08-28 | 2019-08-19
2019-07-01 | MI20A-BS-6A | 2018-09-20 |  | 2018-09-20 | 2018-09-20 |  | 2018-09-20 | 2018-09-24 |  | 2018-09-24 | 2018-12-17 |  | 2019-01-15 | 2019-02-26 |  | 2019-04-15 | 2019-03-05 |  | 2019-04-15 | 2019-03-12 | 2019-04-30 |  | 2019-03-19 | 2019-05-08 |  | 2019-03-26 |  | 2019-04-30 | 2019-04-02 | 2019-05-08 |  | 2019-08-04 | 2019-07-20
2019-07-01 | MI21A-BS-6A | 2018-09-28 |  | 2018-09-28 | 2018-10-02 |  | 2018-10-02 | 2018-10-02 |  | 2018-10-02 | 2018-12-18 |  | 2019-01-14 | 2019-01-17 |  | 2019-04-04 | 2019-03-06 |  | 2019-04-04 | 2019-03-13 |  | 2019-03-21 | 2019-03-20 |  | 2019-04-01 | 2019-03-27 |  | 2019-04-08 | 2019-04-03 |  | 2019-04-17 | 2019-10-16 | 2019-10-05
2019-07-01 | MI22A-BS-6A | 2018-11-02 |  | 2018-11-05 | 2018-11-09 |  | 2018-11-05 | 2018-11-16 |  | 2018-11-06 | 2019-01-21 |  | 2018-12-20 | 2019-03-25 | 2019-05-01 |  | 2019-04-01 | 2019-05-01 |  | 2019-04-08 |  | 2019-04-28 | 2019-04-15 | 2019-05-06 |  | 2019-04-24 | 2019-05-14 |  | 2019-05-01 | 2019-05-21 |  | 2019-12-21 | 2020-01-12
2019-07-01 | MI23A-BS-6A | 2018-10-12 |  | 2018-10-23 | 2018-10-19 |  | 2018-10-23 | 2018-10-26 |  | 2018-10-26 | 2018-12-21 |  | 2018-12-07 | 2019-03-04 |  | 2019-04-03 | 2019-03-11 |  | 2019-04-03 | 2019-03-18 | 2019-04-30 |  | 2019-03-25 | 2019-05-08 |  | 2019-04-01 |  | 2019-04-30 | 2019-04-08 | 2019-05-08 |  | 2019-07-27 | 2019-06-28
2019-07-01 | MI23A-BS-6A | 2018-10-12 |  | 2018-10-23 | 2018-10-19 |  | 2018-10-23 | 2018-10-26 |  | 2018-10-26 | 2018-12-21 |  | 2018-12-07 | 2019-03-04 |  | 2019-04-03 | 2019-03-11 |  | 2019-04-03 | 2019-03-18 | 2019-04-30 |  | 2019-03-25 | 2019-05-08 |  | 2019-04-01 |  | 2019-04-30 | 2019-04-08 | 2019-05-08 |  | 2019-12-27 | 2020-01-01
2019-07-01 | MI25A-BS-6A | 2019-06-12 |  | 2019-04-18 | 2019-06-19 |  | 2019-04-29 | 2019-06-26 | 2019-05-03 |  | 2019-07-24 | 2019-06-04 |  | 2019-08-29 | 2019-07-09 |  | 2019-09-05 | 2019-07-16 |  | 2019-09-12 | 2019-07-23 |  | 2019-09-19 | 2019-07-30 |  | 2019-09-26 | 2019-08-06 |  | 2019-10-03 | 2019-08-13 |  | 2019-06-24 | 2019-07-31
2019-07-01 | MI26A-BS-6A | 2019-07-19 |  | 2019-04-18 | 2019-07-26 |  | 2019-04-29 | 2019-08-02 | 2019-05-03 |  | 2019-09-02 | 2019-06-04 |  | 2019-10-07 | 2019-07-09 |  | 2019-10-14 | 2019-07-16 |  | 2019-10-21 | 2019-07-23 |  | 2019-10-28 | 2019-07-30 |  | 2019-11-04 | 2019-08-06 |  | 2019-11-11 | 2019-08-13 |  | 2019-08-09 | 2019-07-29
2019-07-01 | MI27A-BS-6A | 2019-05-24 | 2019-05-23 |  | 2019-06-03 | 2019-05-31 |  | 2019-06-10 | 2019-06-07 |  | 2019-07-08 | 2019-07-05 |  | 2019-08-12 | 2019-08-09 |  | 2019-08-19 | 2019-08-16 |  | 2019-08-27 | 2019-08-23 |  | 2019-09-03 | 2019-09-02 |  | 2019-09-10 | 2019-09-09 |  | 2019-09-17 | 2019-09-16 |  | 2019-08-07 | 2019-08-30
2019-07-01 | MI30A-BS-6A | 2018-10-22 |  | 2018-11-01 | 2018-10-23 |  | 2018-11-01 | 2018-10-24 |  | 2018-11-01 | 2018-12-04 |  | 2018-12-14 | 2019-02-05 |  | 2019-04-04 | 2019-02-12 |  | 2019-04-04 | 2019-02-14 |  | 2019-04-17 | 2019-02-21 |  | 2019-04-30 | 2019-02-28 |  | 2019-04-17 | 2019-03-05 | 2019-05-02 |  | 2019-06-10 | 2019-06-09
2019-07-01 | MI30A-BS-6A | 2018-10-22 |  | 2018-11-01 | 2018-10-23 |  | 2018-11-01 | 2018-10-24 |  | 2018-11-01 | 2018-12-04 |  | 2018-12-14 | 2019-02-05 |  | 2019-04-04 | 2019-02-12 |  | 2019-04-04 | 2019-02-14 |  | 2019-04-17 | 2019-02-21 |  | 2019-04-30 | 2019-02-28 |  | 2019-04-17 | 2019-03-05 | 2019-05-02 |  | 2019-12-02 | 2019-11-02
2019-07-01 | MI30B-BS-6A |  |  | 2018-11-01 |  |  | 2018-11-01 |  |  | 2018-11-01 |  |  | 2018-12-14 | [18 empty] | 2019-10-08 | 2019-11-02
2019-07-01 | MI31A-BS-6A | 2018-10-18 |  | 2018-11-15 | 2018-10-25 |  | 2018-11-15 | 2018-11-01 |  | 2018-11-15 | 2019-01-04 |  | 2018-12-06 | 2019-03-08 |  | 2019-04-01 | 2019-03-15 |  | 2019-04-01 | 2019-03-22 |  | 2019-04-01 | 2019-03-29 |  | 2019-04-12 | 2019-04-05 |  | 2019-04-12 | 2019-04-12 |  | 2019-04-15 | 2019-08-14 | 2019-07-18
2019-07-01 | MI32A-BS-6A | 2019-03-28 | 2019-05-13 |  | 2019-04-04 | 2019-05-20 |  | 2019-04-11 | 2019-05-28 |  | 2019-05-14 | 2019-06-25 |  | 2019-06-19 | 2019-07-30 |  | 2019-06-26 | 2019-08-06 |  | 2019-07-03 | 2019-08-13 |  | 2019-07-10 | 2019-08-20 |  | 2019-07-17 | 2019-08-28 |  | 2019-07-24 | 2019-09-04 |  | 2019-06-04 | 2019-06-28
2019-07-01 | MI33A-BS-6A | 2019-05-17 | 2019-05-16 |  | 2019-05-24 | 2019-05-23 |  | 2019-06-03 | 2019-05-31 |  | 2019-07-15 | 2019-07-12 |  | 2019-09-03 | 2019-09-02 |  | 2019-09-10 | 2019-09-09 |  | 2019-09-17 | 2019-09-16 |  | 2019-09-24 | 2019-09-23 |  | 2019-10-01 | 2019-09-30 |  | 2019-10-08 | 2019-10-07 |  | 2019-06-07 | 2019-06-22
2019-07-01 | MI34A-BS-6A | 2019-06-25 | 2019-06-25 |  | 2019-07-02 | 2019-07-02 |  | 2019-07-09 | 2019-07-09 |  | 2019-08-06 | 2019-08-06 |  | 2019-09-11 | 2019-09-11 |  | 2019-09-18 | 2019-09-18 |  | 2019-09-25 | 2019-09-25 |  | 2019-10-02 | 2019-10-02 |  | 2019-10-09 | 2019-10-09 |  | 2019-10-16 | 2019-10-16 |  | 2019-08-30 | 2019-10-07
2019-07-01 | MI35A-BS-6A | 2019-07-11 | 2019-07-11 |  | 2019-07-18 | 2019-07-18 |  | 2019-07-25 | 2019-07-25 |  | 2019-09-06 | 2019-09-05 |  | 2019-10-25 | 2019-10-24 |  | 2019-11-01 | 2019-10-31 |  | 2019-11-08 | 2019-11-07 |  | 2019-11-15 | 2019-11-14 |  | 2019-11-22 | 2019-11-21 |  | 2019-11-29 | 2019-11-28 |  | 2019-06-13 | 2019-06-01
2019-07-01 | MI37A-BS-6A | 2019-07-16 | 2019-07-16 |  | 2019-07-23 | 2019-07-23 |  | 2019-07-30 | 2019-07-30 |  | 2019-08-28 | 2019-08-28 |  | 2019-10-02 | 2019-10-02 |  | 2019-10-09 | 2019-10-09 |  | 2019-10-16 | 2019-10-16 |  | 2019-10-23 | 2019-10-23 |  | 2019-10-30 | 2019-10-30 |  | 2019-11-06 | 2019-11-06 |  | 2019-08-29 | 2019-08-02
2019-07-01 | MI45A-BS-6A | 2019-04-29 | 2019-05-28 |  | 2019-05-07 | 2019-06-04 |  | 2019-05-14 | 2019-06-11 |  | 2019-06-12 | 2019-07-09 |  | 2019-07-17 | 2019-08-13 |  | 2019-07-24 | 2019-08-20 |  | 2019-07-31 | 2019-08-28 |  | 2019-08-07 | 2019-09-04 |  | 2019-08-14 | 2019-09-11 |  | 2019-08-21 | 2019-09-18 |  | 2019-06-30 | 2019-06-01
2019-07-01 | MI48A-BS-6A | 2018-08-13 |  | 2018-08-13 | 2018-08-23 |  | 2018-08-23 | 2018-08-28 |  | 2018-08-28 | 2018-09-27 |  | 2018-09-27 | 2018-11-01 |  | 2019-01-16 | 2018-11-08 |  | 2018-12-12 | 2018-11-15 |  | 2018-12-12 | 2019-01-04 |  | 2019-04-26 | 2019-01-04 |  | 2019-04-03 | 2019-01-11 |  | 2019-04-26 | 2019-12-18 | 2019-11-11
2019-07-01 | MI48A-BS-6A | 2018-08-13 |  | 2018-08-13 | 2018-08-23 |  | 2018-08-23 | 2018-08-28 |  | 2018-08-28 | 2018-09-27 |  | 2018-09-27 | 2018-11-01 |  | 2019-01-16 | 2018-11-08 |  | 2018-12-12 | 2018-11-15 |  | 2018-12-12 | 2019-01-04 |  | 2019-04-26 | 2019-01-04 |  | 2019-04-03 | 2019-01-11 |  | 2019-04-26 | 2019-07-24 | 2019-06-20
2019-07-01 | MI48A-BS-6A | 2018-08-13 |  | 2018-08-13 | 2018-08-23 |  | 2018-08-23 | 2018-08-28 |  | 2018-08-28 | 2018-09-27 |  | 2018-09-27 | 2018-11-01 |  | 2019-01-16 | 2018-11-08 |  | 2018-12-12 | 2018-11-15 |  | 2018-12-12 | 2019-01-04 |  | 2019-04-26 | 2019-01-04 |  | 2019-04-03 | 2019-01-11 |  | 2019-04-26 | 2019-09-05 | 2019-10-12
2019-07-01 | MI48A-BS-6A | 2018-08-13 |  | 2018-08-13 | 2018-08-23 |  | 2018-08-23 | 2018-08-28 |  | 2018-08-28 | 2018-09-27 |  | 2018-09-27 | 2018-11-01 |  | 2019-01-16 | 2018-11-08 |  | 2018-12-12 | 2018-11-15 |  | 2018-12-12 | 2019-01-04 |  | 2019-04-26 | 2019-01-04 |  | 2019-04-03 | 2019-01-11 |  | 2019-04-26 | 2019-08-04 | 2019-07-13
2019-07-01 | MI48A-BS-6A | 2018-08-13 |  | 2018-08-13 | 2018-08-23 |  | 2018-08-23 | 2018-08-28 |  | 2018-08-28 | 2018-09-27 |  | 2018-09-27 | 2018-11-01 |  | 2019-01-16 | 2018-11-08 |  | 2018-12-12 | 2018-11-15 |  | 2018-12-12 | 2019-01-04 |  | 2019-04-26 | 2019-01-04 |  | 2019-04-03 | 2019-01-11 |  | 2019-04-26 | 2019-09-18 | 2019-08-26
2019-07-01 | MI61A-BS-6A | 2018-08-31 |  | 2018-08-31 | 2018-08-31 |  | 2018-08-31 | 2018-09-05 |  | 2018-09-05 | 2018-10-24 |  | 2018-10-17 | 2018-12-07 | 2019-05-01 |  | 2018-12-14 | 2019-05-01 |  | 2018-12-20 | 2019-04-30 |  | 2019-02-15 | 2019-06-13 |  | 2019-02-19 | 2019-06-04 |  | 2019-02-21 | 2019-06-13 |  | 2019-11-09 | 2019-11-26
2019-07-01 | MI61A-BS-6A | 2018-08-31 |  | 2018-08-31 | 2018-08-31 |  | 2018-08-31 | 2018-09-05 |  | 2018-09-05 | 2018-10-24 |  | 2018-10-17 | 2018-12-07 | 2019-05-01 |  | 2018-12-14 | 2019-05-01 |  | 2018-12-20 | 2019-04-30 |  | 2019-02-15 | 2019-06-13 |  | 2019-02-19 | 2019-06-04 |  | 2019-02-21 | 2019-06-13 |  | 2019-11-07 | 2019-12-03
2019-07-01 | MI61A-BS-6A | 2018-08-31 |  | 2018-08-31 | 2018-08-31 |  | 2018-08-31 | 2018-09-05 |  | 2018-09-05 | 2018-10-24 |  | 2018-10-17 | 2018-12-07 | 2019-05-01 |  | 2018-12-14 | 2019-05-01 |  | 2018-12-20 | 2019-04-30 |  | 2019-02-15 | 2019-06-13 |  | 2019-02-19 | 2019-06-04 |  | 2019-02-21 | 2019-06-13 |  | 2019-10-03 | 2019-09-22
2019-07-01 | MI63A-BS-6A | 2018-11-29 |  | 2018-12-18 | 2018-12-06 |  | 2018-12-18 | 2019-01-10 |  | 2019-01-10 | 2019-02-01 |  | 2019-04-18 | 2019-03-08 | 2019-06-05 |  | 2019-03-01 | 2019-06-05 |  | 2019-03-08 | 2019-06-12 |  | 2019-03-15 | 2019-06-19 |  | 2019-03-22 | 2019-06-26 |  | 2019-03-29 | 2019-07-03 |  | 2019-11-08 | 2019-12-09
2019-07-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-09-24 | 2019-09-12
2019-07-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-09-12 | 2019-09-22
2019-07-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-11-10 | 2019-11-30
2019-07-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-11-26 | 2019-10-21
2019-07-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-07-09 | 2019-08-16
2019-07-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-10-15 | 2019-09-29
2019-07-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-10-15 | 2019-10-18
2019-07-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-07-26 | 2019-07-30
2019-07-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-08-27 | 2019-09-02
2019-07-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-09-17 | 2019-08-10
2019-07-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-08-30 | 2019-09-08
2019-07-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-08-05 | 2019-08-20
2019-07-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-12-07 | 2019-11-02
2019-07-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-06-15 | 2019-06-06
2019-07-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-06-17 | 2019-07-24
2019-07-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-09-01 | 2019-09-12
2019-07-01 | LP42A-BS-6A | 2018-03-14 |  | 2018-03-14 | 2018-03-21 |  | 2018-03-21 | 2019-11-08 | 2019-11-07 |  | 2020-01-13 | 2020-01-10 |  | 2020-03-16 | 2020-03-13 |  | 2020-03-23 | 2020-03-20 |  | 2020-03-30 | 2020-03-27 |  | 2020-04-06 | 2020-04-03 |  | 2020-04-15 | 2020-04-14 |  | 2020-04-22 | 2020-04-21 |  | 2019-09-04 | 2019-08-07
2019-07-01 | LP50A-BS-6A | 2019-05-06 | 2019-05-06 |  | 2019-05-14 | 2019-05-14 |  | 2019-05-21 | 2019-05-21 |  | 2019-07-03 | 2019-07-03 |  | 2019-08-21 | 2019-08-21 |  | 2019-08-29 | 2019-08-29 |  | 2019-09-05 | 2019-09-05 |  | 2019-09-12 | 2019-09-12 |  | 2019-09-19 | 2019-09-19 |  | 2019-09-26 | 2019-09-26 |  | 2019-07-29 | 2019-07-24
2019-07-01 | LY93A-DC-6J | [7 empty] | 2020-01-05 | [20 empty] | 2020-04-01 |  | 2019-08-11 | 2019-09-06
2019-07-01 | MI25A-DC-6J | 2019-01-15 |  | 2019-05-02 | 2019-01-22 |  | 2019-01-29 | 2019-01-29 |  | 2019-02-10 | 2019-02-19 |  | 2019-03-08 | 2019-03-26 |  | 2019-05-01 | 2019-03-26 | 2019-05-16 |  | 2019-04-02 | 2019-05-22 |  | 2019-05-10 | 2019-05-29 |  | 2019-05-02 | 2019-06-05 |  | 2019-05-10 | 2019-06-12 |  | 2019-11-06 | 2019-10-24
2019-07-01 | MI25A-DC-6J | 2019-01-15 |  | 2019-05-02 | 2019-01-22 |  | 2019-01-29 | 2019-01-29 |  | 2019-02-10 | 2019-02-19 |  | 2019-03-08 | 2019-03-26 |  | 2019-05-01 | 2019-03-26 | 2019-05-16 |  | 2019-04-02 | 2019-05-22 |  | 2019-05-10 | 2019-05-29 |  | 2019-05-02 | 2019-06-05 |  | 2019-05-10 | 2019-06-12 |  | 2019-08-17 | 2019-08-24
2019-07-01 | MI25A-DC-6J | 2019-01-15 |  | 2019-05-02 | 2019-01-22 |  | 2019-01-29 | 2019-01-29 |  | 2019-02-10 | 2019-02-19 |  | 2019-03-08 | 2019-03-26 |  | 2019-05-01 | 2019-03-26 | 2019-05-16 |  | 2019-04-02 | 2019-05-22 |  | 2019-05-10 | 2019-05-29 |  | 2019-05-02 | 2019-06-05 |  | 2019-05-10 | 2019-06-12 |  | 2019-06-04 | 2019-07-03
2019-07-01 | MI26A-DC-6J | 2019-03-25 |  | 2019-03-08 | 2019-04-01 |  | 2019-03-25 | 2019-04-08 |  | 2019-03-26 | 2019-05-09 | 2019-05-13 |  | 2019-06-14 | 2019-05-30 |  | 2019-06-21 | 2019-06-06 |  | 2019-06-28 | 2019-06-13 |  | 2019-07-05 | 2019-06-20 |  | 2019-07-12 | 2019-06-27 |  | 2019-07-19 | 2019-07-04 |  | 2019-07-07 | 2019-07-29
2019-07-01 | MI26A-DC-6J | 2019-03-25 |  | 2019-03-08 | 2019-04-01 |  | 2019-03-25 | 2019-04-08 |  | 2019-03-26 | 2019-05-09 | 2019-05-13 |  | 2019-06-14 | 2019-05-30 |  | 2019-06-21 | 2019-06-06 |  | 2019-06-28 | 2019-06-13 |  | 2019-07-05 | 2019-06-20 |  | 2019-07-12 | 2019-06-27 |  | 2019-07-19 | 2019-07-04 |  | 2019-09-30 | 2019-08-29
2019-07-01 | MI26A-DC-6J | 2019-03-25 |  | 2019-03-08 | 2019-04-01 |  | 2019-03-25 | 2019-04-08 |  | 2019-03-26 | 2019-05-09 | 2019-05-13 |  | 2019-06-14 | 2019-05-30 |  | 2019-06-21 | 2019-06-06 |  | 2019-06-28 | 2019-06-13 |  | 2019-07-05 | 2019-06-20 |  | 2019-07-12 | 2019-06-27 |  | 2019-07-19 | 2019-07-04 |  | 2019-07-06 | 2019-06-09
2019-07-01 | MI59A-DC-6J | 2018-11-14 |  | 2018-12-17 | 2018-11-21 |  | 2018-12-17 | 2018-11-28 |  | 2018-12-17 | 2019-01-31 |  | 2019-01-31 | 2019-04-04 |  | 2019-03-15 | 2019-04-11 |  | 2019-03-19 | 2019-04-18 |  | 2019-04-02 | 2019-04-29 |  | 2019-04-05 | 2019-05-07 |  | 2019-04-15 | 2019-05-14 |  | 2019-04-17 | 2019-10-02 | 2019-10-18
2019-07-01 | RR01A-DC-6J | 2018-06-29 |  | 2018-07-16 | 2018-07-06 |  | 2018-07-17 | 2018-07-13 |  | 2018-07-20 | 2018-09-06 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-05 | 2018-11-05 |  | 2018-12-10 | 2018-11-12 |  | 2019-02-11 | 2018-11-19 |  | 2019-02-13 | 2018-11-26 |  | 2019-02-11 | 2018-12-03 |  | 2019-03-11 | 2019-09-15 | 2019-09-09
2019-07-01 | RR01A-DC-6J | 2018-06-29 |  | 2018-07-16 | 2018-07-06 |  | 2018-07-17 | 2018-07-13 |  | 2018-07-20 | 2018-09-06 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-05 | 2018-11-05 |  | 2018-12-10 | 2018-11-12 |  | 2019-02-11 | 2018-11-19 |  | 2019-02-13 | 2018-11-26 |  | 2019-02-11 | 2018-12-03 |  | 2019-03-11 | 2019-11-10 | 2019-10-28
2019-07-01 | RR01A-DC-6J | 2018-06-29 |  | 2018-07-16 | 2018-07-06 |  | 2018-07-17 | 2018-07-13 |  | 2018-07-20 | 2018-09-06 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-05 | 2018-11-05 |  | 2018-12-10 | 2018-11-12 |  | 2019-02-11 | 2018-11-19 |  | 2019-02-13 | 2018-11-26 |  | 2019-02-11 | 2018-12-03 |  | 2019-03-11 | 2019-09-20 | 2019-10-26
2019-07-01 | RR01A-DC-6J | 2018-06-29 |  | 2018-07-16 | 2018-07-06 |  | 2018-07-17 | 2018-07-13 |  | 2018-07-20 | 2018-09-06 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-05 | 2018-11-05 |  | 2018-12-10 | 2018-11-12 |  | 2019-02-11 | 2018-11-19 |  | 2019-02-13 | 2018-11-26 |  | 2019-02-11 | 2018-12-03 |  | 2019-03-11 | 2019-09-19 | 2019-09-22
2019-07-01 | RR01B-DC-6J | 2018-11-06 |  | 2018-03-16 | 2018-11-13 |  | 2018-03-22 | 2018-07-13 |  | 2018-07-20 | 2018-08-03 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-07 | 2018-11-05 |  | 2018-12-11 | 2018-11-12 |  | 2019-02-20 | 2018-11-19 |  | 2019-02-21 | 2018-11-26 |  | 2019-02-27 | 2018-12-03 |  | 2019-03-14 | 2019-07-13 | 2019-08-18
2019-07-01 | RR01B-DC-6J | 2018-11-06 |  | 2018-03-16 | 2018-11-13 |  | 2018-03-22 | 2018-07-13 |  | 2018-07-20 | 2018-08-03 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-07 | 2018-11-05 |  | 2018-12-11 | 2018-11-12 |  | 2019-02-20 | 2018-11-19 |  | 2019-02-21 | 2018-11-26 |  | 2019-02-27 | 2018-12-03 |  | 2019-03-14 | 2019-06-15 | 2019-06-30
2019-07-01 | RR01B-DC-6J | 2018-11-06 |  | 2018-03-16 | 2018-11-13 |  | 2018-03-22 | 2018-07-13 |  | 2018-07-20 | 2018-08-03 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-07 | 2018-11-05 |  | 2018-12-11 | 2018-11-12 |  | 2019-02-20 | 2018-11-19 |  | 2019-02-21 | 2018-11-26 |  | 2019-02-27 | 2018-12-03 |  | 2019-03-14 | 2019-08-22 | 2019-09-04
2019-07-01 | RR01B-DC-6J | 2018-11-06 |  | 2018-03-16 | 2018-11-13 |  | 2018-03-22 | 2018-07-13 |  | 2018-07-20 | 2018-08-03 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-07 | 2018-11-05 |  | 2018-12-11 | 2018-11-12 |  | 2019-02-20 | 2018-11-19 |  | 2019-02-21 | 2018-11-26 |  | 2019-02-27 | 2018-12-03 |  | 2019-03-14 | 2019-12-21 | 2019-11-16
2019-07-01 | RR01B-DC-6J | 2018-11-06 |  | 2018-03-16 | 2018-11-13 |  | 2018-03-22 | 2018-07-13 |  | 2018-07-20 | 2018-08-03 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-07 | 2018-11-05 |  | 2018-12-11 | 2018-11-12 |  | 2019-02-20 | 2018-11-19 |  | 2019-02-21 | 2018-11-26 |  | 2019-02-27 | 2018-12-03 |  | 2019-03-14 | 2019-12-01 | 2019-11-06
2019-07-01 | RR04A-DC-6J | 2018-06-15 |  | 2018-06-26 | 2018-06-22 |  | 2018-07-03 | 2018-06-29 |  | 2018-07-06 | 2018-07-20 |  | 2018-07-31 | 2018-09-19 |  | 2018-10-25 | 2018-09-26 |  | 2018-10-29 | 2018-10-03 |  | 2018-11-12 | 2018-10-10 |  | 2019-01-03 | 2018-10-17 |  | 2018-12-04 | 2018-10-24 |  | 2019-04-03 | 2019-11-27 | 2019-11-17
2019-07-01 | RR04A-DC-6J | 2018-06-15 |  | 2018-06-26 | 2018-06-22 |  | 2018-07-03 | 2018-06-29 |  | 2018-07-06 | 2018-07-20 |  | 2018-07-31 | 2018-09-19 |  | 2018-10-25 | 2018-09-26 |  | 2018-10-29 | 2018-10-03 |  | 2018-11-12 | 2018-10-10 |  | 2019-01-03 | 2018-10-17 |  | 2018-12-04 | 2018-10-24 |  | 2019-04-03 | 2019-06-29 | 2019-07-04
2019-07-01 | RR04A-DC-6J | 2018-06-15 |  | 2018-06-26 | 2018-06-22 |  | 2018-07-03 | 2018-06-29 |  | 2018-07-06 | 2018-07-20 |  | 2018-07-31 | 2018-09-19 |  | 2018-10-25 | 2018-09-26 |  | 2018-10-29 | 2018-10-03 |  | 2018-11-12 | 2018-10-10 |  | 2019-01-03 | 2018-10-17 |  | 2018-12-04 | 2018-10-24 |  | 2019-04-03 | 2019-08-11 | 2019-08-19
2019-07-01 | RR04A-DC-6J | 2018-06-15 |  | 2018-06-26 | 2018-06-22 |  | 2018-07-03 | 2018-06-29 |  | 2018-07-06 | 2018-07-20 |  | 2018-07-31 | 2018-09-19 |  | 2018-10-25 | 2018-09-26 |  | 2018-10-29 | 2018-10-03 |  | 2018-11-12 | 2018-10-10 |  | 2019-01-03 | 2018-10-17 |  | 2018-12-04 | 2018-10-24 |  | 2019-04-03 | 2019-09-28 | 2019-09-17
2019-07-01 | RR06A-DC-6J | 2017-12-11 |  | 2018-01-12 | 2017-12-18 |  | 2018-01-18 | 2018-01-02 |  | 2018-01-26 | 2018-01-30 |  | 2018-03-02 | 2018-03-13 |  | 2018-03-23 | 2018-03-13 |  | 2018-04-17 | 2018-03-20 |  | 2018-07-31 | 2018-04-26 |  | 2018-08-02 | 2018-04-19 |  | 2018-07-23 | 2018-04-26 |  | 2018-08-06 | 2019-06-26 | 2019-06-14
2019-07-01 | RR06A-DC-6J | 2017-12-11 |  | 2018-01-12 | 2017-12-18 |  | 2018-01-18 | 2018-01-02 |  | 2018-01-26 | 2018-01-30 |  | 2018-03-02 | 2018-03-13 |  | 2018-03-23 | 2018-03-13 |  | 2018-04-17 | 2018-03-20 |  | 2018-07-31 | 2018-04-26 |  | 2018-08-02 | 2018-04-19 |  | 2018-07-23 | 2018-04-26 |  | 2018-08-06 | 2019-09-09 | 2019-09-25
2019-07-01 | RR10A-DC-6J | 2018-03-07 |  | 2018-02-28 | 2018-03-14 |  | 2018-03-01 | 2018-03-21 |  | 2018-03-15 | 2018-04-13 |  | 2018-04-09 | 2018-08-02 |  | 2018-08-18 | 2018-11-16 |  | 2018-11-23 | 2018-12-07 |  | 2018-12-19 | 2018-12-14 |  | 2018-12-21 | 2018-12-21 |  | 2019-01-21 | 2019-01-07 |  | 2019-02-06 | 2019-11-07 | 2019-11-17
2019-07-01 | RR10A-DC-6J | 2018-03-07 |  | 2018-02-28 | 2018-03-14 |  | 2018-03-01 | 2018-03-21 |  | 2018-03-15 | 2018-04-13 |  | 2018-04-09 | 2018-08-02 |  | 2018-08-18 | 2018-11-16 |  | 2018-11-23 | 2018-12-07 |  | 2018-12-19 | 2018-12-14 |  | 2018-12-21 | 2018-12-21 |  | 2019-01-21 | 2019-01-07 |  | 2019-02-06 | 2019-12-18 | 2020-01-01
2019-07-01 | RR16A-DC-6J |  |  | 2019-04-02 |  |  |  |  | 2019-06-06 | [20 empty] | 2019-09-26 |  | 2019-06-30 | 2019-06-27
2019-07-01 | RR17A-DC-6J | [8 empty] | 2019-01-18 | [20 empty] | 2019-05-09 | 2019-07-08 | 2019-07-15
2019-07-01 | RR20A-DC-6J | 2018-08-23 |  | 2018-07-27 | 2018-08-31 |  | 2018-08-03 | 2018-09-07 |  | 2018-08-09 | 2018-09-28 |  | 2018-09-21 | 2018-11-30 |  | 2019-01-07 | 2018-12-07 |  | 2019-01-17 | 2018-12-14 |  | 2019-02-13 | 2018-12-21 |  | 2019-02-25 | 2019-01-07 |  | 2019-01-23 | 2019-01-14 |  | 2019-03-04 | 2019-08-10 | 2019-09-12
2019-07-01 | RR20A-DC-6J | 2018-08-23 |  | 2018-07-27 | 2018-08-31 |  | 2018-08-03 | 2018-09-07 |  | 2018-08-09 | 2018-09-28 |  | 2018-09-21 | 2018-11-30 |  | 2019-01-07 | 2018-12-07 |  | 2019-01-17 | 2018-12-14 |  | 2019-02-13 | 2018-12-21 |  | 2019-02-25 | 2019-01-07 |  | 2019-01-23 | 2019-01-14 |  | 2019-03-04 | 2019-11-23 | 2019-10-25
2019-07-01 | RR20A-DC-6J | 2018-08-23 |  | 2018-07-27 | 2018-08-31 |  | 2018-08-03 | 2018-09-07 |  | 2018-08-09 | 2018-09-28 |  | 2018-09-21 | 2018-11-30 |  | 2019-01-07 | 2018-12-07 |  | 2019-01-17 | 2018-12-14 |  | 2019-02-13 | 2018-12-21 |  | 2019-02-25 | 2019-01-07 |  | 2019-01-23 | 2019-01-14 |  | 2019-03-04 | 2019-10-05 | 2019-10-29
2019-07-01 | RR20A-DC-6J | 2018-08-23 |  | 2018-07-27 | 2018-08-31 |  | 2018-08-03 | 2018-09-07 |  | 2018-08-09 | 2018-09-28 |  | 2018-09-21 | 2018-11-30 |  | 2019-01-07 | 2018-12-07 |  | 2019-01-17 | 2018-12-14 |  | 2019-02-13 | 2018-12-21 |  | 2019-02-25 | 2019-01-07 |  | 2019-01-23 | 2019-01-14 |  | 2019-03-04 | 2019-10-23 | 2019-10-23
2019-07-01 | RR47A-DC-6J | 2018-12-13 |  | 2018-09-26 | 2018-12-20 |  | 2018-10-02 | 2019-01-04 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-01-31 | 2019-01-11 |  | 2019-01-31 | 2019-01-18 |  | 2019-03-29 | 2019-01-25 |  | 2019-04-12 | 2019-02-01 |  | 2019-03-26 | 2019-02-08 |  | 2019-04-16 | 2019-07-08 | 2019-06-09
2019-07-01 | RR47A-DC-6J | 2018-12-13 |  | 2018-09-26 | 2018-12-20 |  | 2018-10-02 | 2019-01-04 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-01-31 | 2019-01-11 |  | 2019-01-31 | 2019-01-18 |  | 2019-03-29 | 2019-01-25 |  | 2019-04-12 | 2019-02-01 |  | 2019-03-26 | 2019-02-08 |  | 2019-04-16 | 2019-11-23 | 2020-01-02
2019-07-01 | RR47A-DC-6J | 2018-12-13 |  | 2018-09-26 | 2018-12-20 |  | 2018-10-02 | 2019-01-04 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-01-31 | 2019-01-11 |  | 2019-01-31 | 2019-01-18 |  | 2019-03-29 | 2019-01-25 |  | 2019-04-12 | 2019-02-01 |  | 2019-03-26 | 2019-02-08 |  | 2019-04-16 | 2019-06-08 | 2019-05-11
2019-07-01 | RR47A-DC-6J | 2018-12-13 |  | 2018-09-26 | 2018-12-20 |  | 2018-10-02 | 2019-01-04 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-01-31 | 2019-01-11 |  | 2019-01-31 | 2019-01-18 |  | 2019-03-29 | 2019-01-25 |  | 2019-04-12 | 2019-02-01 |  | 2019-03-26 | 2019-02-08 |  | 2019-04-16 | 2019-10-10 | 2019-11-02
2019-07-01 | RR47A-DC-6J | 2018-12-13 |  | 2018-09-26 | 2018-12-20 |  | 2018-10-02 | 2019-01-04 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-01-31 | 2019-01-11 |  | 2019-01-31 | 2019-01-18 |  | 2019-03-29 | 2019-01-25 |  | 2019-04-12 | 2019-02-01 |  | 2019-03-26 | 2019-02-08 |  | 2019-04-16 | 2019-11-03 | 2019-11-01
2019-07-01 | RR47A-DC-6J | 2018-12-13 |  | 2018-09-26 | 2018-12-20 |  | 2018-10-02 | 2019-01-04 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-01-31 | 2019-01-11 |  | 2019-01-31 | 2019-01-18 |  | 2019-03-29 | 2019-01-25 |  | 2019-04-12 | 2019-02-01 |  | 2019-03-26 | 2019-02-08 |  | 2019-04-16 | 2019-10-30 | 2019-11-17
2019-07-01 | RR47A-DC-6J | 2018-12-13 |  | 2018-09-26 | 2018-12-20 |  | 2018-10-02 | 2019-01-04 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-01-31 | 2019-01-11 |  | 2019-01-31 | 2019-01-18 |  | 2019-03-29 | 2019-01-25 |  | 2019-04-12 | 2019-02-01 |  | 2019-03-26 | 2019-02-08 |  | 2019-04-16 | 2019-07-07 | 2019-07-26
2019-07-01 | RR58A-DC-6J | 2019-08-20 | 2019-08-20 |  | 2019-08-28 | 2019-08-28 |  | 2019-09-04 | 2019-09-04 |  | 2019-10-02 | 2019-10-02 |  | 2019-11-06 | 2019-11-06 |  | 2019-11-13 | 2019-11-13 |  | 2019-11-20 | 2019-11-20 |  | 2019-11-27 | 2019-11-27 |  | 2019-12-04 | 2019-12-04 |  | 2019-12-11 | 2019-12-11 |  | 2019-11-16 | 2019-12-25
2019-07-01 | LP01A-DC-6J | 2018-11-08 |  | 2018-10-29 | 2018-11-15 |  | 2018-10-29 | 2018-11-22 |  | 2018-10-31 | 2018-12-20 |  | 2018-11-28 | 2019-02-01 |  | 2019-01-29 | 2019-02-08 |  | 2019-02-18 | 2019-02-15 |  | 2019-02-26 | 2019-02-22 |  | 2019-04-02 | 2019-03-01 |  | 2019-03-18 | 2019-03-08 |  | 2019-04-05 | 2019-10-27 | 2019-10-24
2019-07-01 | LP02A-DC-6J | 2018-09-20 |  | 2018-09-21 | 2018-09-27 |  | 2018-09-25 | 2018-10-04 |  | 2018-10-31 | 2018-11-01 |  | 2018-12-03 | 2018-12-06 |  | 2019-01-29 | 2018-12-13 |  | 2019-02-18 | 2018-12-20 |  | 2019-03-11 | 2019-01-04 |  | 2019-04-02 | 2019-01-11 |  | 2019-03-19 | 2019-01-18 |  | 2019-04-03 | 2019-11-19 | 2019-10-26
2019-07-01 | LP02A-DC-6J | 2018-09-20 |  | 2018-09-21 | 2018-09-27 |  | 2018-09-25 | 2018-10-04 |  | 2018-10-31 | 2018-11-01 |  | 2018-12-03 | 2018-12-06 |  | 2019-01-29 | 2018-12-13 |  | 2019-02-18 | 2018-12-20 |  | 2019-03-11 | 2019-01-04 |  | 2019-04-02 | 2019-01-11 |  | 2019-03-19 | 2019-01-18 |  | 2019-04-03 | 2019-08-26 | 2019-09-04
2019-07-01 | LP04A-DC-6J | [30 empty] | 2019-08-02 | 2019-07-27
2019-07-01 | LP08A-DC-6J | 2019-06-06 | 2019-06-06 |  | 2019-06-13 | 2019-06-13 |  | 2019-06-20 | 2019-06-20 |  | 2019-07-18 | 2019-07-18 |  | 2019-08-22 | 2019-08-22 |  | 2019-08-30 | 2019-08-30 |  | 2019-09-06 | 2019-09-06 |  | 2019-09-13 | 2019-09-13 |  | 2019-09-20 | 2019-09-20 |  | 2019-09-27 | 2019-09-27 |  | 2019-09-25 | 2019-09-26
2019-07-01 | LP67A-DC-6J | 2019-10-07 | 2019-10-07 |  | 2019-10-14 | 2019-10-14 |  | 2019-10-21 | 2019-10-21 |  | 2019-11-18 | 2019-11-18 |  | 2019-12-23 | 2019-12-23 |  | 2020-01-07 | 2020-01-07 |  | 2020-01-14 | 2020-01-14 |  | 2020-01-21 | 2020-01-21 |  | 2020-01-28 | 2020-01-28 |  | 2020-02-04 | 2020-02-04 |  | 2019-08-16 | 2019-07-09

## Procurement Data-Aug
Date | Workpackage No. | Design Docs Complete Planned | Design Docs Complete Forecast | Design Docs Complete Actual | Complete RFI Planned | Complete RFI Forecast | Complete RFI Actual | Issue RFP Planned | Issue RFP Forecast | Issue RFP Actual | Bid Return Planned | Bid Return Forecast | Bid Return Actual | Technical Evaluation Planned | Technical Evaluation Forecast | Technical Evaluation Actual | Commercial Evaluation Planned | Commercial Evaluation Forecast | Commercial Evaluation Actual | RFQ Issue Planned | RFQ Issue Forecast | RFQ Issue Actual | RFQ Approved Planned | RFQ Approved Forecast | RFQ Approved Actual | Complete RFT Planned | Complete RFT Forecast | Complete RFT Actual | Issue PO Planned | Issue PO Forecast | Issue PO Actual | ROS | ETA
2019-08-01 | LY38A-BS-XX | 2018-05-13 |  | 2018-06-22 | 2018-04-24 |  | 2018-06-07 | 2018-05-16 |  | 2018-07-06 | 2018-06-19 |  | 2018-06-04 | 2018-08-28 |  | 2018-06-22 | 2018-07-07 |  | 2018-07-08 | 2018-08-27 |  | 2018-11-22 | 2018-08-01 |  | 2018-09-22 | 2018-08-25 |  | 2018-08-29 | 2018-09-22 |  | 2018-09-19 | 2019-08-11 | 2019-07-25
2019-08-01 | NH07A-BS-XX | 2018-03-11 |  | 2018-04-14 | 2018-04-17 |  | 2018-04-29 | 2018-03-30 |  | 2018-05-22 | 2018-05-25 |  | 2018-05-04 | 2018-05-23 |  | 2018-07-29 | 2018-05-21 |  | 2018-05-28 | 2018-04-13 |  | 2018-07-18 | 2018-06-14 |  | 2018-08-23 | 2018-06-05 |  | 2018-07-03 | 2018-07-15 |  | 2018-09-25 | 2019-12-23 | 2019-12-14
2019-08-01 | LY03A-BS-YY | 2019-04-07 |  | 2019-03-20 | 2019-05-17 |  | 2019-03-21 | 2019-04-14 |  | 2019-04-27 | 2019-04-25 |  | 2019-07-01 | 2019-06-28 | 2019-06-06 |  | 2019-05-01 | 2019-05-20 |  | 2019-06-08 | 2019-07-24 |  | 2019-05-20 | 2019-08-23 |  | 2019-07-13 | 2019-08-23 |  | 2019-07-22 | 2019-08-04 |  | 2019-12-23 | 2020-01-10
2019-08-01 | LY03A-BS-YY | 2019-04-03 |  | 2019-03-06 | 2019-04-28 |  | 2019-03-18 | 2019-05-26 |  | 2019-05-13 | 2019-05-03 |  | 2019-07-07 | 2019-06-11 | 2019-06-24 |  | 2019-05-23 | 2019-07-23 |  | 2019-08-03 | 2019-07-10 |  | 2019-07-27 | 2019-07-11 |  | 2019-08-03 | 2019-07-16 |  | 2019-05-27 | 2019-08-24 |  | 2019-12-22 | 2019-12-10
2019-08-01 | LY03A-BS-YY | 2019-04-07 |  | 2019-04-25 | 2019-04-06 |  | 2019-04-16 | 2019-04-11 |  | 2019-04-24 | 2019-05-02 |  | 2019-05-27 | 2019-07-02 | 2019-08-09 |  | 2019-05-14 | 2019-07-29 |  | 2019-07-10 | 2019-05-17 |  | 2019-07-02 | 2019-08-04 |  | 2019-06-17 | 2019-07-25 |  | 2019-06-24 | 2019-06-07 |  | 2019-09-13 | 2019-08-26
2019-08-01 | LY03A-BS-YY | 2019-05-17 |  | 2019-03-23 | 2019-04-25 |  | 2019-03-04 | 2019-04-22 |  | 2019-03-20 | 2019-05-09 |  | 2019-05-01 | 2019-05-16 | 2019-08-09 |  | 2019-06-16 | 2019-08-08 |  | 2019-06-03 | 2019-06-30 |  | 2019-07-04 | 2019-06-11 |  | 2019-06-28 | 2019-08-10 |  | 2019-07-18 | 2019-06-18 |  | 2019-07-22 | 2019-08-13
2019-08-01 | LY26A-BS-YY | 2018-07-13 |  | 2018-06-30 | 2018-07-29 |  | 2018-05-25 | 2018-06-11 |  | 2018-07-12 | 2018-08-14 |  | 2018-07-09 | 2018-06-27 |  | 2018-11-04 | 2018-07-24 |  | 2018-07-20 | 2018-09-22 |  | 2018-08-14 | 2018-08-29 |  | 2018-10-08 | 2018-09-01 |  | 2018-11-23 | 2018-08-09 |  | 2019-01-01 | 2019-12-01 | 2019-12-12
2019-08-01 | LY26A-BS-YY | 2018-07-07 |  | 2018-06-23 | 2018-07-22 |  | 2018-05-27 | 2018-07-09 |  | 2018-06-07 | 2018-06-16 |  | 2018-08-14 | 2018-08-13 |  | 2018-11-28 | 2018-06-26 |  | 2018-07-08 | 2018-08-13 |  | 2018-08-24 | 2018-08-20 |  | 2018-09-24 | 2018-10-08 |  | 2018-12-13 | 2018-09-21 |  | 2019-01-08 | 2019-10-25 | 2019-09-24
2019-08-01 | LY33A-BS-YY | 2019-01-27 |  | 2019-01-14 | 2018-11-23 |  | 2019-01-12 | 2018-12-06 |  | 2019-03-02 | 2019-01-03 |  | 2019-02-05 | 2019-03-13 |  | 2019-05-09 | 2019-03-17 |  | 2019-05-28 | 2019-03-21 |  | 2019-03-30 | 2019-02-16 |  | 2019-08-07 | 2019-03-12 |  | 2019-04-28 | 2019-03-10 | 2019-07-31 |  | 2019-08-05 | 2019-07-14
2019-08-01 | LY35A-BS-YY | 2018-12-11 |  | 2019-01-09 | 2018-11-11 |  | 2019-01-15 | 2019-01-11 |  | 2018-11-18 | 2019-01-07 |  | 2019-02-18 | 2019-01-03 |  | 2019-02-25 | 2018-12-21 |  | 2019-01-29 | 2019-01-04 |  | 2019-02-06 | 2019-01-19 |  | 2019-03-09 | 2019-01-27 |  | 2019-03-07 | 2019-03-10 |  | 2019-04-07 | 2019-10-20 | 2019-10-02
2019-08-01 | LY38B-BS-YY | 2019-05-04 |  | 2019-04-11 | 2019-06-23 |  | 2019-06-05 | 2019-04-11 |  | 2019-05-07 | 2019-07-06 | 2019-06-04 |  | 2019-06-30 | 2019-08-27 |  | 2019-07-31 | 2019-08-14 |  | 2019-06-11 | 2019-08-28 |  | 2019-08-17 | 2019-07-10 |  | 2019-06-29 | 2019-06-22 |  | 2019-07-31 | 2019-08-03 |  | 2019-10-06 | 2019-09-27
2019-08-01 | LY41A-BS-YY | [30 empty] | 2019-08-25 | 2019-07-16
2019-08-01 | LY42A-BS-YY | 2019-04-06 |  | 2019-02-24 | 2019-05-04 |  | 2019-03-30 | 2019-04-29 |  | 2019-05-11 | 2019-04-21 |  | 2019-05-01 | 2019-06-21 | 2019-08-07 |  | 2019-06-29 | 2019-07-28 |  | 2019-05-12 | 2019-08-10 |  | 2019-05-28 | 2019-06-02 |  | 2019-06-08 | 2019-07-23 |  | 2019-06-10 | 2019-08-12 |  | 2019-06-04 | 2019-05-21
2019-08-01 | LY45A-BS-YY | 2018-06-05 |  | 2018-08-26 | 2018-05-26 |  | 2018-08-09 | 2018-08-05 |  | 2018-07-06 | 2018-06-24 |  | 2018-08-03 | 2018-08-20 |  | 2018-09-18 | 2018-09-18 |  | 2018-10-21 | 2018-10-03 |  | 2018-10-08 | 2018-08-24 |  | 2018-11-01 | 2018-09-03 |  | 2018-09-19 | 2018-10-22 |  | 2018-12-24 | 2019-10-13 | 2019-10-19
2019-08-01 | LY45A-BS-YY | 2018-07-05 |  | 2018-09-09 | 2018-07-12 |  | 2018-08-12 | 2018-07-04 |  | 2018-08-25 | 2018-09-19 |  | 2018-07-29 | 2018-09-22 |  | 2018-09-16 | 2018-09-13 |  | 2018-09-29 | 2018-09-27 |  | 2018-10-30 | 2018-08-19 |  | 2018-11-21 | 2018-09-25 |  | 2018-09-10 | 2018-09-12 |  | 2018-12-15 | 2019-07-08 | 2019-06-20
2019-08-01 | LY49A-BS-YY | 2019-02-01 |  | 2019-01-18 | 2019-02-25 |  | 2019-01-08 | 2019-01-31 |  | 2019-01-27 | 2019-04-15 |  | 2019-04-13 |  |  | 2019-04-18 | 2019-05-12 |  | 2019-05-06 | 2019-04-19 |  | 2019-02-18 | 2019-04-17 |  | 2019-07-07 | 2019-03-16 |  | 2019-05-28 | 2019-04-03 | 2019-07-02 |  | 2019-09-30 | 2019-09-03
2019-08-01 | LY50B-BS-YY | 2019-02-27 |  | 2019-01-25 | 2018-12-29 |  | 2019-02-27 | 2019-03-15 |  | 2019-01-06 | 2019-04-11 |  | 2019-02-01 | 2019-03-09 |  | 2019-03-27 | 2019-04-06 |  | 2019-04-01 | 2019-05-26 |  | 2019-04-28 | 2019-04-21 |  | 2019-06-01 | 2019-06-08 |  | 2019-06-23 | 2019-04-14 | 2019-08-08 |  | 2019-07-06 | 2019-05-29
2019-08-01 | LY66B-BS-YY | 2019-12-20 |  | 2019-04-22 | 2019-12-04 | 2020-01-27 |  | 2019-12-03 | 2020-01-19 |  | 2020-01-24 | 2020-03-11 |  | 2020-03-24 | 2020-03-25 |  | 2020-03-09 | 2020-03-04 |  | 2020-04-25 | 2020-04-26 |  | 2020-04-06 | 2020-03-17 |  | 2020-04-08 | 2020-05-23 |  | 2020-04-05 | 2020-04-27 |  | 2019-10-29 | 2019-12-02
2019-08-01 | LY66B-BS-YY | 2020-01-10 |  | 2019-03-13 | 2019-12-19 | 2019-12-22 |  | 2019-12-07 | 2020-01-30 |  | 2020-01-17 | 2020-02-02 |  | 2020-03-04 | 2020-03-11 |  | 2020-04-10 | 2020-04-21 |  | 2020-05-23 | 2020-04-01 |  | 2020-06-11 | 2020-04-15 |  | 2020-03-24 | 2020-06-10 |  | 2020-04-03 | 2020-06-14 |  | 2019-10-15 | 2019-11-28
2019-08-01 | LY66C-BS-YY | 2018-10-01 |  | 2018-12-29 | 2018-12-13 |  | 2019-01-10 | 2018-12-23 |  | 2019-01-09 | 2019-01-03 |  | 2018-11-14 | 2019-01-21 |  | 2019-02-12 | 2018-11-18 |  | 2018-12-31 | 2018-12-25 |  | 2019-01-30 | 2019-02-23 |  | 2019-01-03 | 2019-01-28 |  | 2018-12-24 | 2018-12-18 |  | 2019-02-18 | 2019-09-14 | 2019-10-06
2019-08-01 | AL88A-BS-YY | 2019-04-07 |  | 2018-12-03 | 2019-02-23 |  | 2018-11-30 | 2019-03-21 |  | 2018-11-27 | 2019-05-01 |  | 2019-02-19 | 2019-04-02 |  | 2019-06-19 | 2019-06-12 |  | 2019-06-22 | 2019-04-24 |  | 2019-05-21 | 2019-05-16 |  | 2019-07-13 | 2019-04-14 |  | 2019-04-16 | 2019-07-03 | 2019-06-12 |  | 2019-06-27 | 2019-07-07
2019-08-01 | NH07B-BS-YY | 2018-03-14 |  | 2018-10-02 | 2018-03-05 |  | 2018-10-04 | 2018-04-13 |  | 2018-08-30 | 2018-05-26 |  | 2018-07-30 |  |  | 2019-07-05 | 2018-05-02 |  | 2019-05-29 | 2018-12-05 | 2019-07-03 |  | 2018-12-22 | 2019-08-24 |  | 2019-01-09 | 2019-08-29 |  | 2018-12-31 | 2019-07-12 |  | 2019-12-12 | 2019-12-29
2019-08-01 | NH07B-BS-YY | 2018-05-06 |  | 2018-08-31 | 2018-04-01 |  | 2018-08-29 | 2018-05-02 |  | 2018-08-25 | 2018-06-03 |  | 2018-08-26 |  |  | 2019-06-30 | 2018-06-18 |  | 2019-06-16 | 2018-12-14 | 2019-07-01 |  | 2019-01-08 | 2019-09-21 |  | 2019-01-20 | 2019-07-03 |  | 2019-01-05 | 2019-08-22 |  | 2019-10-15 | 2019-09-25
2019-08-01 | NH07B-BS-YY | 2018-03-05 |  | 2018-09-07 | 2018-04-22 |  | 2018-08-22 | 2018-04-04 |  | 2018-09-20 | 2018-05-26 |  | 2018-08-09 |  |  | 2019-05-15 | 2018-06-28 |  | 2019-06-15 | 2018-11-16 | 2019-07-25 |  | 2019-01-15 | 2019-08-01 |  | 2018-12-08 | 2019-08-28 |  | 2019-02-01 | 2019-10-01 |  | 2019-07-11 | 2019-06-05
2019-08-01 | NH07B-BS-YY | 2018-04-09 |  | 2018-07-25 | 2018-04-29 |  | 2018-08-29 | 2018-03-10 |  | 2018-08-18 | 2018-05-20 |  | 2018-10-09 |  |  | 2019-05-11 | 2018-06-12 |  | 2019-05-04 | 2019-02-01 | 2019-08-03 |  | 2018-11-26 | 2019-07-19 |  | 2019-01-01 | 2019-08-20 |  | 2019-01-15 | 2019-08-22 |  | 2019-07-30 | 2019-07-07
2019-08-01 | NH07C-BS-YY | 2019-03-03 |  | 2019-04-15 | 2019-02-17 |  | 2019-02-13 | 2019-02-21 |  | 2019-05-01 | 2019-03-23 |  | 2019-05-17 | 2019-05-12 |  | 2019-06-27 | 2019-04-09 |  | 2019-05-17 | 2019-05-09 | 2019-07-04 |  | 2019-05-19 | 2019-06-19 |  | 2019-07-10 | 2019-07-11 |  | 2019-07-03 | 2019-07-29 |  | 2019-08-29 | 2019-09-26
2019-08-01 | NH18A-BS-YY | 2018-06-15 |  | 2018-07-10 | 2018-07-02 |  | 2018-08-02 | 2018-06-27 |  | 2018-08-05 | 2018-08-13 |  | 2018-08-08 | 2018-08-14 |  | 2018-08-28 | 2018-09-01 |  | 2018-10-29 | 2018-07-19 |  | 2018-09-29 | 2018-08-15 |  | 2018-12-17 | 2018-08-12 |  | 2018-11-05 | 2018-08-11 |  | 2018-11-06 | 2019-08-19 | 2019-08-18
2019-08-01 | NH18B-BS-YY |  |  | 2019-05-28 |  |  | 2019-06-04 |  |  | 2019-04-30 |  |  | 2019-05-25 |  |  |  |  | 2019-08-20 | [8 empty] | 2019-08-21 |  |  | 2019-08-23 |  | 2019-08-03 | 2019-08-04
2019-08-01 | NH18B-BS-YY |  |  | 2019-03-29 |  |  | 2019-05-14 |  |  | 2019-04-26 |  |  | 2019-04-26 |  |  |  |  | 2019-07-22 | [8 empty] | 2019-06-17 |  |  | 2019-07-18 |  | 2019-06-19 | 2019-05-14
2019-08-01 | NH49A-BS-YY | 2019-01-08 |  | 2019-01-21 | 2018-12-26 |  | 2019-02-01 | 2018-12-31 |  | 2019-01-24 | 2019-02-13 |  | 2019-03-29 | 2019-04-12 | 2019-06-25 |  | 2019-03-15 | 2019-06-15 |  | 2019-04-05 | 2019-08-12 |  | 2019-05-14 | 2019-05-28 |  | 2019-05-26 | 2019-08-22 |  | 2019-06-19 | 2019-06-26 |  | 2019-09-01 | 2019-08-12
2019-08-01 | MI01A-BS-YY | 2018-12-19 |  | 2018-12-15 | 2018-10-29 |  | 2019-02-26 | 2018-12-30 |  | 2018-11-18 | 2019-02-11 |  | 2019-01-17 | 2019-02-17 |  | 2019-03-05 | 2019-01-09 |  | 2019-02-17 | 2019-01-11 |  | 2019-05-30 | 2018-12-18 | 2019-07-14 |  | 2018-12-30 |  | 2019-06-14 | 2019-03-05 | 2019-07-08 |  | 2019-06-10 | 2019-07-03
2019-08-01 | MI01A-BS-YY | 2019-01-06 |  | 2019-02-11 | 2018-12-20 |  | 2019-01-01 | 2018-11-29 |  | 2018-11-17 | 2019-01-27 |  | 2018-12-18 | 2019-02-01 |  | 2019-03-24 | 2019-02-18 |  | 2019-03-18 | 2018-12-30 |  | 2019-03-22 | 2019-02-21 | 2019-06-01 |  | 2019-01-01 |  | 2019-05-06 | 2019-02-19 | 2019-08-18 |  | 2019-09-21 | 2019-08-25
2019-08-01 | MI01A-BS-YY | 2018-12-17 |  | 2018-12-22 | 2018-11-01 |  | 2019-02-05 | 2018-12-19 |  | 2019-01-08 | 2019-01-12 |  | 2018-12-13 | 2018-12-12 |  | 2019-04-15 | 2019-02-18 |  | 2019-02-18 | 2019-03-07 |  | 2019-05-09 | 2019-01-08 | 2019-06-17 |  | 2019-02-06 |  | 2019-05-20 | 2019-03-11 | 2019-06-22 |  | 2019-06-30 | 2019-08-03
2019-08-01 | MI01A-BS-YY | 2018-11-16 |  | 2018-12-19 | 2018-12-28 |  | 2019-02-20 | 2018-11-21 |  | 2018-10-28 | 2019-01-10 |  | 2018-12-29 | 2019-01-26 |  | 2019-04-26 | 2019-02-11 |  | 2019-03-12 | 2019-01-18 |  | 2019-03-18 | 2018-12-23 | 2019-07-17 |  | 2018-12-28 |  | 2019-06-17 | 2019-02-15 | 2019-07-31 |  | 2019-07-07 | 2019-08-13
2019-08-01 | MI16A-BS-YY | 2019-01-04 |  | 2018-12-20 | 2018-11-14 |  | 2018-11-22 | 2018-11-10 |  | 2019-01-01 | 2019-01-08 |  | 2018-12-28 | 2019-01-26 |  | 2019-07-08 | 2019-03-08 |  | 2019-07-24 | 2019-02-02 | 2019-06-30 |  | 2019-04-26 | 2019-06-12 |  | 2019-04-21 | 2019-07-12 |  | 2019-04-26 | 2019-07-26 |  | 2019-06-14 | 2019-05-26
2019-08-01 | MI16A-BS-YY | 2018-11-23 |  | 2018-12-01 | 2018-11-11 |  | 2018-11-17 | 2018-11-08 |  | 2019-01-26 | 2019-01-21 |  | 2018-12-27 | 2018-12-31 |  | 2019-06-30 | 2019-02-11 |  | 2019-08-09 | 2019-03-19 | 2019-08-01 |  | 2019-02-07 | 2019-08-24 |  | 2019-04-06 | 2019-07-29 |  | 2019-04-28 | 2019-06-25 |  | 2019-10-10 | 2019-09-12
2019-08-01 | MI20A-BS-YY | 2018-12-21 |  | 2018-12-17 | 2018-12-26 |  | 2018-12-17 | 2018-11-16 |  | 2018-11-25 | 2019-01-29 |  | 2019-01-12 | 2019-01-27 |  | 2019-02-24 | 2019-01-28 |  | 2019-04-13 | 2019-01-14 |  | 2019-03-01 | 2019-01-28 |  | 2019-04-27 | 2019-01-16 |  | 2019-06-24 | 2019-03-13 | 2019-08-15 |  | 2019-09-30 | 2019-09-23
2019-08-01 | MI21A-BS-YY | 2019-01-07 |  | 2018-12-15 | 2018-11-23 |  | 2018-12-16 | 2018-12-23 |  | 2019-01-15 | 2019-02-03 |  | 2018-11-28 | 2019-03-14 |  | 2019-02-21 | 2019-04-14 |  | 2019-03-05 | 2019-04-03 |  | 2019-04-29 | 2019-03-27 |  | 2019-07-01 | 2019-02-18 |  | 2019-05-01 | 2019-03-26 | 2019-07-12 |  | 2019-09-21 | 2019-09-13
2019-08-01 | MI23A-BS-YY | 2018-12-17 |  | 2018-11-11 | 2018-12-27 |  | 2019-01-18 | 2018-11-24 |  | 2018-12-21 | 2019-02-23 |  | 2019-01-01 | 2019-03-22 |  | 2019-06-23 | 2019-04-07 |  | 2019-04-17 | 2019-02-10 |  | 2019-02-12 | 2019-03-16 |  | 2019-05-08 | 2019-03-08 |  | 2019-06-20 | 2019-03-24 | 2019-06-21 |  | 2019-09-25 | 2019-10-22
2019-08-01 | MI23B-BS-YY |  |  | 2019-01-09 |  |  | 2018-12-20 |  |  | 2019-01-12 | 2018-12-28 |  | 2018-12-23 | 2019-01-09 |  | 2018-12-26 | 2019-03-05 |  | 2019-01-28 | 2019-03-18 |  | 2019-02-01 | 2019-02-16 |  | 2018-12-23 | 2019-01-23 |  | 2019-01-19 | 2019-04-03 |  | 2019-01-20 | 2019-08-21 | 2019-09-08
2019-08-01 | MI25A-BS-YY | 2019-06-21 |  | 2019-05-12 | 2019-06-13 |  | 2019-07-23 | 2019-06-26 | 2019-08-06 |  | 2019-07-27 | 2019-08-17 |  | 2019-07-20 | 2019-09-07 |  | 2019-06-11 | 2019-06-23 |  | 2019-08-12 | 2019-08-17 |  | 2019-06-15 | 2019-09-13 |  | 2019-08-19 | 2019-07-27 |  | 2019-09-09 | 2019-10-07 |  | 2019-12-30 | 2020-01-25
2019-08-01 | MI26A-BS-YY | 2019-05-10 |  | 2019-06-30 | 2019-04-22 |  | 2019-08-07 | 2019-07-18 | 2019-07-07 |  | 2019-05-19 | 2019-06-20 |  | 2019-06-23 | 2019-08-21 |  | 2019-06-17 | 2019-08-04 |  | 2019-08-27 | 2019-07-06 |  | 2019-08-09 | 2019-09-17 |  | 2019-08-30 | 2019-09-07 |  | 2019-09-22 | 2019-08-12 |  | 2019-06-09 | 2019-05-09
2019-08-01 | MI27A-BS-YY | [30 empty] | 2019-09-24 | 2019-10-23
2019-08-01 | MI32A-BS-YY | 2019-01-26 |  | 2019-01-20 | 2019-02-10 |  | 2019-03-24 | 2019-01-21 |  | 2019-03-09 | 2019-02-12 |  | 2019-02-14 | 2019-01-25 | 2019-05-19 |  | 2019-02-11 | 2019-05-23 |  | 2019-02-11 | 2019-07-21 |  | 2019-04-02 | 2019-08-12 |  | 2019-04-18 | 2019-08-19 |  | 2019-05-13 | 2019-08-17 |  | 2019-09-15 | 2019-09-27
2019-08-01 | MI35A-BS-YY | 2019-07-30 | 2019-08-14 |  | 2019-09-14 | 2019-07-20 |  | 2019-10-17 | 2019-08-28 |  | 2019-11-05 | 2019-08-13 |  | 2019-09-28 | 2019-09-17 |  | 2019-11-17 | 2019-09-05 |  | 2019-11-19 | 2019-11-13 |  | 2019-12-17 | 2019-10-30 |  | 2019-10-05 | 2019-09-22 |  | 2019-11-16 | 2019-10-04 |  | 2019-10-22 | 2019-11-27
2019-08-01 | MI37A-BS-YY | 2019-07-01 | 2019-07-02 |  | 2019-05-21 | 2019-07-12 |  | 2019-06-25 | 2019-07-10 |  | 2019-06-05 | 2019-08-18 |  | 2019-07-02 | 2019-07-16 |  | 2019-09-02 | 2019-09-11 |  | 2019-06-19 | 2019-08-16 |  | 2019-08-12 | 2019-09-24 |  | 2019-07-09 | 2019-10-22 |  | 2019-10-05 | 2019-08-26 |  | 2019-12-03 | 2020-01-05
2019-08-01 | MI45A-BS-YY | 2019-08-05 | 2019-07-18 |  | 2019-07-13 | 2019-08-21 |  | 2019-09-20 | 2019-08-30 |  | 2019-08-26 | 2019-10-14 |  | 2019-08-16 | 2019-10-04 |  | 2019-10-12 | 2019-10-29 |  | 2019-09-28 | 2019-09-04 |  | 2019-10-05 | 2019-10-21 |  | 2019-09-24 | 2019-11-21 |  | 2019-10-27 | 2019-12-16 |  | 2019-07-15 | 2019-07-30
2019-08-01 | MI67A-BS-YY | 2019-06-30 |  | 2018-12-05 | 2019-05-22 |  | 2018-12-06 | 2019-05-25 |  | 2018-12-22 | 2019-08-20 |  | 2018-11-28 | 2019-07-08 |  | 2019-01-21 | 2019-09-08 |  | 2018-12-22 | 2019-09-02 |  | 2019-02-13 | 2019-07-22 |  | 2019-01-28 | 2019-10-09 |  | 2019-02-06 | 2019-09-16 |  | 2019-04-30 | 2019-06-28 | 2019-06-17
2019-08-01 | LP99A-BS-1F | 2018-11-25 |  | 2018-10-13 | 2018-10-25 |  | 2018-09-15 | 2018-10-16 |  | 2018-09-26 | 2018-12-06 |  | 2019-01-03 | 2019-01-20 |  | 2018-12-16 | 2019-01-02 |  | 2018-11-23 | 2019-01-13 |  | 2018-12-07 | 2019-01-31 |  | 2019-02-09 | 2018-12-02 |  | 2019-01-13 | 2019-02-01 |  | 2019-03-02 | 2019-07-16 | 2019-07-16
2019-08-01 | LP99A-BS-1F | 2018-09-14 |  | 2018-11-20 | 2018-11-13 |  | 2018-10-27 | 2018-10-16 |  | 2018-10-08 | 2018-11-08 |  | 2018-12-09 | 2019-01-26 |  | 2018-11-18 | 2018-12-28 |  | 2018-12-05 | 2018-11-16 |  | 2018-12-30 | 2019-02-13 |  | 2019-02-28 | 2019-02-13 |  | 2019-03-03 | 2018-12-22 |  | 2019-01-14 | 2019-07-26 | 2019-08-08
2019-08-01 | LP99A-BS-1F | 2018-10-09 |  | 2018-10-17 | 2018-10-03 |  | 2018-10-25 | 2018-10-17 |  | 2018-11-25 | 2018-11-13 |  | 2018-12-12 | 2018-12-22 |  | 2019-02-01 | 2018-12-06 |  | 2019-01-21 | 2019-01-31 |  | 2019-02-11 | 2018-12-25 |  | 2019-02-06 | 2019-01-03 |  | 2019-01-23 | 2018-12-25 |  | 2019-03-21 | 2019-09-03 | 2019-09-27
2019-08-01 | LP99A-BS-1F | 2018-10-12 |  | 2018-10-13 | 2018-10-18 |  | 2018-10-20 | 2018-10-10 |  | 2018-10-15 | 2018-10-21 |  | 2019-01-01 | 2018-11-12 |  | 2018-12-13 | 2018-11-12 |  | 2019-01-13 | 2019-01-13 |  | 2018-12-08 | 2019-01-25 |  | 2019-02-01 | 2019-01-09 |  | 2019-02-16 | 2019-03-05 |  | 2019-02-02 | 2019-11-09 | 2019-10-04
2019-08-01 | LY03A-BS-2E | 2019-12-18 | 2019-10-13 |  | 2019-10-16 | 2019-10-08 |  | 2019-12-16 | 2019-10-12 |  | 2019-11-26 | 2019-11-30 |  | 2020-01-27 | 2020-02-02 |  | 2020-01-02 | 2019-12-19 |  | 2020-02-10 | 2020-01-05 |  | 2020-02-07 | 2020-01-19 |  | 2020-01-07 | 2020-01-11 |  | 2020-02-01 | 2020-02-04 |  | 2019-12-17 | 2019-11-19
2019-08-01 | LY03A-BS-2E | 2019-09-22 | 2019-12-06 |  | 2019-10-09 | 2019-10-09 |  | 2020-01-02 | 2019-11-09 |  | 2020-01-02 | 2019-12-21 |  | 2019-11-18 | 2019-11-21 |  | 2020-01-14 | 2020-01-01 |  | 2019-12-12 | 2019-12-12 |  | 2019-12-13 | 2020-01-23 |  | 2020-02-09 | 2020-02-10 |  | 2020-01-31 | 2020-01-14 |  | 2019-11-26 | 2019-12-30
2019-08-01 | LY03A-BS-2E | 2019-09-24 | 2019-10-06 |  | 2019-12-25 | 2019-09-29 |  | 2019-12-28 | 2019-10-22 |  | 2019-12-29 | 2019-12-30 |  | 2019-12-16 | 2020-01-29 |  | 2020-01-05 | 2019-12-13 |  | 2020-01-28 | 2020-01-26 |  | 2019-12-25 | 2020-02-14 |  | 2019-12-26 | 2020-01-25 |  | 2020-01-08 | 2020-03-02 |  | 2019-12-02 | 2020-01-03
2019-08-01 | LY26A-BS-2E | 2020-04-05 | 2020-04-03 |  | 2020-06-12 | 2020-03-25 |  | 2020-06-23 | 2020-04-02 |  | 2020-07-02 | 2020-05-17 |  | 2020-09-06 | 2020-07-22 |  | 2020-08-28 | 2020-08-23 |  | 2020-09-25 | 2020-09-10 |  | 2020-08-13 | 2020-08-17 |  | 2020-08-02 | 2020-09-06 |  | 2020-10-17 | 2020-09-10 |  | 2019-08-14 | 2019-07-19
2019-08-01 | AL19A-BS-2E | 2019-06-21 |  | 2018-07-16 | 2019-07-06 |  | 2018-06-25 | 2019-07-07 |  | 2018-07-15 | 2019-07-09 |  | 2018-10-17 | 2019-08-21 |  | 2019-05-13 | 2019-07-10 |  | 2019-03-21 | [6 empty] | 2019-10-01 | 2019-05-30 |  | 2019-08-20 | 2019-07-24 |  | 2019-10-12 | 2019-11-16
2019-08-01 | AL87A-BS-2E | 2019-09-07 | 2019-07-04 |  | 2019-08-15 | 2019-06-17 |  | 2019-10-14 | 2019-06-30 |  | 2019-10-14 | 2019-07-14 |  | 2019-09-20 | 2019-08-15 |  | 2019-12-01 | 2019-08-01 |  | 2019-11-03 | 2019-09-21 |  | 2019-11-25 | 2019-10-03 |  | 2019-10-14 | 2019-08-15 |  | 2019-11-24 | 2019-10-27 |  | 2019-10-11 | 2019-09-13
2019-08-01 | AL87A-BS-2E | 2019-09-26 | 2019-06-15 |  | 2019-08-22 | 2019-07-02 |  | 2019-08-08 | 2019-06-12 |  | 2019-10-09 | 2019-07-11 |  | 2019-10-15 | 2019-07-26 |  | 2019-12-10 | 2019-08-18 |  | 2019-11-01 | 2019-08-20 |  | 2019-12-04 | 2019-09-14 |  | 2019-10-25 | 2019-08-21 |  | 2019-12-20 | 2019-08-07 |  | 2019-07-18 | 2019-09-27
2019-08-01 | LP98A-BS-2E | 2021-03-29 | 2021-05-23 |  | 2021-05-16 | 2021-06-01 |  | 2021-05-11 | 2021-04-07 |  | 2021-05-11 | 2021-05-27 |  | 2021-07-18 | 2021-08-14 |  | 2021-08-05 | 2021-06-28 |  | 2021-07-29 | 2021-06-15 |  | 2021-09-08 | 2021-07-03 |  | 2021-09-03 | 2021-09-01 |  | 2021-09-17 | 2021-07-14 |  | 2019-11-05 | 2019-12-03
2019-08-01 | ZA01A-BW-6A | 2019-04-22 |  | 2019-03-30 | 2019-06-10 |  | 2019-06-03 | 2019-05-13 |  | 2019-04-11 | 2019-05-03 |  | 2019-06-19 | 2019-06-11 | 2019-08-05 |  | 2019-07-17 |  | 2019-07-09 | [6 empty] | 2019-07-27 | 2019-07-23 |  | 2019-08-12 | 2019-08-08 |  | 2019-11-04 | 2019-11-07
2019-08-01 | ZA01A-BW-6A | 2019-04-24 |  | 2019-06-03 | 2019-06-10 |  | 2019-06-10 | 2019-06-16 |  | 2019-06-07 | 2019-05-16 |  | 2019-05-31 | 2019-07-03 | 2019-08-17 |  | 2019-05-18 |  | 2019-06-14 | [6 empty] | 2019-06-28 | 2019-06-19 |  | 2019-07-21 | 2019-06-24 |  | 2019-06-06 | 2019-06-26
2019-08-01 | ZA01A-BW-6A | 2019-04-26 |  | 2019-04-04 | 2019-04-06 |  | 2019-04-15 | 2019-05-15 |  | 2019-05-25 | 2019-04-26 |  | 2019-06-16 | 2019-07-20 | 2019-06-28 |  | 2019-06-11 |  | 2019-07-11 | [6 empty] | 2019-08-08 | 2019-08-23 |  | 2019-07-06 | 2019-06-28 |  | 2019-06-27 | 2019-06-20
2019-08-01 | ZA01B-BW-6A | 2019-07-26 | 2019-06-27 |  | 2019-06-20 | 2019-07-19 |  | 2019-06-15 | 2019-07-31 |  | 2019-08-26 | 2019-10-02 |  | 2019-09-17 | 2019-07-22 |  | 2019-09-10 | 2019-10-20 |  |  |  |  | 2019-08-28 | 2019-10-31 |  | 2019-09-09 | 2019-09-23 |  | 2019-09-22 | 2019-11-20 |  | 2019-12-21 | 2020-01-06
2019-08-01 | ZA04A-BW-6A | 2019-05-03 |  | 2019-03-09 | 2019-03-26 |  | 2019-05-24 | 2019-06-07 |  | 2019-05-09 | 2019-06-30 |  | 2019-06-18 | 2019-06-19 | 2019-07-21 |  | 2019-06-08 |  | 2019-05-31 | [6 empty] | 2019-06-02 | 2019-06-08 |  | 2019-08-14 | 2019-07-15 |  | 2019-12-12 | 2019-11-22
2019-08-01 | ZA04A-BW-6A | 2019-03-13 |  | 2019-04-17 | 2019-04-17 |  | 2019-05-17 | 2019-04-01 |  | 2019-05-11 | 2019-06-07 |  | 2019-05-10 | 2019-05-03 | 2019-08-05 |  | 2019-08-03 |  | 2019-07-29 | [6 empty] | 2019-05-29 | 2019-06-19 |  | 2019-07-03 | 2019-06-19 |  | 2019-06-16 | 2019-06-07
2019-08-01 | ZA04A-BW-6A | 2019-06-05 |  | 2019-05-08 | 2019-05-15 |  | 2019-06-04 | 2019-04-17 |  | 2019-04-14 | 2019-06-08 |  | 2019-06-03 | 2019-07-25 | 2019-06-16 |  | 2019-07-01 |  | 2019-06-18 | [6 empty] | 2019-07-17 | 2019-08-06 |  | 2019-08-21 | 2019-06-30 |  | 2019-06-27 | 2019-07-22
2019-08-01 | ZA08A-BW-6A | 2020-03-10 | 2020-02-23 |  | 2020-04-15 | 2020-05-07 |  | 2020-04-28 | 2020-05-15 |  | 2020-04-26 | 2020-06-08 |  | 2020-04-09 | 2020-06-21 |  | 2020-06-06 | 2020-06-19 | [7 empty] | 2020-05-06 | 2020-06-13 |  | 2020-07-14 | 2020-06-05 |  | 2019-10-10 | 2019-08-31
2019-08-01 | ZA09A-BW-6A | 2019-12-23 | 2020-01-13 |  | 2019-12-29 | 2020-01-06 |  | 2019-11-11 | 2019-12-20 |  | 2020-01-30 | 2020-02-27 |  | 2019-12-17 | 2020-02-01 |  | 2020-02-20 | 2020-02-09 | [7 empty] | 2020-02-23 | 2020-01-23 |  | 2020-02-27 | 2020-02-17 |  | 2019-12-12 | 2019-11-16
2019-08-01 | ZA10A-BW-6A | 2019-09-03 | 2019-08-25 |  | 2019-07-01 | 2019-09-08 |  | 2019-09-29 | 2019-07-28 |  | 2019-08-12 | 2019-10-01 |  | 2019-09-08 | 2019-10-24 |  | 2019-09-22 | 2019-10-25 | [7 empty] | 2019-11-10 | 2019-12-02 |  | 2019-11-07 | 2019-11-06 |  | 2019-12-21 | 2019-12-21
2019-08-01 | ZA12A-BW-6A | 2019-05-08 |  | 2019-06-13 | 2019-07-12 |  | 2019-04-27 | 2019-07-14 |  | 2019-06-22 | 2019-05-30 | 2019-07-18 |  | 2019-07-02 | 2019-06-18 |  | 2019-07-23 | 2019-07-04 | [7 empty] | 2019-09-25 | 2019-09-15 |  | 2019-09-19 | 2019-10-01 |  | 2019-11-27 | 2019-12-22
2019-08-01 | LY02A-BW-6A | 2019-05-02 |  | 2019-06-21 | 2019-05-22 |  | 2019-07-01 | 2019-06-01 |  | 2019-05-20 | 2019-08-12 |  | 2019-05-11 | 2019-08-19 | 2019-07-26 |  | 2019-07-08 | 2019-08-15 |  |  | 2019-06-03 |  |  | 2019-08-16 |  | 2019-07-17 | 2019-08-07 |  | 2019-09-22 | 2019-09-17 |  | 2019-10-06 | 2019-09-25
2019-08-01 | LY02A-BW-6A | 2019-06-17 |  | 2019-05-27 | 2019-06-10 |  | 2019-06-02 | 2019-05-04 |  | 2019-06-26 | 2019-07-04 |  | 2019-06-17 | 2019-06-24 | 2019-07-07 |  | 2019-07-22 | 2019-07-14 |  |  | 2019-07-19 |  |  | 2019-07-11 |  | 2019-07-26 | 2019-09-28 |  | 2019-09-13 | 2019-08-04 |  | 2019-09-30 | 2019-09-15
2019-08-01 | LY03A-BW-6A | 2019-06-28 |  | 2019-05-27 | 2019-05-01 |  | 2019-04-27 | 2019-05-25 |  | 2019-06-17 | 2019-07-14 | 2019-08-09 |  | 2019-06-26 | 2019-06-22 |  | 2019-09-09 | 2019-07-10 | [7 empty] | 2019-09-04 | 2019-10-08 |  | 2019-08-29 | 2019-09-06 |  | 2019-12-22 | 2020-01-19
2019-08-01 | LY04A-BW-6A | 2019-05-05 |  | 2019-03-29 | 2019-05-18 |  | 2019-06-03 | 2019-04-15 |  | 2019-05-14 | 2019-04-28 |  | 2019-04-13 | 2019-04-18 |  | 2019-06-26 | 2019-05-17 |  | 2019-06-12 | [6 empty] | 2019-07-01 | 2019-06-27 |  | 2019-05-30 | 2019-07-01 |  | 2019-12-21 | 2020-01-06
2019-08-01 | LY05A-BW-6A | 2019-09-10 | 2019-07-13 |  | 2019-07-28 | 2019-09-02 |  | 2019-08-06 | 2019-09-14 |  | 2019-09-09 | 2019-10-20 |  | 2019-09-26 | 2019-09-27 |  | 2019-11-04 | 2019-10-13 | [7 empty] | 2019-12-07 | 2019-11-26 |  | 2019-11-17 | 2019-11-07 |  | 2019-08-15 | 2019-07-09
2019-08-01 | LY48A-BW-6A | 2019-05-20 |  | 2019-05-11 | 2019-04-22 |  | 2019-05-12 | 2019-06-16 |  | 2019-05-02 | 2019-05-29 | 2019-08-12 |  | 2019-07-07 | 2019-07-25 |  | 2019-08-20 | 2019-09-16 | [7 empty] | 2019-08-31 | 2019-08-26 |  | 2019-09-11 | 2019-09-22 |  | 2019-10-21 | 2019-09-23
2019-08-01 | LY48A-BW-6A | 2019-04-24 |  | 2019-06-16 | 2019-05-25 |  | 2019-06-20 | 2019-06-08 |  | 2019-05-01 | 2019-07-18 | 2019-07-22 |  | 2019-06-15 | 2019-06-30 |  | 2019-08-11 | 2019-08-21 | [7 empty] | 2019-08-29 | 2019-10-05 |  | 2019-08-29 | 2019-10-25 |  | 2019-10-05 | 2019-09-01
2019-08-01 | LY48A-BW-6A | 2019-04-09 |  | 2019-05-04 | 2019-07-12 |  | 2019-07-07 | 2019-05-24 |  | 2019-06-22 | 2019-08-16 | 2019-08-14 |  | 2019-07-18 | 2019-09-05 |  | 2019-08-04 | 2019-08-24 | [7 empty] | 2019-07-15 | 2019-09-10 |  | 2019-10-06 | 2019-08-05 |  | 2019-12-28 | 2019-12-03
2019-08-01 | LY48A-BW-6A | 2019-05-29 |  | 2019-05-21 | 2019-06-17 |  | 2019-06-08 | 2019-07-10 |  | 2019-06-21 | 2019-06-17 | 2019-07-27 |  | 2019-08-27 | 2019-08-21 |  | 2019-09-05 | 2019-07-21 | [7 empty] | 2019-10-05 | 2019-08-20 |  | 2019-07-26 | 2019-08-30 |  | 2019-11-05 | 2019-10-12
2019-08-01 | LY49A-BW-6A | 2019-03-01 |  | 2019-03-24 | 2019-04-17 |  | 2019-04-13 | 2019-05-26 |  | 2019-03-24 | 2019-06-16 |  | 2019-05-07 | 2019-04-12 | 2019-05-17 |  | 2019-04-20 | 2019-07-31 | [7 empty] | 2019-06-02 | 2019-07-15 |  | 2019-05-22 | 2019-08-07 |  | 2019-06-30 | 2019-06-20
2019-08-01 | LY78A-BW-6A |  | 2019-07-06 |  |  | 2019-07-02 |  |  | 2019-07-27 |  |  | 2019-08-28 |  |  | 2019-07-27 |  |  | 2019-10-02 | [8 empty] | 2019-11-07 |  |  | 2019-09-21 |  | 2019-07-26 | 2019-06-21
2019-08-01 | LY78B-BW-6A |  | 2019-08-02 |  |  | 2019-06-27 |  |  | 2019-09-05 |  |  | 2019-08-06 |  |  | 2019-07-29 |  |  | 2019-09-30 | [8 empty] | 2019-11-04 |  |  | 2019-10-13 |  | 2019-08-14 | 2019-07-21
2019-08-01 | LY78C-BW-6A |  | 2019-08-02 |  |  | 2019-08-11 |  |  | 2019-08-30 |  |  | 2019-09-30 |  |  | 2019-08-11 |  |  | 2019-10-28 | [8 empty] | 2019-10-04 |  |  | 2019-11-01 |  | 2019-10-24 | 2019-11-10
2019-08-01 | LY78C-BW-6A |  | 2019-05-31 |  |  | 2019-08-29 |  |  | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-09-04 |  |  | 2019-09-09 | [8 empty] | 2019-09-13 |  |  | 2019-11-06 |  | 2019-08-19 | 2019-09-05
2019-08-01 | LY78C-BW-6A |  | 2019-08-12 |  |  | 2019-08-14 |  |  | 2019-07-12 |  |  | 2019-08-01 |  |  | 2019-09-14 |  |  | 2019-09-15 | [8 empty] | 2019-09-19 |  |  | 2019-10-16 |  | 2019-08-09 | 2019-07-25
2019-08-01 | LY78D-BW-6A |  | 2019-08-12 |  |  | 2019-07-23 |  |  | 2019-08-27 |  |  | 2019-09-20 |  |  | 2019-08-23 |  |  | 2019-09-14 | [8 empty] | 2019-11-29 |  |  | 2019-10-31 |  | 2019-06-04 | 2019-06-10
2019-08-01 | LY78D-BW-6A |  | 2019-08-22 |  |  | 2019-08-24 |  |  | 2019-09-05 |  |  | 2019-08-21 |  |  | 2019-11-13 |  |  | 2019-11-09 | [8 empty] | 2019-09-28 |  |  | 2019-12-26 |  | 2019-06-26 | 2019-07-27
2019-08-01 | QW10A-QW-6A | [30 empty] | 2019-12-14 | 2020-01-13
2019-08-01 | QW60A-QW-6A | 2019-05-29 | 2019-09-18 |  | 2019-05-17 | 2019-07-16 |  | 2019-06-20 | 2019-08-16 |  | 2019-05-30 | 2019-11-16 |  | 2019-07-08 | 2019-11-30 |  | 2019-07-09 | 2019-10-06 | [7 empty] | 2019-10-10 | 2019-10-15 |  | 2019-09-20 | 2019-11-02 |  | 2019-08-08 | 2019-08-26
2019-08-01 | QW60A-QW-6A | 2019-06-06 | 2019-07-07 |  | 2019-05-16 | 2019-10-05 |  | 2019-07-13 | 2019-08-27 |  | 2019-06-07 | 2019-09-16 |  | 2019-07-11 | 2019-10-09 |  | 2019-09-14 | 2019-12-07 | [7 empty] | 2019-08-17 | 2019-10-17 |  | 2019-08-16 | 2019-12-15 |  | 2019-08-19 | 2019-09-01
2019-08-01 | QW65A-QW-6A | 2019-11-17 | 2019-09-02 |  | 2019-09-18 | 2019-09-27 |  | 2019-10-11 | 2019-10-07 |  | 2019-10-10 | 2019-10-22 |  | 2020-01-22 | 2020-01-03 |  | 2019-11-17 | 2019-11-24 | [7 empty] | 2020-02-21 | 2020-02-13 |  | 2019-12-26 | 2019-12-21 |  | 2019-11-28 | 2019-11-01
2019-08-01 | QW67A-QW-6A | 2019-07-14 | 2019-08-09 |  | 2019-08-20 | 2019-08-03 |  | 2019-09-06 | 2019-10-08 |  | 2019-08-15 | 2019-09-27 |  | 2019-11-15 | 2019-10-09 |  | 2019-11-20 | 2019-11-25 | [7 empty] | 2019-11-28 | 2019-11-17 |  | 2020-01-01 | 2019-12-31 |  | 2019-11-20 | 2019-11-02
2019-08-01 | QW70A-QW-6A | [30 empty] | 2019-09-25 | 2019-10-22
2019-08-01 | AL91A-BW-6A | [30 empty] | 2019-08-14 | 2019-07-13
2019-08-01 | VC02A-BW-6A | 2019-05-02 |  | 2019-07-03 | 2019-06-05 |  | 2019-06-06 | 2019-04-22 |  | 2019-05-24 | 2019-06-13 |  | 2019-05-05 | 2019-07-12 | 2019-05-10 |  | 2019-09-03 | 2019-06-06 | [7 empty] | 2019-07-30 | 2019-07-01 |  | 2019-09-13 | 2019-07-06 |  | 2019-11-22 | 2019-11-18
2019-08-01 | VC03A-BW-6A | 2019-04-24 | 2019-07-18 |  | 2019-05-15 | 2019-07-21 |  | 2019-05-23 | 2019-06-07 |  | 2019-06-20 | 2019-08-28 |  | 2019-08-05 | 2019-09-23 |  | 2019-08-21 | 2019-08-01 | [7 empty] | 2019-09-18 | 2019-09-12 |  | 2019-07-27 | 2019-09-02 |  | 2019-11-05 | 2019-10-25
2019-08-01 | VC03A-BW-6A | 2019-05-14 | 2019-07-19 |  | 2019-04-25 | 2019-06-25 |  | 2019-06-01 | 2019-07-09 |  | 2019-06-30 | 2019-08-14 |  | 2019-06-08 | 2019-09-20 |  | 2019-07-11 | 2019-10-27 | [7 empty] | 2019-09-02 | 2019-10-22 |  | 2019-08-24 | 2019-09-07 |  | 2019-11-28 | 2019-12-28
2019-08-01 | NH19A-BW-6A | 2019-11-20 | 2019-10-14 |  | 2019-10-28 | 2019-11-09 |  | 2019-11-27 | 2019-11-09 |  | 2019-12-19 | 2019-11-23 |  | 2019-12-06 | 2019-12-21 |  | 2020-02-28 | 2020-02-25 | [7 empty] | 2020-04-05 | 2020-04-11 |  | 2020-03-21 | 2020-04-14 |  | 2019-11-13 | 2019-12-08
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-04-21 | 2019-08-02 |  | 2019-06-13 | 2019-09-02 |  | 2019-10-07 | 2019-10-18
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-06-03 | 2019-08-04 |  | 2019-05-08 | 2019-06-14 |  | 2019-08-16 | 2019-08-23
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-05-09 | 2019-08-26 |  | 2019-07-13 | 2019-08-16 |  | 2019-09-28 | 2019-10-30
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-05-26 | 2019-07-16 |  | 2019-05-22 | 2019-07-12 |  | 2019-06-05 | 2019-05-28
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-05-28 | 2019-08-22 |  | 2019-06-13 | 2019-08-22 |  | 2019-07-17 | 2019-06-17
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-05-23 | 2019-06-14 |  | 2019-05-24 | 2019-07-05 |  | 2019-11-13 | 2019-11-20
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-06-28 | 2019-06-25 |  | 2019-06-03 | 2019-08-06 |  | 2019-09-27 | 2019-10-23
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-05-05 | 2019-06-22 |  | 2019-05-15 | 2019-07-12 |  | 2019-11-02 | 2019-10-23
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-06-24 | 2019-07-16 |  | 2019-06-17 | 2019-08-12 |  | 2019-12-22 | 2019-11-18
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-04-29 | 2019-07-26 |  | 2019-05-02 | 2019-08-23 |  | 2019-12-24 | 2020-01-16
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-05-06 | 2019-08-14 |  | 2019-05-16 | 2019-08-08 |  | 2019-06-16 | 2019-07-05
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-04-24 | 2019-08-26 |  | 2019-06-26 | 2019-08-14 |  | 2019-12-28 | 2019-11-30
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-07-12 | 2019-08-20 |  | 2019-05-11 | 2019-07-02 |  | 2019-08-22 | 2019-08-01
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-06-15 | 2019-08-02 |  | 2019-05-28 | 2019-08-30 |  | 2019-10-27 | 2019-09-25
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-07-02 | 2019-07-19 |  | 2019-05-01 | 2019-06-20 |  | 2019-11-27 | 2019-10-29
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-06-11 | 2019-08-22 |  | 2019-05-29 | 2019-06-14 |  | 2019-09-07 | 2019-08-01
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-05-07 | 2019-07-15 |  | 2019-07-04 | 2019-07-13 |  | 2019-11-01 | 2019-11-25
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-04-21 | 2019-08-01 |  | 2019-07-25 | 2019-06-17 |  | 2019-12-05 | 2019-12-06
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-04-28 | 2019-07-11 |  | 2019-07-23 | 2019-08-20 |  | 2019-07-29 | 2019-07-16
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-06-24 | 2019-07-15 |  | 2019-06-18 | 2019-06-20 |  | 2019-11-15 | 2019-11-11
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-04-28 | 2019-07-09 |  | 2019-06-18 | 2019-07-08 |  | 2019-10-17 | 2019-10-16
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-07-04 | 2019-08-14 |  | 2019-05-23 | 2019-07-28 |  | 2019-12-14 | 2019-12-09
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-05-26 | 2019-08-22 |  | 2019-07-19 | 2019-07-08 |  | 2019-12-05 | 2019-12-19
2019-08-01 | MI01A-BW-6A | [24 empty] | 2019-06-17 | 2019-08-15 |  | 2019-05-11 | 2019-07-22 |  | 2019-09-04 | 2019-09-13
2019-08-01 | MI01B-BW-6A | [24 empty] | 2019-07-17 | 2019-06-23 |  | 2019-06-14 | 2019-07-07 |  | 2019-11-11 | 2019-12-05
2019-08-01 | MI01B-BW-6A | [24 empty] | 2019-07-08 | 2019-07-02 |  | 2019-07-08 | 2019-08-07 |  | 2019-12-24 | 2019-12-01
2019-08-01 | MI01B-BW-6A | [24 empty] | 2019-06-21 | 2019-06-08 |  | 2019-05-24 | 2019-06-30 |  | 2019-09-01 | 2019-08-08
2019-08-01 | MI01B-BW-6A | [24 empty] | 2019-05-26 | 2019-08-09 |  | 2019-06-29 | 2019-07-06 |  | 2019-10-12 | 2019-11-19
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-07-10 | 2019-06-15 |  | 2019-05-28 | 2019-09-06 |  | 2019-10-26 | 2019-10-30
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-05-10 | 2019-08-19 |  | 2019-04-27 | 2019-07-16 |  | 2019-11-09 | 2019-10-09
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-05-02 | 2019-06-29 |  | 2019-06-06 | 2019-06-26 |  | 2019-11-09 | 2019-12-07
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-05-07 | 2019-06-24 |  | 2019-06-18 | 2019-06-26 |  | 2019-06-05 | 2019-07-13
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-07-18 | 2019-06-12 |  | 2019-07-11 | 2019-07-10 |  | 2019-07-16 | 2019-08-18
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-06-30 | 2019-06-27 |  | 2019-07-17 | 2019-07-13 |  | 2019-08-05 | 2019-08-06
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-06-11 | 2019-06-26 |  | 2019-06-28 | 2019-06-23 |  | 2019-08-27 | 2019-08-26
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-05-20 | 2019-07-21 |  | 2019-06-30 | 2019-07-13 |  | 2019-08-18 | 2019-09-22
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-07-02 | 2019-08-01 |  | 2019-05-18 | 2019-08-21 |  | 2019-10-01 | 2019-08-27
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-05-04 | 2019-07-03 |  | 2019-06-26 | 2019-06-29 |  | 2019-12-23 | 2020-01-23
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-07-11 | 2019-08-27 |  | 2019-06-03 | 2019-08-24 |  | 2019-07-22 | 2019-08-07
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-06-11 | 2019-08-16 |  | 2019-07-05 | 2019-08-27 |  | 2019-06-13 | 2019-08-07
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-07-08 | 2019-07-29 |  | 2019-07-15 | 2019-06-24 |  | 2019-11-08 | 2019-10-26
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-05-23 | 2019-06-25 |  | 2019-05-28 | 2019-08-16 |  | 2019-12-03 | 2019-12-04
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-07-07 | 2019-06-25 |  | 2019-06-19 | 2019-09-01 |  | 2019-11-04 | 2019-11-10
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-06-10 | 2019-08-12 |  | 2019-05-02 | 2019-06-28 |  | 2019-07-29 | 2019-08-30
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-05-11 | 2019-07-30 |  | 2019-06-06 | 2019-08-04 |  | 2019-06-19 | 2019-07-06
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-06-01 | 2019-07-19 |  | 2019-05-20 | 2019-06-13 |  | 2019-06-26 | 2019-06-18
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-06-28 | 2019-08-02 |  | 2019-06-13 | 2019-08-08 |  | 2019-11-01 | 2019-11-18
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-06-05 | 2019-07-27 |  | 2019-07-14 | 2019-07-06 |  | 2019-11-21 | 2019-12-22
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-06-19 | 2019-07-11 |  | 2019-05-15 | 2019-07-29 |  | 2019-06-15 | 2019-06-19
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-05-07 | 2019-06-22 |  | 2019-04-28 | 2019-07-17 |  | 2019-06-12 | 2019-07-19
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-04-20 | 2019-07-29 |  | 2019-05-23 | 2019-07-11 |  | 2019-12-18 | 2019-11-29
2019-08-01 | MI08A-BW-6A | [24 empty] | 2019-07-18 | 2019-07-15 |  | 2019-07-26 | 2019-07-30 |  | 2019-07-24 | 2019-06-16
2019-08-01 | MI08B-BW-6A | [24 empty] | 2019-07-13 | 2019-08-24 |  | 2019-05-24 | 2019-08-26 |  | 2019-09-13 | 2019-08-19
2019-08-01 | MI08B-BW-6A | [24 empty] | 2019-05-04 | 2019-08-15 |  | 2019-05-02 | 2019-09-06 |  | 2019-09-06 | 2019-08-09
2019-08-01 | MI11A-BW-6A | [30 empty] | 2019-08-23 | 2019-08-15
2019-08-01 | MI16A-BW-6A | 2019-05-25 |  | 2019-05-08 | 2019-04-27 |  | 2019-04-21 | 2019-06-12 |  | 2019-05-27 | 2019-06-14 |  | 2019-05-07 | 2019-07-04 | 2019-08-21 |  | 2019-05-11 | 2019-06-25 | [7 empty] | 2019-07-24 | 2019-07-30 |  | 2019-07-28 | 2019-08-16 |  | 2019-11-24 | 2019-11-20
2019-08-01 | MI16B-BW-6A | 2019-05-01 |  | 2019-04-07 | 2019-03-24 |  | 2019-05-28 | 2019-03-26 |  | 2019-04-27 | 2019-03-31 |  | 2019-05-07 | 2019-06-26 | 2019-08-05 |  | 2019-07-24 | 2019-08-08 | [7 empty] | 2019-07-07 | 2019-07-13 |  | 2019-07-28 | 2019-06-29 |  | 2019-10-29 | 2019-10-31
2019-08-01 | MI17A-BW-6A | 2019-04-16 |  | 2019-04-08 | 2019-06-01 |  | 2019-04-19 | 2019-03-24 |  | 2019-04-29 | 2019-05-15 |  | 2019-06-13 | 2019-05-01 | 2019-06-20 |  | 2019-07-15 | 2019-07-12 | [7 empty] | 2019-06-14 | 2019-07-01 |  | 2019-06-05 | 2019-06-29 |  | 2019-06-12 | 2019-05-17
2019-08-01 | MI17B-BW-6A | 2019-03-31 |  | 2019-04-29 | 2019-05-29 |  | 2019-03-27 | 2019-05-26 |  | 2019-03-18 | 2019-05-14 |  | 2019-04-09 | 2019-05-13 | 2019-08-07 |  | 2019-05-14 | 2019-06-22 | [7 empty] | 2019-07-11 | 2019-07-16 |  | 2019-08-17 | 2019-08-09 |  | 2019-10-25 | 2019-10-13
2019-08-01 | MI18A-BW-6A | [30 empty] | 2019-08-13 | 2019-10-12
2019-08-01 | MI18A-BW-6A | [30 empty] | 2019-11-22 | 2019-11-21
2019-08-01 | MI18B-BW-6A | 2019-05-20 |  | 2019-06-01 | 2019-04-08 |  | 2019-06-12 | 2019-04-19 |  | 2019-03-17 | 2019-04-06 |  | 2019-04-27 | 2019-04-30 | 2019-07-12 |  | 2019-07-09 | 2019-06-16 | [7 empty] | 2019-05-27 | 2019-06-06 |  | 2019-07-18 | 2019-08-31 |  | 2019-08-05 | 2019-07-03
2019-08-01 | MI19A-BW-6A | 2019-05-17 |  |  | 2019-04-17 |  |  | 2019-04-11 |  |  | 2019-04-23 |  |  | 2019-05-15 |  |  | 2019-07-21 | [8 empty] | 2019-08-10 |  |  | 2019-07-06 |  |  | 2019-08-17 | 2019-08-27
2019-08-01 | MI19B-BW-6A | 2019-06-04 |  | 2019-06-06 | 2019-04-14 |  | 2019-05-27 | 2019-04-25 |  | 2019-05-28 | 2019-06-19 |  | 2019-04-27 | 2019-05-04 | 2019-07-17 |  | 2019-05-04 | 2019-06-26 | [7 empty] | 2019-07-15 | 2019-08-02 |  | 2019-05-31 | 2019-06-26 |  | 2019-12-28 | 2019-12-18
2019-08-01 | MI20A-BW-6A | 2019-03-14 |  | 2019-04-23 | 2019-03-21 |  | 2019-05-24 | 2019-04-29 |  | 2019-03-21 | 2019-04-08 |  | 2019-04-08 | 2019-05-17 | 2019-08-18 |  | 2019-07-22 | 2019-08-22 | [7 empty] | 2019-08-05 | 2019-07-18 |  | 2019-07-19 | 2019-07-03 |  | 2019-07-02 | 2019-08-01
2019-08-01 | MI20B-BW-6A | 2019-05-29 |  | 2019-03-24 | 2019-06-04 |  | 2019-05-12 | 2019-05-12 |  | 2019-05-16 | 2019-05-08 |  | 2019-05-26 | 2019-05-20 | 2019-07-30 |  | 2019-05-21 | 2019-07-02 | [7 empty] | 2019-07-06 | 2019-06-17 |  | 2019-07-20 | 2019-06-18 |  | 2019-07-22 | 2019-08-27
2019-08-01 | MI21A-BW-6A | 2019-04-15 |  | 2019-05-11 | 2019-06-07 |  | 2019-05-26 | 2019-05-24 |  | 2019-05-23 | 2019-06-07 |  | 2019-05-22 | 2019-05-02 | 2019-07-27 |  | 2019-06-25 | 2019-06-14 | [7 empty] | 2019-06-20 | 2019-06-05 |  | 2019-06-22 | 2019-08-27 |  | 2019-08-02 | 2019-08-07
2019-08-01 | MI21B-BW-6A | 2019-04-02 |  | 2019-06-01 | 2019-03-26 |  | 2019-04-08 | 2019-05-30 |  | 2019-05-15 | 2019-04-11 |  | 2019-05-24 | 2019-05-28 | 2019-08-16 |  | 2019-05-03 | 2019-06-02 | [7 empty] | 2019-07-05 | 2019-06-20 |  | 2019-06-04 | 2019-07-12 |  | 2019-12-08 | 2019-12-24
2019-08-01 | MI23A-BW-6A | 2019-05-18 |  |  | 2019-03-30 |  |  | 2019-05-03 |  |  | 2019-06-28 |  |  | 2019-06-13 |  |  | 2019-06-20 | [8 empty] | 2019-06-13 |  |  | 2019-06-09 |  |  | 2019-11-27 | 2019-12-25
2019-08-01 | MI23B-BW-6A | 2019-03-20 |  |  | 2019-04-16 |  |  | 2019-05-25 |  |  | 2019-04-03 |  |  | 2019-06-30 |  |  | 2019-05-03 | [8 empty] | 2019-07-03 |  |  | 2019-07-28 |  |  | 2019-09-26 | 2019-10-22
2019-08-01 | MI25A-BW-6A | 2019-04-28 |  | 2019-06-18 | 2019-04-21 |  | 2019-07-04 | 2019-07-19 | 2019-06-15 |  | 2019-06-05 | 2019-07-21 |  | 2019-06-09 | 2019-07-16 |  | 2019-06-28 | 2019-08-17 | [7 empty] | 2019-09-05 | 2019-09-07 |  | 2019-07-25 | 2019-11-10 |  | 2019-07-21 | 2019-06-22
2019-08-01 | MI25B-BW-6A | 2019-05-09 | 2019-05-21 |  | 2019-06-28 | 2019-08-13 |  | 2019-06-30 | 2019-08-29 |  | 2019-06-20 | 2019-09-17 |  | 2019-07-07 | 2019-08-16 |  | 2019-06-16 | 2019-08-16 | [7 empty] | 2019-09-05 | 2019-10-25 |  | 2019-07-20 | 2019-08-21 |  | 2019-07-02 | 2019-07-26
2019-08-01 | MI25C-BW-6A | 2019-07-27 |  |  | 2019-07-08 |  |  | 2019-08-09 |  |  | 2019-09-07 |  |  | 2019-08-21 |  |  | 2019-10-01 | [8 empty] | 2019-09-16 |  |  | 2019-10-28 |  |  | 2019-10-30 | 2019-11-21
2019-08-01 | MI26A-BW-6A | 2019-06-10 |  | 2019-05-21 | 2019-05-20 |  | 2019-05-23 | 2019-06-08 |  | 2019-05-22 | 2019-06-12 |  | 2019-07-03 | 2019-08-23 | 2019-08-22 |  | 2019-07-24 | 2019-08-16 | [7 empty] | 2019-08-08 | 2019-07-23 |  | 2019-10-02 | 2019-09-21 |  | 2019-07-25 | 2019-07-26
2019-08-01 | MI26B-BW-6A | 2019-06-02 |  | 2019-05-07 | 2019-05-16 |  | 2019-05-07 | 2019-05-28 |  | 2019-07-09 | 2019-08-10 |  | 2019-05-25 | 2019-09-01 | 2019-07-28 |  | 2019-08-03 | 2019-07-29 | [7 empty] | 2019-07-21 | 2019-07-29 |  | 2019-08-04 | 2019-08-21 |  | 2019-12-28 | 2019-12-29
2019-08-01 | MI27A-BW-6A | 2019-03-19 | 2019-05-21 |  | 2019-04-20 | 2019-07-27 |  | 2019-04-21 | 2019-06-09 |  | 2019-05-14 | 2019-09-08 |  | 2019-07-22 | 2019-07-14 |  | 2019-06-04 | 2019-08-25 | [7 empty] | 2019-09-19 | 2019-10-21 |  | 2019-08-24 | 2019-09-28 |  | 2019-06-17 | 2019-07-11
2019-08-01 | MI27B-BW-6A | 2019-04-05 | 2019-08-08 |  | 2019-06-09 | 2019-06-26 |  | 2019-06-21 | 2019-06-04 |  | 2019-05-21 | 2019-08-20 |  | 2019-08-10 | 2019-09-10 |  | 2019-07-09 | 2019-07-26 | [7 empty] | 2019-07-09 | 2019-09-13 |  | 2019-08-16 | 2019-09-27 |  | 2019-07-18 | 2019-06-22
2019-08-01 | MI35A-BW-6A | 2019-09-24 |  |  | 2019-10-31 |  |  | 2019-11-21 |  |  | 2019-11-18 |  |  | 2019-11-30 |  |  | 2019-12-23 | [8 empty] | 2019-12-26 |  |  | 2019-12-24 |  |  | 2019-10-03 | 2019-08-27
2019-08-01 | MI48A-BW-6A | [30 empty] | 2019-08-28 | 2019-09-07
2019-08-01 | MI61A-BW-6A |  | 2019-07-06 |  |  | 2019-06-23 |  |  | 2019-08-17 |  |  | 2019-09-05 |  |  | 2019-09-07 |  |  | 2019-10-26 |  |  | 2019-11-16 |  |  | 2019-11-05 |  |  | 2019-11-21 |  |  | 2019-12-14 |  | 2019-09-30 | 2019-10-18
2019-08-01 | MI62A-BW-6A |  | 2019-06-14 |  |  | 2019-07-28 |  |  | 2019-07-07 |  |  | 2019-09-08 |  |  | 2019-07-27 |  |  | 2019-08-11 |  |  | 2019-08-29 |  |  | 2019-08-15 |  |  | 2019-11-09 |  |  | 2019-11-15 |  | 2019-12-06 | 2019-11-27
2019-08-01 | LP01A-BW-6A | 2019-04-09 |  | 2019-03-20 | 2019-04-16 |  | 2019-03-06 | 2019-04-16 |  | 2019-02-07 | 2019-02-22 |  | 2019-05-04 | 2019-05-29 |  | 2019-04-04 | 2019-04-29 |  | 2019-04-13 | 2019-05-03 |  | 2019-05-17 | 2019-06-14 |  | 2019-05-11 | 2019-06-20 |  | 2019-04-20 | 2019-04-01 |  | 2019-06-03 | 2019-08-07 | 2019-08-08
2019-08-01 | LP01A-BW-6A | 2019-04-06 |  | 2019-04-16 | 2019-04-11 |  | 2019-02-25 | 2019-03-08 |  | 2019-03-23 | 2019-03-16 |  | 2019-04-19 | 2019-05-29 |  | 2019-03-26 | 2019-04-18 |  | 2019-04-09 | 2019-06-19 |  | 2019-04-22 | 2019-05-21 |  | 2019-05-18 | 2019-05-30 |  | 2019-04-30 | 2019-04-03 |  | 2019-06-22 | 2019-08-28 | 2019-07-28
2019-08-01 | LP01A-BW-6A | 2019-04-16 |  | 2019-03-06 | 2019-04-13 |  | 2019-02-22 | 2019-02-15 |  | 2019-02-12 | 2019-05-16 |  | 2019-03-11 | 2019-04-14 |  | 2019-05-05 | 2019-05-04 |  | 2019-03-14 | 2019-06-06 |  | 2019-05-23 | 2019-03-29 |  | 2019-05-17 | 2019-04-01 |  | 2019-04-21 | 2019-05-24 |  | 2019-07-02 | 2019-12-05 | 2019-12-06
2019-08-01 | LP01A-BW-6A | 2019-03-20 |  | 2019-04-12 | 2019-03-08 |  | 2019-04-19 | 2019-02-20 |  | 2019-02-17 | 2019-03-02 |  | 2019-03-17 | 2019-04-30 |  | 2019-03-14 | 2019-03-30 |  | 2019-05-15 | 2019-06-14 |  | 2019-06-13 | 2019-03-30 |  | 2019-05-22 | 2019-03-27 |  | 2019-05-14 | 2019-05-14 |  | 2019-06-01 | 2019-07-06 | 2019-06-19
2019-08-01 | LP01A-BW-6A | 2019-02-24 |  | 2019-02-22 | 2019-01-27 |  | 2019-02-01 | 2019-02-09 |  | 2019-04-08 | 2019-03-27 |  | 2019-04-02 | 2019-03-18 |  | 2019-04-08 | 2019-06-05 |  | 2019-05-27 | 2019-03-22 |  | 2019-05-16 | 2019-05-19 |  | 2019-06-12 | 2019-05-16 |  | 2019-04-08 | 2019-06-05 |  | 2019-06-01 | 2019-11-11 | 2019-11-19
2019-08-01 | LP01A-BW-6A | 2019-04-10 |  | 2019-02-08 | 2019-03-16 |  | 2019-04-10 | 2019-02-15 |  | 2019-03-29 | 2019-04-03 |  | 2019-04-13 | 2019-03-21 |  | 2019-03-09 | 2019-03-10 |  | 2019-04-09 | 2019-04-12 |  | 2019-06-02 | 2019-05-18 |  | 2019-03-28 | 2019-05-14 |  | 2019-04-01 | 2019-04-18 |  | 2019-05-03 | 2019-09-25 | 2019-09-11
2019-08-01 | LP02A-BW-6A | 2019-02-26 |  | 2019-01-30 | 2019-02-11 |  | 2019-02-13 | 2019-03-21 |  | 2019-04-25 | 2019-04-12 |  | 2019-05-07 |  |  | 2019-06-25 | 2019-06-26 |  | 2019-04-24 | 2019-06-05 |  | 2019-07-11 | 2019-06-19 |  | 2019-06-08 | 2019-06-28 |  | 2019-07-28 | 2019-06-29 |  | 2019-05-07 | 2019-11-05 | 2019-10-12
2019-08-01 | LP02A-BW-6A | 2019-02-11 |  | 2019-02-23 | 2019-02-06 |  | 2019-01-30 | 2019-02-21 |  | 2019-04-13 | 2019-05-23 |  | 2019-04-08 |  |  | 2019-05-18 | 2019-05-04 |  | 2019-07-03 | 2019-06-02 |  | 2019-06-30 | 2019-07-18 |  | 2019-07-07 | 2019-05-22 |  | 2019-06-29 | 2019-07-28 |  | 2019-06-07 | 2019-08-24 | 2019-07-24
2019-08-01 | LP02A-BW-6A | 2019-01-25 |  | 2019-04-04 | 2019-04-19 |  | 2019-02-10 | 2019-02-27 |  | 2019-02-20 | 2019-04-09 |  | 2019-05-22 |  |  | 2019-06-16 | 2019-04-14 |  | 2019-06-11 | 2019-06-14 |  | 2019-05-05 | 2019-05-20 |  | 2019-07-04 | 2019-06-28 |  | 2019-05-06 | 2019-06-22 |  | 2019-05-28 | 2019-12-18 | 2020-01-27
2019-08-01 | LP04A-BW-6A | 2019-04-08 |  | 2019-04-24 | 2019-03-12 |  | 2019-01-29 | 2019-02-11 |  | 2019-04-14 | 2019-03-27 |  | 2019-04-07 | 2019-05-26 |  | 2019-04-28 | 2019-04-13 |  | 2019-06-01 | 2019-05-20 |  | 2019-04-07 | 2019-05-27 |  | 2019-05-29 | 2019-05-12 |  | 2019-05-02 | 2019-06-08 |  | 2019-04-16 | 2019-12-18 | 2019-11-24
2019-08-01 | LP04A-BW-6A | 2019-03-24 |  | 2019-03-31 | 2019-02-25 |  | 2019-02-21 | 2019-03-16 |  | 2019-03-06 | 2019-04-03 |  | 2019-02-22 | 2019-05-13 |  | 2019-04-28 | 2019-03-24 |  | 2019-04-24 | 2019-05-16 |  | 2019-04-13 | 2019-05-05 |  | 2019-04-29 | 2019-05-25 |  | 2019-05-11 | 2019-04-23 |  | 2019-04-07 | 2019-06-02 | 2019-07-11
2019-08-01 | LP04A-BW-6A | 2019-02-24 |  | 2019-04-22 | 2019-02-26 |  | 2019-03-06 | 2019-04-04 |  | 2019-02-06 | 2019-02-25 |  | 2019-04-20 | 2019-05-11 |  | 2019-06-07 | 2019-06-07 |  | 2019-04-22 | 2019-06-19 |  | 2019-04-09 | 2019-04-14 |  | 2019-04-15 | 2019-03-30 |  | 2019-04-19 | 2019-04-18 |  | 2019-06-11 | 2019-09-28 | 2019-10-07
2019-08-01 | NT01A-BW-6A |  | 2019-07-12 |  |  | 2019-07-30 |  |  | 2019-07-20 |  |  | 2019-08-15 |  |  | 2019-10-05 |  |  | 2019-09-09 | [8 empty] | 2019-10-26 |  |  | 2019-11-14 |  | 2019-08-16 | 2019-08-14
2019-08-01 | NT01A-BW-6A |  | 2019-06-19 |  |  | 2019-08-18 |  |  | 2019-06-27 |  |  | 2019-08-24 |  |  | 2019-09-29 |  |  | 2019-09-07 | [8 empty] | 2019-09-26 |  |  | 2019-11-21 |  | 2019-11-13 | 2019-10-25
2019-08-01 | NT01A-BW-6A |  | 2019-06-15 |  |  | 2019-08-23 |  |  | 2019-06-24 |  |  | 2019-09-01 |  |  | 2019-08-22 |  |  | 2019-10-06 | [8 empty] | 2019-11-22 |  |  | 2019-11-07 |  | 2019-07-06 | 2019-07-12
2019-08-01 | NT01A-BW-6A |  | 2019-08-18 |  |  | 2019-06-07 |  |  | 2019-07-02 |  |  | 2019-10-08 |  |  | 2019-10-14 |  |  | 2019-10-23 | [8 empty] | 2019-11-24 |  |  | 2019-10-20 |  | 2019-11-10 | 2019-11-24
2019-08-01 | AX13A-EC-6A | 2018-02-22 |  | 2018-02-02 | 2018-01-31 |  | 2018-04-12 | 2018-03-09 |  | 2018-02-15 | 2018-04-29 |  | 2018-05-11 | 2018-06-16 |  | 2018-06-08 | 2018-05-11 |  | 2018-08-02 | 2018-10-24 |  | 2018-12-11 | 2019-01-31 |  | 2019-04-17 | 2019-01-10 |  | 2019-02-20 | 2019-01-31 |  | 2019-05-22 | 2019-10-01 | 2019-10-29
2019-08-01 | AX13A-EC-6A | 2018-04-12 |  | 2018-02-27 | 2018-04-05 |  | 2018-02-22 | 2018-02-05 |  | 2018-03-01 | 2018-04-20 |  | 2018-03-27 | 2018-07-28 |  | 2018-07-28 | 2018-06-30 |  | 2018-05-24 | 2019-01-12 |  | 2019-02-08 | 2019-01-06 |  | 2019-03-24 | 2019-02-22 |  | 2019-01-27 | 2018-12-19 |  | 2019-03-17 | 2019-06-26 | 2019-06-23
2019-08-01 | AX13A-EC-6A | 2018-02-04 |  | 2018-02-01 | 2018-04-07 |  | 2018-04-23 | 2018-02-21 |  | 2018-04-26 | 2018-03-19 |  | 2018-05-23 | 2018-07-18 |  | 2018-06-15 | 2018-05-14 |  | 2018-07-31 | 2019-01-01 |  | 2018-11-27 | 2018-12-22 |  | 2019-04-10 | 2019-02-24 |  | 2019-01-04 | 2019-01-25 |  | 2019-03-06 | 2019-08-06 | 2019-08-30
2019-08-01 | AX13A-EC-6A | 2018-04-13 |  | 2018-03-28 | 2018-01-27 |  | 2018-03-18 | 2018-02-20 |  | 2018-03-28 | 2018-05-22 |  | 2018-04-09 | 2018-07-09 |  | 2018-06-09 | 2018-07-02 |  | 2018-07-29 | 2018-11-05 |  | 2018-12-23 | 2019-02-22 |  | 2019-02-26 | 2019-01-09 |  | 2019-01-24 | 2019-02-19 |  | 2019-04-23 | 2019-06-06 | 2019-04-30
2019-08-01 | AX13A-EC-6A | 2018-03-27 |  | 2018-04-06 | 2018-02-15 |  | 2018-04-22 | 2018-03-24 |  | 2018-04-12 | 2018-04-24 |  | 2018-05-27 | 2018-06-15 |  | 2018-05-14 | 2018-07-23 |  | 2018-07-08 | 2018-11-15 |  | 2019-01-22 | 2019-02-24 |  | 2019-02-24 | 2019-02-20 |  | 2019-02-25 | 2019-02-08 |  | 2019-04-27 | 2019-11-06 | 2019-09-27
2019-08-01 | AX36A-EC-6A | 2019-01-26 |  | 2018-11-22 | 2018-11-03 |  | 2019-02-01 | 2018-11-04 |  | 2018-11-09 | 2019-02-22 |  | 2019-01-21 | 2019-02-25 |  | 2019-04-06 | 2019-03-29 |  | 2019-04-22 | 2019-02-20 |  | 2019-06-21 | 2019-05-02 |  | 2019-07-07 | 2019-05-20 |  | 2019-05-21 | 2019-03-14 |  | 2019-06-12 | 2019-08-22 | 2019-09-16
2019-08-01 | AX36A-EC-6A | 2019-01-14 |  | 2018-12-16 | 2019-01-23 |  | 2018-12-02 | 2019-01-05 |  | 2018-11-19 | 2019-01-31 |  | 2019-03-19 | 2019-02-05 |  | 2019-03-30 | 2019-02-18 |  | 2019-03-30 | 2019-04-12 |  | 2019-04-16 | 2019-05-10 |  | 2019-06-27 | 2019-05-26 |  | 2019-05-09 | 2019-05-30 |  | 2019-07-01 | 2019-07-19 | 2019-07-12
2019-08-01 | MI01A-EC-6A | 2019-01-08 |  | 2018-11-25 | 2018-11-30 |  | 2019-01-11 | 2019-02-18 |  | 2018-12-20 | 2019-03-07 |  | 2018-12-30 | [18 empty] | 2019-07-09 | 2019-07-15
2019-08-01 | MI01A-EC-6A | 2019-02-08 |  | 2018-12-11 | 2019-02-02 |  | 2018-11-06 | 2019-02-11 |  | 2018-12-02 | 2019-03-21 |  | 2019-02-23 | [18 empty] | 2019-08-27 | 2019-10-02
2019-08-01 | MI08A-EC-6A | [30 empty] | 2019-08-19 | 2019-09-02
2019-08-01 | MI25A-EC-6A | 2019-01-24 |  | 2018-12-30 | 2019-02-26 |  | 2019-02-05 | 2019-01-31 |  | 2019-04-12 | 2019-03-20 |  | 2019-02-16 | 2019-03-28 |  | 2019-06-01 | 2019-05-25 |  | 2019-04-15 | 2019-04-19 |  | 2019-05-26 | 2019-05-24 |  | 2019-06-14 | 2019-06-26 |  | 2019-05-13 | 2019-06-29 |  | 2019-05-06 | 2019-08-28 | 2019-07-27
2019-08-01 | MI26A-EC-6A | 2019-01-21 |  | 2019-03-13 | 2019-02-06 |  | 2019-01-04 | 2019-03-07 |  | 2019-02-11 | 2019-04-11 |  | 2019-03-01 | 2019-03-15 |  | 2019-03-29 | 2019-03-19 |  | 2019-04-21 | 2019-04-28 |  | 2019-05-19 | 2019-04-04 |  | 2019-06-25 | 2019-04-30 |  | 2019-05-30 | 2019-07-13 |  | 2019-05-05 | 2019-07-15 | 2019-07-31
2019-08-01 | MI48A-EC-6A | [30 empty] | 2019-06-27 | 2019-06-04
2019-08-01 | MI48A-EC-6A | [30 empty] | 2019-07-04 | 2019-06-13
2019-08-01 | RR01A-EC-6A | 2018-05-12 |  | 2018-06-06 | 2018-04-29 |  | 2018-05-31 | 2018-09-18 |  | 2018-08-19 | 2018-11-25 |  | 2018-10-08 | 2019-01-29 |  | 2018-12-24 | 2018-11-30 |  | 2019-03-12 | 2018-11-24 |  | 2019-04-19 | 2018-11-30 |  | 2019-03-23 | 2019-01-06 |  | 2019-05-17 | 2019-01-16 |  | 2019-03-27 | 2019-06-07 | 2019-05-26
2019-08-01 | RR01A-EC-6A | 2018-06-16 |  | 2018-05-16 | 2018-06-24 |  | 2018-04-18 | 2018-09-27 |  | 2018-08-14 | 2018-09-24 |  | 2018-11-23 | 2019-01-07 |  | 2019-03-11 | 2018-11-24 |  | 2019-02-23 | 2018-12-14 |  | 2019-04-09 | 2018-12-01 |  | 2019-03-21 | 2019-01-27 |  | 2019-05-17 | 2019-01-25 |  | 2019-04-19 | 2019-11-09 | 2019-12-19
2019-08-01 | RR01A-EC-6A | 2018-06-12 |  | 2018-05-27 | 2018-05-22 |  | 2018-04-21 | 2018-08-23 |  | 2018-09-15 | 2018-11-26 |  | 2018-09-15 | 2019-01-24 |  | 2019-03-03 | 2018-12-26 |  | 2019-02-07 | 2019-01-16 |  | 2019-03-06 | 2019-01-29 |  | 2019-05-13 | 2018-12-13 |  | 2019-05-21 | 2019-03-02 |  | 2019-06-02 | 2019-11-13 | 2019-11-09
2019-08-01 | RR20B-EC-6A | 2018-09-11 |  | 2018-10-03 | 2018-08-26 |  | 2018-08-20 | 2018-09-03 |  | 2018-10-02 | 2018-10-15 |  | 2018-11-10 | 2018-11-12 |  | 2019-02-05 | 2019-01-03 |  | 2019-02-07 | 2019-04-18 |  | 2019-03-27 | 2019-05-20 |  | 2019-05-21 | 2019-03-29 |  | 2019-06-02 | 2019-05-09 |  | 2019-04-07 | 2019-12-09 | 2020-01-05
2019-08-01 | RR20B-EC-6A | 2018-08-31 |  | 2018-10-14 | 2018-10-09 |  | 2018-09-06 | 2018-07-26 |  | 2018-08-25 | 2018-09-08 |  | 2018-09-15 | 2019-01-25 |  | 2019-02-19 | 2018-11-30 |  | 2019-02-02 | 2019-04-09 |  | 2019-04-09 | 2019-05-20 |  | 2019-05-07 | 2019-05-18 |  | 2019-05-12 | 2019-06-21 |  | 2019-05-13 | 2019-11-19 | 2019-12-06
2019-08-01 | LP01A-EC-6A | 2018-06-27 |  | 2018-07-09 | 2018-06-26 |  | 2018-07-10 | 2018-09-28 |  | 2018-08-12 | 2018-11-11 |  | 2018-10-29 | 2018-12-03 |  | 2018-10-06 | 2018-12-06 |  | 2018-11-25 | 2018-12-06 |  | 2019-01-17 | 2018-12-22 |  | 2019-03-08 | 2019-01-07 |  | 2019-03-02 | 2019-01-03 |  | 2019-04-08 | 2019-10-22 | 2019-11-07
2019-08-01 | LP01A-EC-6A | 2018-06-29 |  | 2018-07-10 | 2018-06-27 |  | 2018-08-01 | 2018-07-22 |  | 2018-08-19 | 2018-10-16 |  | 2018-11-08 | 2018-10-22 |  | 2018-11-08 | 2018-11-24 |  | 2018-10-31 | 2018-12-12 |  | 2018-12-08 | 2019-02-05 |  | 2019-03-19 | 2018-12-07 |  | 2019-01-23 | 2019-02-18 |  | 2019-04-19 | 2019-09-24 | 2019-10-11
2019-08-01 | LP01A-EC-6A | 2018-06-04 |  | 2018-07-17 | 2018-07-28 |  | 2018-07-23 | 2018-09-17 |  | 2018-09-02 | 2018-10-13 |  | 2018-08-18 | 2018-09-28 |  | 2018-11-28 | 2018-12-09 |  | 2018-11-01 | 2018-11-24 |  | 2018-12-05 | 2018-12-24 |  | 2019-03-26 | 2019-01-25 |  | 2019-03-12 | 2018-12-11 |  | 2019-05-22 | 2019-11-12 | 2019-12-12
2019-08-01 | LP01A-EC-6A | 2018-08-16 |  | 2018-06-23 | 2018-06-03 |  | 2018-08-21 | 2018-08-28 |  | 2018-08-27 | 2018-09-27 |  | 2018-09-26 | 2018-11-06 |  | 2018-11-21 | 2019-01-17 |  | 2019-01-09 | 2018-11-24 |  | 2018-11-19 | 2019-01-17 |  | 2019-02-11 | 2019-01-15 |  | 2019-03-17 | 2018-12-28 |  | 2019-03-22 | 2019-09-22 | 2019-11-03
2019-08-01 | LP01A-EC-6A | 2018-08-07 |  | 2018-06-21 | 2018-07-19 |  | 2018-06-18 | 2018-09-04 |  | 2018-10-02 | 2018-10-23 |  | 2018-09-15 | 2018-11-17 |  | 2018-10-13 | 2018-12-25 |  | 2019-01-02 | 2019-01-22 |  | 2018-12-07 | 2019-02-20 |  | 2019-04-05 | 2019-02-10 |  | 2019-01-21 | 2019-03-02 |  | 2019-03-24 | 2019-11-02 | 2019-10-15
2019-08-01 | LP01A-EC-6A | 2018-08-05 |  | 2018-07-17 | 2018-06-10 |  | 2018-07-11 | 2018-10-11 |  | 2018-08-18 | 2018-11-08 |  | 2018-09-19 | 2018-12-05 |  | 2018-10-20 | 2019-01-14 |  | 2018-11-19 | 2019-01-01 |  | 2019-01-22 | 2019-02-20 |  | 2019-04-08 | 2019-01-23 |  | 2019-03-08 | 2018-12-19 |  | 2019-04-22 | 2019-11-17 | 2019-12-22
2019-08-01 | LP01A-EC-6A | 2018-07-12 |  | 2018-08-16 | 2018-06-11 |  | 2018-07-30 | 2018-08-19 |  | 2018-10-05 | 2018-10-02 |  | 2018-10-21 | 2018-10-03 |  | 2018-10-20 | 2018-11-08 |  | 2018-10-20 | 2018-12-13 |  | 2019-02-02 | 2019-02-03 |  | 2019-03-22 | 2019-02-01 |  | 2019-02-07 | 2018-12-18 |  | 2019-05-18 | 2019-08-02 | 2019-07-02
2019-08-01 | LP01A-EC-6A | 2018-05-21 |  | 2018-06-29 | 2018-07-18 |  | 2018-08-03 | 2018-07-24 |  | 2018-08-03 | 2018-10-17 |  | 2018-08-14 | 2018-11-29 |  | 2018-10-19 | 2018-11-27 |  | 2018-11-22 | 2018-11-21 |  | 2018-12-17 | 2019-01-16 |  | 2019-03-12 | 2018-12-12 |  | 2019-01-07 | 2019-01-14 |  | 2019-04-05 | 2019-10-18 | 2019-09-12
2019-08-01 | LP01A-EC-6A | 2018-07-04 |  | 2018-05-30 | 2018-06-03 |  | 2018-07-27 | 2018-09-29 |  | 2018-08-11 | 2018-09-12 |  | 2018-09-16 | 2018-11-17 |  | 2018-12-18 | 2018-12-04 |  | 2018-11-28 | 2018-12-16 |  | 2018-12-25 | 2019-02-04 |  | 2019-03-16 | 2019-01-23 |  | 2019-03-16 | 2019-02-17 |  | 2019-03-09 | 2019-10-02 | 2019-10-19
2019-08-01 | LP01A-EC-6A | 2018-05-22 |  | 2018-06-26 | 2018-06-29 |  | 2018-06-07 | 2018-09-18 |  | 2018-09-15 | 2018-09-22 |  | 2018-08-28 | 2018-12-08 |  | 2018-10-11 | 2019-01-05 |  | 2018-11-29 | 2018-11-02 |  | 2019-01-03 | 2019-02-14 |  | 2019-05-09 | 2019-01-12 |  | 2019-01-16 | 2019-01-16 |  | 2019-05-13 | 2019-10-09 | 2019-09-21
2019-08-01 | LP01A-EC-6A | 2018-08-14 |  | 2018-07-07 | 2018-08-13 |  | 2018-06-18 | 2018-09-19 |  | 2018-09-12 | 2018-10-11 |  | 2018-09-05 | 2018-12-18 |  | 2018-11-25 | 2018-12-01 |  | 2018-12-06 | 2018-10-26 |  | 2018-12-07 | 2019-02-12 |  | 2019-04-04 | 2019-02-16 |  | 2019-01-23 | 2019-01-08 |  | 2019-04-13 | 2019-12-13 | 2020-01-09
2019-08-01 | LP01A-EC-6A | 2018-07-30 |  | 2018-07-15 | 2018-06-04 |  | 2018-07-20 | 2018-07-24 |  | 2018-08-24 | 2018-09-22 |  | 2018-08-21 | 2018-12-22 |  | 2018-12-20 | 2018-12-15 |  | 2018-12-30 | 2018-11-30 |  | 2018-12-08 | 2018-12-14 |  | 2019-02-17 | 2019-01-12 |  | 2019-02-23 | 2019-01-04 |  | 2019-03-26 | 2019-08-10 | 2019-09-11
2019-08-01 | LP02A-EC-6A | 2018-08-05 |  | 2018-08-09 | 2018-07-20 |  | 2018-07-19 | 2018-08-05 |  | 2018-10-25 | 2018-10-20 |  | 2018-09-15 | 2018-11-28 |  | 2019-01-01 | 2019-01-19 |  | 2018-12-14 | 2019-01-15 |  | 2018-11-30 | 2019-01-05 |  | 2018-12-20 | 2019-03-02 |  | 2019-02-08 | 2019-03-15 |  | 2019-02-18 | 2019-06-15 | 2019-05-18
2019-08-01 | LP02A-EC-6A | 2018-06-24 |  | 2018-07-26 | 2018-06-25 |  | 2018-08-01 | 2018-09-29 |  | 2018-09-17 | 2018-10-06 |  | 2018-09-16 | 2018-12-24 |  | 2018-11-30 | 2018-11-14 |  | 2018-12-31 | 2019-01-13 |  | 2019-01-10 | 2018-12-03 |  | 2019-02-17 | 2019-03-08 |  | 2019-01-29 | 2019-01-09 |  | 2019-02-03 | 2019-08-27 | 2019-07-22
2019-08-01 | LP02A-EC-6A | 2018-06-06 |  | 2018-05-24 | 2018-07-14 |  | 2018-06-21 | 2018-08-23 |  | 2018-08-06 | 2018-11-05 |  | 2018-09-17 | 2018-12-01 |  | 2018-11-29 | 2018-11-17 |  | 2019-01-25 | 2018-12-17 |  | 2019-01-24 | 2019-01-05 |  | 2019-02-06 | 2019-01-20 |  | 2019-03-11 | 2018-12-31 |  | 2019-02-01 | 2019-08-04 | 2019-09-01
2019-08-01 | LP02A-EC-6A | 2018-05-24 |  | 2018-07-16 | 2018-07-11 |  | 2018-06-22 | 2018-09-14 |  | 2018-10-05 | 2018-09-16 |  | 2018-09-19 | 2018-12-19 |  | 2018-12-20 | 2018-11-10 |  | 2018-11-14 | 2018-11-16 |  | 2019-01-06 | 2019-02-08 |  | 2019-01-01 | 2019-01-05 |  | 2019-01-27 | 2019-01-27 |  | 2019-03-09 | 2019-06-26 | 2019-05-21
2019-08-01 | LP02A-EC-6A | 2018-08-12 |  | 2018-07-21 | 2018-06-11 |  | 2018-08-15 | 2018-08-03 |  | 2018-08-21 | 2018-12-07 |  | 2018-10-27 | 2019-01-09 |  | 2018-12-11 | 2019-01-12 |  | 2019-01-15 | 2018-12-17 |  | 2019-01-25 | 2019-01-10 |  | 2019-02-04 | 2019-03-05 |  | 2019-03-03 | 2019-03-06 |  | 2019-02-10 | 2019-06-10 | 2019-05-14
2019-08-01 | LP02A-EC-6A | 2018-06-21 |  | 2018-05-24 | 2018-07-15 |  | 2018-06-12 | 2018-10-21 |  | 2018-08-30 | 2018-10-10 |  | 2018-09-16 | 2018-11-27 |  | 2018-12-16 | 2018-11-04 |  | 2019-01-10 | 2018-11-17 |  | 2018-11-19 | 2018-12-09 |  | 2019-01-04 | 2019-02-19 |  | 2019-03-11 | 2019-02-13 |  | 2019-02-01 | 2019-08-06 | 2019-06-28
2019-08-01 | LP02A-EC-6A | 2018-06-10 |  | 2018-08-18 | 2018-06-14 |  | 2018-08-03 | 2018-08-17 |  | 2018-08-30 | 2018-11-15 |  | 2018-11-26 | 2019-01-30 |  | 2019-01-20 | 2018-11-28 |  | 2018-11-14 | 2018-12-31 |  | 2019-01-21 | 2019-02-04 |  | 2018-12-05 | 2018-12-18 |  | 2019-01-30 | 2019-03-03 |  | 2019-02-14 | 2019-09-23 | 2019-10-06
2019-08-01 | LP06A-EC-6A | 2018-11-08 |  | 2018-12-20 | 2018-10-19 |  | 2018-11-07 | 2018-10-12 |  | 2018-10-27 | 2019-01-13 |  | 2019-02-02 | 2018-12-24 |  | 2019-02-10 | 2019-02-09 |  | 2019-02-14 | 2019-01-06 |  | 2019-07-03 | 2019-02-11 |  | 2019-05-06 | 2019-02-19 |  | 2019-05-12 | 2019-03-06 |  | 2019-07-04 | 2019-07-10 | 2019-08-19
2019-08-01 | LP06A-EC-6A | 2018-11-22 |  | 2018-10-11 | 2018-11-21 |  | 2018-12-21 | 2018-12-05 |  | 2018-11-26 | 2018-11-16 |  | 2019-01-02 | 2018-12-22 |  | 2019-04-20 | 2019-01-22 |  | 2019-03-09 | 2019-03-26 |  | 2019-06-22 | 2019-04-06 |  | 2019-04-07 | 2019-04-16 |  | 2019-04-17 | 2019-02-14 |  | 2019-05-17 | 2019-10-23 | 2019-10-20
2019-08-01 | LP06A-EC-6A | 2018-11-24 |  | 2018-12-22 | 2019-01-01 |  | 2018-10-23 | 2018-10-18 |  | 2018-12-22 | 2019-01-30 |  | 2019-01-08 | 2019-02-21 |  | 2019-03-28 | 2019-02-01 |  | 2019-02-22 | 2019-01-27 |  | 2019-04-23 | 2019-03-31 |  | 2019-06-16 | 2019-01-23 |  | 2019-04-11 | 2019-04-06 |  | 2019-04-22 | 2019-08-01 | 2019-06-23
2019-08-01 | LP08A-EC-6A | 2019-06-03 |  | 2019-07-01 | 2019-05-09 |  | 2019-07-28 | 2019-07-13 |  | 2019-07-24 | 2019-06-06 | 2019-08-18 |  | 2019-09-28 | 2019-10-03 |  | 2019-09-28 | 2019-09-30 |  | 2019-07-29 | 2019-07-31 |  | 2019-09-21 | 2019-10-18 |  | 2019-08-24 | 2019-09-18 |  | 2019-10-25 | 2019-09-25 |  | 2019-07-17 | 2019-06-08
2019-08-01 | LP08A-EC-6A | 2019-06-02 |  | 2019-06-07 | 2019-07-10 |  | 2019-06-23 | 2019-07-09 |  | 2019-07-03 | 2019-07-25 | 2019-06-18 |  | 2019-09-12 | 2019-07-25 |  | 2019-07-22 | 2019-09-18 |  | 2019-09-21 | 2019-10-12 |  | 2019-10-15 | 2019-10-01 |  | 2019-08-21 | 2019-09-19 |  | 2019-11-03 | 2019-08-22 |  | 2019-06-05 | 2019-07-11
2019-08-01 | LP10A-EC-6A | 2018-12-31 |  | 2019-01-05 | 2018-12-09 |  | 2018-12-28 | 2019-01-18 |  | 2019-03-14 | 2019-03-27 |  | 2019-04-10 | 2019-05-12 |  | 2019-04-23 | 2019-05-12 |  | 2019-05-10 | 2019-04-23 | 2019-08-07 |  | 2019-03-30 | 2019-05-31 |  | 2019-05-14 |  | 2019-05-09 | 2019-05-25 | 2019-07-21 |  | 2019-12-28 | 2019-12-17
2019-08-01 | LP10A-EC-6A | 2019-01-26 |  | 2019-01-28 | 2019-01-06 |  | 2019-02-08 | 2018-12-30 |  | 2019-01-03 | 2019-03-19 |  | 2019-04-20 | 2019-05-11 |  | 2019-05-06 | 2019-04-03 |  | 2019-06-03 | 2019-05-07 | 2019-05-19 |  | 2019-05-13 | 2019-05-26 |  | 2019-05-05 |  | 2019-06-18 | 2019-06-02 | 2019-06-06 |  | 2019-06-19 | 2019-07-12
2019-08-01 | LP11A-EC-6A | 2019-01-15 |  | 2018-12-10 | 2019-02-21 |  | 2019-03-11 | 2019-01-10 |  | 2019-03-05 | 2019-04-01 |  | 2019-04-24 | 2019-06-01 |  | 2019-06-29 | 2019-04-18 |  | 2019-06-03 | 2019-07-06 |  | 2019-07-10 | 2019-07-06 |  | 2019-07-09 | 2019-06-08 |  | 2019-05-05 | 2019-05-21 |  | 2019-05-04 | 2019-06-27 | 2019-06-30
2019-08-01 | LP12A-EC-6A |  |  | 2019-03-20 |  |  | 2019-03-20 |  |  | 2019-02-17 |  |  | 2019-02-26 |  |  | 2019-04-27 |  |  | 2019-05-09 |  |  | 2019-05-11 |  |  | 2019-04-05 |  |  | 2019-06-24 |  |  | 2019-05-18 | 2019-10-15 | 2019-09-09
2019-08-01 | LP12A-EC-6A |  |  | 2019-03-04 |  |  | 2019-03-13 |  |  | 2019-02-21 |  |  | 2019-02-03 |  |  | 2019-04-15 |  |  | 2019-04-06 |  |  | 2019-05-14 |  |  | 2019-06-16 |  |  | 2019-05-12 |  |  | 2019-05-31 | 2019-11-22 | 2019-12-27
2019-08-01 | LP32A-EC-6A | 2019-06-03 |  | 2019-04-25 | 2019-06-05 |  | 2019-07-18 | 2019-07-29 |  | 2019-07-23 | 2019-07-15 | 2019-07-31 |  | 2019-10-01 | 2019-07-17 |  | 2019-09-08 | 2019-08-27 |  | 2019-08-29 | 2019-10-18 |  | 2019-09-20 | 2019-08-06 |  | 2019-08-12 | 2019-09-02 |  | 2019-10-02 | 2019-09-24 |  | 2019-10-10 | 2019-09-23
2019-08-01 | LP32A-EC-6A | 2019-05-22 |  | 2019-05-01 | 2019-07-19 |  | 2019-05-20 | 2019-06-24 |  | 2019-07-08 | 2019-08-24 | 2019-06-04 |  | 2019-10-03 | 2019-08-28 |  | 2019-08-30 | 2019-09-04 |  | 2019-08-19 | 2019-08-30 |  | 2019-08-19 | 2019-09-04 |  | 2019-08-22 | 2019-09-20 |  | 2019-08-26 | 2019-08-10 |  | 2019-07-21 | 2019-07-26
2019-08-01 | LP34A-EC-6A | 2019-08-05 | 2019-05-31 |  | 2019-05-21 | 2019-05-31 |  | 2019-08-05 | 2019-07-06 |  | 2019-07-14 | 2019-07-26 |  | 2019-08-23 | 2019-10-12 |  | 2019-10-27 | 2019-08-18 |  | 2019-10-22 | 2019-10-28 |  | 2019-11-11 | 2019-11-05 |  | 2019-11-02 | 2019-11-04 |  | 2019-10-31 | 2019-11-22 |  | 2019-12-12 | 2019-12-30
2019-08-01 | LP35A-EC-6A | 2019-04-26 |  | 2019-07-16 | 2019-06-26 |  | 2019-05-05 | 2019-07-24 |  | 2019-05-25 | 2019-08-21 | 2019-07-09 |  | 2019-09-27 | 2019-07-24 |  | 2019-08-31 | 2019-08-23 |  | 2019-10-08 | 2019-10-05 |  | 2019-07-24 | 2019-09-17 |  | 2019-10-22 | 2019-10-23 |  | 2019-11-02 | 2019-10-13 |  | 2019-06-15 | 2019-07-01
2019-08-01 | LP48A-EC-6A | 2019-05-21 |  | 2019-05-21 | 2019-07-13 |  | 2019-06-05 | 2019-04-30 |  | 2019-05-11 | 2019-08-20 | 2019-08-05 |  | 2019-08-30 | 2019-10-17 |  | 2019-10-09 | 2019-10-19 |  | 2019-09-25 | 2019-08-12 |  | 2019-10-13 | 2019-08-31 |  | 2019-09-29 | 2019-10-01 |  | 2019-10-04 | 2019-09-18 |  | 2019-06-17 | 2019-06-21
2019-08-01 | LP48A-EC-6A | 2019-06-06 |  | 2019-05-24 | 2019-06-03 |  | 2019-05-07 | 2019-06-05 |  | 2019-07-13 | 2019-08-18 | 2019-07-12 |  | 2019-09-14 | 2019-10-20 |  | 2019-10-28 | 2019-09-16 |  | 2019-09-06 | 2019-08-28 |  | 2019-09-24 | 2019-11-02 |  | 2019-09-15 | 2019-10-11 |  | 2019-11-07 | 2019-08-30 |  | 2019-07-06 | 2019-07-16
2019-08-01 | LP49A-EC-6A | 2019-04-30 |  | 2019-07-02 | 2019-07-16 | 2019-05-15 |  | 2019-07-16 | 2019-07-08 |  | 2019-06-28 | 2019-07-15 |  | 2019-10-17 | 2019-10-15 |  | 2019-08-31 | 2019-09-29 |  | 2019-09-24 | 2019-11-24 |  | 2019-08-19 | 2019-09-13 |  | 2019-09-29 | 2019-11-13 |  | 2019-09-16 | 2019-09-30 |  | 2019-06-07 | 2019-06-04
2019-08-01 | LP49A-EC-6A | 2019-05-04 |  | 2019-06-19 | 2019-04-24 | 2019-06-22 |  | 2019-04-27 | 2019-05-30 |  | 2019-07-15 | 2019-09-18 |  | 2019-10-20 | 2019-09-13 |  | 2019-09-25 | 2019-10-20 |  | 2019-10-14 | 2019-10-04 |  | 2019-10-25 | 2019-12-01 |  | 2019-08-27 | 2019-09-20 |  | 2019-11-02 | 2019-11-27 |  | 2019-08-09 | 2019-08-01
2019-08-01 | LP51A-EC-6A | 2019-08-16 | 2019-05-25 |  | 2019-10-10 | 2019-07-13 |  | 2019-09-23 | 2019-08-14 |  | 2019-11-08 | 2019-08-18 |  | 2020-01-02 | 2019-10-11 |  | 2020-01-06 | 2019-11-02 |  | 2020-02-28 | 2019-10-26 |  | 2020-02-22 | 2019-11-28 |  | 2020-03-16 | 2020-01-17 |  | 2020-03-01 | 2019-11-29 |  | 2019-11-08 | 2019-10-04
2019-08-01 | LP62A-EC-6A | 2019-01-02 |  | 2019-02-05 | 2019-03-02 |  | 2019-03-08 | 2019-01-15 |  | 2019-01-28 | 2019-02-17 |  | 2019-04-01 | 2019-03-29 |  | 2019-06-20 | 2019-04-15 |  | 2019-05-10 | 2019-04-13 |  | 2019-06-10 | 2019-04-03 |  | 2019-06-07 | 2019-05-25 |  | 2019-06-22 | 2019-05-24 |  | 2019-07-09 | 2019-06-30 | 2019-06-11
2019-08-01 | LP65A-EC-6A | 2019-04-15 |  | 2019-03-11 | 2019-03-17 |  | 2019-04-26 | 2019-05-06 |  | 2019-06-09 | 2019-05-24 |  | 2019-07-08 | 2019-05-29 | 2019-06-27 |  | 2019-08-05 | 2019-08-08 |  | 2019-08-20 | 2019-06-10 |  | 2019-06-18 | 2019-07-24 |  | 2019-08-25 | 2019-08-21 |  | 2019-07-08 | 2019-08-23 |  | 2019-09-04 | 2019-08-12
2019-08-01 | LP66A-EC-6A | 2019-08-21 | 2019-06-18 |  | 2019-09-13 | 2019-08-23 |  | 2019-09-06 | 2019-08-18 |  | 2019-09-07 | 2019-10-26 |  | 2019-12-21 | 2019-12-15 |  | 2019-10-03 | 2019-12-19 |  | 2019-10-21 | 2019-12-26 |  | 2019-10-31 | 2019-10-18 |  | 2019-12-23 | 2019-10-25 |  | 2019-11-05 | 2019-11-25 |  | 2019-12-02 | 2020-01-10
2019-08-01 | LP66A-EC-6A | 2019-09-01 | 2019-09-04 |  | 2019-09-01 | 2019-06-26 |  | 2019-07-18 | 2019-08-24 |  | 2019-08-31 | 2019-08-04 |  | 2019-11-15 | 2019-10-15 |  | 2019-10-29 | 2019-10-28 |  | 2019-10-15 | 2019-11-03 |  | 2019-12-06 | 2019-10-23 |  | 2019-12-13 | 2019-10-28 |  | 2019-12-09 | 2019-10-31 |  | 2019-11-11 | 2019-10-16
2019-08-01 | AL88A-PL-6A | 2018-03-07 |  | 2018-03-27 | 2018-03-13 |  | 2018-04-26 | 2018-02-28 |  | 2018-04-13 | 2018-06-03 |  | 2018-05-13 | 2018-09-17 |  | 2018-11-23 | 2019-01-17 |  | 2019-01-21 | 2019-01-14 |  | 2019-01-24 | 2019-01-07 |  | 2019-03-28 | 2019-02-15 | 2019-07-23 |  | 2019-01-18 | 2019-08-06 |  | 2019-08-22 | 2019-09-22
2019-08-01 | NT01A-PL-6A | 2018-03-25 |  | 2018-03-18 | 2018-04-14 |  | 2018-03-15 | 2018-04-30 |  | 2018-03-21 | 2018-06-28 |  | 2018-08-06 | 2018-09-24 |  | 2018-11-07 | 2018-10-31 |  | 2018-11-28 | 2018-09-22 |  | 2018-11-28 | 2018-12-03 |  | 2019-01-16 | 2019-03-04 |  | 2018-12-12 | 2019-01-24 |  | 2019-03-06 | 2019-09-09 | 2019-10-15
2019-08-01 | NT01A-PL-6A | 2018-03-06 |  | 2018-03-30 | 2018-05-23 |  | 2018-03-15 | 2018-03-08 |  | 2018-03-14 | 2018-06-01 |  | 2018-07-16 | 2018-10-29 |  | 2018-09-26 | 2018-11-17 |  | 2018-09-29 | 2018-10-05 |  | 2018-11-28 | 2018-12-13 |  | 2019-02-02 | 2019-02-12 |  | 2019-02-28 | 2019-01-29 |  | 2019-01-28 | 2019-10-03 | 2019-09-07
2019-08-01 | NT01A-PL-6A | 2018-03-16 |  | 2018-04-04 | 2018-05-02 |  | 2018-04-07 | 2018-05-26 |  | 2018-05-04 | 2018-06-21 |  | 2018-08-14 | 2018-09-23 |  | 2018-11-12 | 2018-10-06 |  | 2018-09-14 | 2018-09-28 |  | 2019-02-02 | 2019-01-04 |  | 2018-11-20 | 2019-03-10 |  | 2018-12-31 | 2019-01-01 |  | 2019-03-05 | 2019-10-03 | 2019-09-01
2019-08-01 | NT01A-PL-6A | 2018-02-26 |  | 2018-04-26 | 2018-03-31 |  | 2018-04-28 | 2018-03-25 |  | 2018-05-07 | 2018-08-13 |  | 2018-08-09 | 2018-08-29 |  | 2018-10-10 | 2018-09-18 |  | 2018-10-22 | 2018-09-29 |  | 2018-11-17 | 2018-12-31 |  | 2018-12-10 | 2019-02-21 |  | 2019-02-23 | 2019-01-20 |  | 2019-02-06 | 2019-11-07 | 2019-11-14
2019-08-01 | AX26A-IN-6A | 2018-01-24 |  | 2017-11-14 | 2017-12-27 |  | 2017-11-25 | 2017-12-29 |  | 2018-02-13 | 2018-04-01 |  | 2018-04-10 | 2018-04-26 |  | 2018-04-09 | 2018-04-25 |  | 2018-03-05 | 2018-05-31 |  | 2018-05-04 | 2018-04-13 |  | 2018-04-16 | 2018-06-28 |  | 2018-05-01 | 2018-07-21 |  | 2018-08-27 | 2019-06-16 | 2019-06-09
2019-08-01 | LP01A-IN-6A | 2017-11-30 |  | 2018-01-18 | 2018-02-02 |  | 2018-02-03 | 2018-02-02 |  | 2018-01-14 | 2018-03-09 |  | 2018-01-22 | 2018-04-28 |  | 2018-03-11 | 2018-05-31 |  | 2018-03-27 | 2018-06-04 |  | 2018-06-15 | 2018-04-01 |  | 2018-05-22 | 2018-06-28 |  | 2018-04-21 | 2018-05-09 |  | 2018-05-25 | 2019-12-24 | 2019-11-23
2019-08-01 | LP02A-IN-6A | 2018-02-12 |  | 2018-01-08 | 2017-12-25 |  | 2017-12-31 | 2018-01-09 |  | 2017-12-16 | 2018-04-03 |  | 2018-03-11 | 2018-05-24 |  | 2018-06-04 | 2018-04-22 |  | 2018-04-09 | 2018-06-13 |  | 2018-05-23 | 2018-03-25 |  | 2018-05-13 | 2018-05-02 |  | 2018-03-29 | 2018-06-23 |  | 2018-06-03 | 2019-10-19 | 2019-09-16
2019-08-01 | LP10A-IN-6A | 2018-01-06 |  | 2018-01-04 | 2018-02-07 |  | 2018-02-08 | 2018-01-21 |  | 2018-03-16 | 2018-05-01 |  | 2018-05-04 | 2018-04-14 |  | 2018-05-20 | 2018-07-06 |  | 2018-06-14 | 2018-06-26 |  | 2018-07-07 | 2018-07-17 |  | 2018-06-29 | 2018-07-06 |  | 2018-05-18 | 2018-08-14 |  | 2018-09-16 | 2019-08-29 | 2019-09-17
2019-08-01 | LP38A-IN-6A | 2018-01-15 |  | 2017-12-22 | 2018-02-13 |  | 2018-02-09 | 2018-03-07 |  | 2018-03-15 | 2018-02-05 |  | 2018-04-08 | 2018-05-03 |  | 2018-05-19 | 2018-05-09 |  | 2018-03-13 | 2018-06-06 |  | 2018-04-03 | 2018-05-07 |  | 2018-04-20 | 2018-05-17 |  | 2018-05-22 | 2018-08-29 |  | 2018-09-08 | 2019-12-08 | 2020-01-05
2019-08-01 | LP40A-IN-6A | 2018-04-23 |  | 2018-02-28 | 2018-02-22 |  | 2018-02-09 | 2018-04-01 |  | 2018-02-08 | 2018-05-13 |  | 2018-05-05 | 2018-06-17 |  | 2018-08-01 | 2018-06-30 |  | 2018-06-21 | 2018-07-24 |  | 2018-07-12 | 2018-09-23 |  | 2018-09-26 | 2018-08-15 |  | 2018-09-09 | 2018-08-31 |  | 2018-07-17 | 2019-11-05 | 2019-12-15
2019-08-01 | ZA01A-BS-6A | 2019-02-01 |  | 2019-02-11 | 2019-02-07 |  | 2019-02-16 | 2019-02-14 |  | 2019-02-16 | 2019-03-28 |  | 2019-04-02 | 2019-05-21 | 2019-05-09 |  | 2019-05-29 | 2019-05-09 |  | 2019-06-05 | 2019-05-15 |  | 2019-06-12 | 2019-05-23 |  | 2019-06-19 | 2019-05-29 |  | 2019-06-26 | 2019-06-05 |  | 2019-12-01 | 2020-01-02
2019-08-01 | ZA01B-BS-6A | 2019-02-15 |  | 2019-03-04 | 2019-02-22 |  | 2019-03-05 | 2019-03-01 |  | 2019-03-05 | 2019-04-12 |  | 2019-04-01 | 2019-06-06 | 2019-05-23 |  | 2019-06-13 | 2019-06-02 |  | 2019-06-20 | 2019-06-11 |  | 2019-06-27 | 2019-06-17 |  | 2019-07-04 | 2019-06-23 |  | 2019-07-11 | 2019-06-30 |  | 2019-07-14 | 2019-06-06
2019-08-01 | ZA04A-BS-6A | 2019-05-29 | 2019-05-31 |  | 2019-06-06 | 2019-06-06 |  | 2019-06-13 | 2019-06-12 |  | 2019-07-11 | 2019-07-11 |  | 2019-08-15 | 2019-08-16 |  | 2019-08-22 | 2019-08-22 |  | 2019-08-30 | 2019-08-28 |  | 2019-09-06 | 2019-09-06 |  | 2019-09-13 | 2019-09-11 |  | 2019-09-20 | 2019-09-19 |  | 2019-11-16 | 2019-10-19
2019-08-01 | ZA08A-BS-6A | 2019-10-23 | 2019-10-25 |  | 2019-10-31 | 2019-10-30 |  | 2019-11-07 | 2019-11-08 |  | 2019-12-05 | 2019-12-05 |  | 2020-01-17 | 2020-01-15 |  | 2020-01-24 | 2020-01-22 |  | 2020-01-31 | 2020-01-31 |  | 2020-02-07 | 2020-02-05 |  | 2020-02-14 | 2020-02-14 |  | 2020-02-21 | 2020-02-21 |  | 2019-09-18 | 2019-10-15
2019-08-01 | ZA09A-BS-6A | 2020-02-17 | 2020-02-17 |  | 2020-02-24 | 2020-02-25 |  | 2020-03-02 | 2020-03-03 |  | 2020-03-30 | 2020-03-31 |  | 2020-05-07 | 2020-05-06 |  | 2020-05-14 | 2020-05-14 |  | 2020-05-21 | 2020-05-20 |  | 2020-05-29 | 2020-05-27 |  | 2020-06-05 | 2020-06-03 |  | 2020-06-12 | 2020-06-11 |  | 2019-06-21 | 2019-06-24
2019-08-01 | ZA10A-BS-6A | 2020-03-26 | 2020-03-27 |  | 2020-04-02 | 2020-04-02 |  | 2020-04-09 | 2020-04-09 |  | 2020-05-12 | 2020-05-11 |  | 2020-06-17 | 2020-06-18 |  | 2020-06-24 | 2020-06-25 |  | 2020-07-01 | 2020-06-30 |  | 2020-07-08 | 2020-07-09 |  | 2020-07-15 | 2020-07-14 |  | 2020-07-22 | 2020-07-23 |  | 2019-11-24 | 2019-10-22
2019-08-01 | LY02A-BS-6A | 2019-02-02 |  | 2019-02-08 | 2019-02-08 |  | 2019-02-07 | 2019-02-15 |  | 2019-02-14 | 2019-03-15 |  | 2019-03-15 | 2019-04-23 | 2019-05-01 |  | 2019-04-30 | 2019-04-29 |  | 2019-05-08 | 2019-04-30 |  | 2019-05-15 | 2019-05-07 |  | 2019-05-22 | 2019-05-22 |  | 2019-05-30 | 2019-05-29 |  | 2019-08-20 | 2019-09-23
2019-08-01 | LY03A-BS-6A | 2019-01-09 |  | 2019-01-14 | 2019-01-17 |  | 2019-01-15 | 2019-01-24 |  | 2019-01-22 | 2019-03-07 |  | 2019-03-07 | 2019-04-29 | 2019-05-08 |  | 2019-05-07 | 2019-05-06 |  | 2019-05-14 | 2019-05-13 |  | 2019-05-21 | 2019-05-20 |  | 2019-05-29 | 2019-05-28 |  | 2019-06-05 | 2019-06-05 |  | 2019-10-03 | 2019-09-02
2019-08-01 | LY04A-BS-6A | 2018-11-12 |  | 2018-11-24 | 2018-11-20 |  | 2018-11-23 | 2018-11-27 |  | 2018-11-29 | 2019-01-02 |  | 2019-01-09 | 2019-02-06 |  | 2019-02-27 | 2019-02-13 |  | 2019-02-27 | 2019-02-20 |  | 2019-02-22 | 2019-04-03 | 2019-06-15 |  | 2019-04-03 | 2019-05-01 |  | 2019-04-10 | 2019-06-13 |  | 2019-09-13 | 2019-08-22
2019-08-01 | LY04B-BS-6A | 2018-11-12 |  | 2018-11-22 | 2018-11-20 |  | 2018-11-22 | 2018-11-27 |  | 2018-11-28 | 2019-01-02 |  | 2019-01-09 | 2019-02-06 |  | 2019-03-11 | 2019-02-13 |  | 2019-03-11 | 2019-02-20 |  | 2019-04-17 | 2019-02-27 | 2019-04-29 |  | 2019-03-06 |  | 2019-04-04 | 2019-03-13 | 2019-05-01 |  | 2019-08-07 | 2019-08-01
2019-08-01 | LY05A-BS-6A | 2019-10-17 | 2019-10-15 |  | 2019-10-23 | 2019-10-22 |  | 2019-10-30 | 2019-10-30 |  | 2019-12-11 | 2019-12-10 |  | 2020-02-06 | 2020-02-07 |  | 2020-02-13 | 2020-02-12 |  | 2020-02-20 | 2020-02-21 |  | 2020-02-27 | 2020-02-26 |  | 2020-03-05 | 2020-03-04 |  | 2020-03-12 | 2020-03-11 |  | 2019-11-11 | 2019-12-12
2019-08-01 | LY26A-BS-6A | 2017-12-11 |  | 2017-12-11 | 2017-12-12 |  | 2017-12-13 | 2017-12-12 |  | 2017-12-11 | 2018-02-12 |  | 2018-02-12 | 2018-04-04 |  | 2018-04-04 | 2018-04-04 |  | 2018-04-03 | 2018-04-11 |  | 2018-04-10 | 2018-05-09 |  | 2018-05-10 | 2018-04-25 |  | 2018-04-25 | 2018-06-14 |  | 2018-06-13 | 2019-09-15 | 2019-10-16
2019-08-01 | LY26A-BS-6A | 2017-12-13 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-13 | 2017-12-12 |  | 2017-12-13 | 2018-02-12 |  | 2018-02-12 | 2018-04-04 |  | 2018-04-04 | 2018-04-04 |  | 2018-04-04 | 2018-04-11 |  | 2018-04-10 | 2018-05-09 |  | 2018-05-09 | 2018-04-25 |  | 2018-04-24 | 2018-06-14 |  | 2018-06-15 | 2019-11-04 | 2019-10-11
2019-08-01 | LY26A-BS-6A | 2017-12-11 |  | 2017-12-13 | 2017-12-12 |  | 2017-12-13 | 2017-12-12 |  | 2017-12-11 | 2018-02-12 |  | 2018-02-11 | 2018-04-04 |  | 2018-04-04 | 2018-04-04 |  | 2018-04-03 | 2018-04-11 |  | 2018-04-12 | 2018-05-09 |  | 2018-05-09 | 2018-04-25 |  | 2018-04-25 | 2018-06-14 |  | 2018-06-13 | 2019-11-27 | 2019-12-23
2019-08-01 | LY26A-BS-6A | 2017-12-12 |  | 2017-12-11 | 2017-12-12 |  | 2017-12-13 | 2017-12-12 |  | 2017-12-12 | 2018-02-12 |  | 2018-02-11 | 2018-04-04 |  | 2018-04-04 | 2018-04-04 |  | 2018-04-03 | 2018-04-11 |  | 2018-04-10 | 2018-05-09 |  | 2018-05-09 | 2018-04-25 |  | 2018-04-25 | 2018-06-14 |  | 2018-06-15 | 2019-06-15 | 2019-05-28
2019-08-01 | LY26A-BS-6A | 2017-12-11 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-13 | 2017-12-12 |  | 2017-12-12 | 2018-02-12 |  | 2018-02-11 | 2018-04-04 |  | 2018-04-03 | 2018-04-04 |  | 2018-04-04 | 2018-04-11 |  | 2018-04-10 | 2018-05-09 |  | 2018-05-10 | 2018-04-25 |  | 2018-04-25 | 2018-06-14 |  | 2018-06-13 | 2019-07-06 | 2019-07-23
2019-08-01 | LY26A-BS-6A | 2017-12-13 |  | 2017-12-12 | 2017-12-12 |  | 2017-12-13 | 2017-12-12 |  | 2017-12-11 | 2018-02-12 |  | 2018-02-13 | 2018-04-04 |  | 2018-04-05 | 2018-04-04 |  | 2018-04-04 | 2018-04-11 |  | 2018-04-10 | 2018-05-09 |  | 2018-05-10 | 2018-04-25 |  | 2018-04-24 | 2018-06-14 |  | 2018-06-14 | 2019-08-21 | 2019-08-25
2019-08-01 | LY26A-BS-6A | 2017-12-13 |  | 2017-12-11 | 2017-12-12 |  | 2017-12-11 | 2017-12-12 |  | 2017-12-13 | 2018-02-12 |  | 2018-02-11 | 2018-04-04 |  | 2018-04-04 | 2018-04-04 |  | 2018-04-04 | 2018-04-11 |  | 2018-04-12 | 2018-05-09 |  | 2018-05-09 | 2018-04-25 |  | 2018-04-24 | 2018-06-14 |  | 2018-06-13 | 2019-12-02 | 2019-12-19
2019-08-01 | LY29A-BS-6A | 2018-10-03 |  | 2018-10-05 | 2018-10-08 |  | 2018-10-07 | 2018-10-10 |  | 2018-10-09 | 2018-11-12 |  | 2018-11-30 | 2019-01-22 |  | 2019-03-09 | 2019-01-21 |  | 2019-03-10 | 2019-01-28 |  | 2019-03-05 | 2019-02-04 |  | 2019-03-31 | 2019-02-11 |  | 2019-03-27 | 2019-02-18 |  | 2019-04-02 | 2019-10-02 | 2019-09-13
2019-08-01 | LY29A-BS-6A | 2018-10-05 |  | 2018-10-05 | 2018-10-08 |  | 2018-10-08 | 2018-10-10 |  | 2018-10-10 | 2018-11-12 |  | 2018-11-30 | 2019-01-22 |  | 2019-03-10 | 2019-01-21 |  | 2019-03-08 | 2019-01-28 |  | 2019-03-07 | 2019-02-04 |  | 2019-03-31 | 2019-02-11 |  | 2019-03-27 | 2019-02-18 |  | 2019-04-04 | 2019-06-14 | 2019-07-11
2019-08-01 | LY29A-BS-6A | 2018-10-03 |  | 2018-10-03 | 2018-10-08 |  | 2018-10-09 | 2018-10-10 |  | 2018-10-11 | 2018-11-12 |  | 2018-11-29 | 2019-01-22 |  | 2019-03-10 | 2019-01-21 |  | 2019-03-08 | 2019-01-28 |  | 2019-03-06 | 2019-02-04 |  | 2019-03-31 | 2019-02-11 |  | 2019-03-28 | 2019-02-18 |  | 2019-04-03 | 2019-06-21 | 2019-05-16
2019-08-01 | LY30A-BS-6A | 2019-02-19 |  | 2019-03-29 | 2019-02-25 |  | 2019-04-10 | 2019-03-04 |  | 2019-04-10 | 2019-05-01 | 2019-05-24 |  | 2019-07-05 | 2019-07-06 |  | 2019-07-12 | 2019-07-05 |  | 2019-07-19 | 2019-07-05 |  | 2019-09-02 | 2019-08-16 |  | 2019-09-02 | 2019-08-16 |  | 2019-09-09 | 2019-08-22 |  | 2019-06-06 | 2019-05-01
2019-08-01 | LY31A-BS-6A | 2019-04-25 | 2019-05-22 |  | 2019-05-01 | 2019-05-30 |  | 2019-05-09 | 2019-06-06 |  | 2019-06-21 | 2019-07-18 |  | 2019-08-09 | 2019-09-07 |  | 2019-08-16 | 2019-09-14 |  | 2019-08-23 | 2019-09-20 |  | 2019-09-02 | 2019-09-28 |  | 2019-09-09 | 2019-10-05 |  | 2019-09-16 | 2019-10-12 |  | 2019-06-17 | 2019-05-10
2019-08-01 | LY32A-BS-6A | 2019-01-20 |  | 2019-03-27 | 2019-01-28 |  | 2019-03-27 | 2019-02-04 |  | 2019-03-29 | 2019-03-18 | 2019-05-08 |  | 2019-05-09 | 2019-06-27 |  | 2019-05-16 | 2019-07-03 |  | 2019-05-23 | 2019-07-10 |  | 2019-05-31 | 2019-07-16 |  | 2019-06-07 | 2019-07-25 |  | 2019-06-14 | 2019-08-01 |  | 2019-11-21 | 2019-11-15
2019-08-01 | LY33A-BS-6A | 2018-12-04 |  | 2019-01-23 | 2018-12-10 |  | 2019-01-24 | 2018-12-13 |  | 2019-01-28 | 2019-01-29 |  | 2019-02-22 | 2019-03-07 | 2019-05-08 |  | 2019-03-26 | 2019-05-09 |  | 2019-04-02 | 2019-05-16 |  | 2019-04-09 | 2019-05-23 |  | 2019-04-11 | 2019-05-17 |  | 2019-04-16 | 2019-05-24 |  | 2019-11-03 | 2019-12-01
2019-08-01 | LY33A-BS-6A | 2018-12-06 |  | 2019-01-23 | 2018-12-10 |  | 2019-01-23 | 2018-12-13 |  | 2019-01-29 | 2019-01-29 |  | 2019-02-23 | 2019-03-07 | 2019-05-09 |  | 2019-03-26 | 2019-05-08 |  | 2019-04-02 | 2019-05-16 |  | 2019-04-09 | 2019-05-22 |  | 2019-04-11 | 2019-05-16 |  | 2019-04-16 | 2019-05-23 |  | 2019-12-06 | 2019-12-04
2019-08-01 | LY33A-BS-6A | 2018-12-05 |  | 2019-01-23 | 2018-12-10 |  | 2019-01-25 | 2018-12-13 |  | 2019-01-27 | 2019-01-29 |  | 2019-02-22 | 2019-03-07 | 2019-05-08 |  | 2019-03-26 | 2019-05-09 |  | 2019-04-02 | 2019-05-15 |  | 2019-04-09 | 2019-05-22 |  | 2019-04-11 | 2019-05-16 |  | 2019-04-16 | 2019-05-23 |  | 2019-06-20 | 2019-06-03
2019-08-01 | LY33B-BS-6A | 2018-11-22 |  | 2018-12-20 | 2018-11-26 |  | 2018-12-25 | 2018-11-27 |  | 2018-12-24 | 2019-01-15 |  | 2019-01-29 | 2019-03-07 | 2019-04-28 |  | 2019-03-12 | 2019-04-28 |  | 2019-03-19 | 2019-05-06 |  | 2019-03-26 | 2019-05-15 |  | 2019-03-28 | 2019-05-06 |  | 2019-04-01 | 2019-05-13 |  | 2019-09-16 | 2019-10-16
2019-08-01 | LY33B-BS-6A | 2018-11-20 |  | 2018-12-21 | 2018-11-26 |  | 2018-12-23 | 2018-11-27 |  | 2018-12-25 | 2019-01-15 |  | 2019-01-28 | 2019-03-07 | 2019-04-29 |  | 2019-03-12 | 2019-04-28 |  | 2019-03-19 | 2019-05-07 |  | 2019-03-26 | 2019-05-13 |  | 2019-03-28 | 2019-05-07 |  | 2019-04-01 | 2019-05-13 |  | 2019-06-16 | 2019-06-21
2019-08-01 | LY33B-BS-6A | 2018-11-21 |  | 2018-12-22 | 2018-11-26 |  | 2018-12-24 | 2018-11-27 |  | 2018-12-25 | 2019-01-15 |  | 2019-01-28 | 2019-03-07 | 2019-04-29 |  | 2019-03-12 | 2019-04-28 |  | 2019-03-19 | 2019-05-08 |  | 2019-03-26 | 2019-05-14 |  | 2019-03-28 | 2019-05-08 |  | 2019-04-01 | 2019-05-14 |  | 2019-12-19 | 2019-12-04
2019-08-01 | LY35A-BS-6A | 2018-12-11 |  | 2019-02-04 | 2018-12-13 |  | 2019-02-06 | 2018-12-20 |  | 2019-02-12 | 2019-01-20 |  | 2019-03-05 | 2019-03-25 | 2019-05-10 |  | 2019-04-01 | 2019-05-09 |  | 2019-04-08 | 2019-05-17 |  | 2019-04-15 | 2019-05-24 |  | 2019-04-11 | 2019-05-23 |  | 2019-04-15 | 2019-05-30 |  | 2019-06-18 | 2019-07-08
2019-08-01 | LY35A-BS-6A | 2018-12-11 |  | 2019-02-06 | 2018-12-13 |  | 2019-02-05 | 2018-12-20 |  | 2019-02-12 | 2019-01-20 |  | 2019-03-05 | 2019-03-25 | 2019-05-09 |  | 2019-04-01 | 2019-05-10 |  | 2019-04-08 | 2019-05-16 |  | 2019-04-15 | 2019-05-23 |  | 2019-04-11 | 2019-05-22 |  | 2019-04-15 | 2019-05-30 |  | 2019-10-24 | 2019-11-09
2019-08-01 | LY36A-BS-6A | 2018-10-30 |  | 2018-11-16 | 2018-11-05 |  | 2018-11-15 | 2018-11-12 |  | 2018-11-14 | 2019-01-15 |  | 2019-01-17 | 2019-03-19 | 2019-05-09 |  | 2019-03-05 | 2019-05-11 |  | 2019-03-12 | 2019-05-10 |  | 2019-03-19 | 2019-05-17 |  | 2019-03-21 | 2019-05-24 |  | 2019-03-25 | 2019-06-04 |  | 2019-10-17 | 2019-11-13
2019-08-01 | LY38A-BS-6A | 2018-08-19 |  | 2018-08-21 | 2018-08-23 |  | 2018-08-23 | 2018-08-29 |  | 2018-08-29 | 2018-10-12 |  | 2018-10-11 | 2018-11-30 |  | 2019-03-14 | 2018-12-07 |  | 2019-03-14 | 2018-12-14 | 2019-05-03 |  | 2018-12-21 | 2019-05-10 |  | 2019-04-29 | 2019-06-03 |  | 2019-05-07 | 2019-06-10 |  | 2019-09-23 | 2019-09-12
2019-08-01 | LY41A-BS-6A | 2019-05-15 | 2019-06-06 |  | 2019-05-22 | 2019-06-14 |  | 2019-05-30 | 2019-06-21 |  | 2019-06-27 | 2019-07-17 |  | 2019-08-01 | 2019-08-21 |  | 2019-08-08 | 2019-08-29 |  | 2019-08-15 | 2019-09-07 |  | 2019-08-22 | 2019-09-14 |  | 2019-08-30 | 2019-09-19 |  | 2019-09-06 | 2019-09-27 |  | 2019-08-14 | 2019-08-13
2019-08-01 | LY42A-BS-6A | 2018-08-18 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-19 | 2018-08-31 |  | 2018-08-31 | 2018-10-12 |  | 2018-10-13 | 2018-11-30 |  | 2019-03-06 | 2018-12-07 |  | 2019-03-06 | 2018-12-14 |  | 2019-04-25 | 2018-12-21 | 2019-05-08 |  | 2019-01-07 | 2019-06-05 |  | 2019-01-14 | 2019-06-10 |  | 2019-10-20 | 2019-09-28
2019-08-01 | LY42A-BS-6A | 2018-08-19 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-21 | 2018-08-31 |  | 2018-08-30 | 2018-10-12 |  | 2018-10-11 | 2018-11-30 |  | 2019-03-07 | 2018-12-07 |  | 2019-03-07 | 2018-12-14 |  | 2019-04-25 | 2018-12-21 | 2019-05-07 |  | 2019-01-07 | 2019-06-04 |  | 2019-01-14 | 2019-06-10 |  | 2019-12-14 | 2020-01-17
2019-08-01 | LY44A-BS-6A | 2019-01-29 |  | 2019-04-18 | 2019-02-05 |  | 2019-04-21 | 2019-02-12 |  | 2019-04-26 | 2019-03-26 | 2019-05-25 |  | 2019-05-17 | 2019-07-01 |  | 2019-05-24 | 2019-07-10 |  | 2019-06-03 | 2019-07-16 |  | 2019-06-10 | 2019-07-24 |  | 2019-06-17 | 2019-07-29 |  | 2019-06-24 | 2019-08-07 |  | 2019-10-28 | 2019-10-19
2019-08-01 | LY48A-BS-6A | 2019-02-15 |  | 2019-03-30 | 2019-02-21 |  | 2019-04-01 | 2019-02-28 |  | 2019-04-10 | 2019-04-11 | 2019-05-22 |  | 2019-06-05 | 2019-07-12 |  | 2019-06-12 | 2019-07-18 |  | 2019-06-19 | 2019-07-25 |  | 2019-06-26 | 2019-08-01 |  | 2019-07-03 | 2019-08-10 |  | 2019-07-10 | 2019-08-17 |  | 2019-08-15 | 2019-07-21
2019-08-01 | LY49A-BS-6A | 2019-01-23 |  | 2019-02-12 | 2019-01-31 |  | 2019-02-13 | 2019-02-07 |  | 2019-02-14 | 2019-03-21 |  | 2019-03-13 | 2019-05-14 | 2019-05-02 |  | 2019-05-21 | 2019-05-09 |  | 2019-05-29 | 2019-05-17 |  | 2019-07-10 | 2019-06-28 |  | 2019-07-10 | 2019-06-28 |  | 2019-07-17 | 2019-07-05 |  | 2019-09-23 | 2019-09-17
2019-08-01 | LY50A-BS-6A | 2018-11-29 |  | 2019-02-25 | 2018-12-05 |  | 2019-03-06 | 2018-12-12 |  | 2019-03-07 | 2019-01-31 | 2019-04-30 |  | 2019-03-21 | 2019-06-20 |  | 2019-03-28 | 2019-06-19 |  | 2019-04-04 | 2019-06-26 |  | 2019-04-11 | 2019-07-04 |  | 2019-04-18 | 2019-07-10 |  | 2019-04-29 | 2019-07-16 |  | 2019-09-30 | 2019-08-28
2019-08-01 | LY52A-BS-6A | 2019-03-06 | 2019-05-08 |  | 2019-03-13 | 2019-05-14 |  | 2019-03-20 | 2019-05-16 |  | 2019-05-03 | 2019-06-28 |  | 2019-06-25 | 2019-08-15 |  | 2019-07-02 | 2019-08-24 |  | 2019-07-09 | 2019-09-01 |  | 2019-07-16 | 2019-09-09 |  | 2019-07-23 | 2019-09-16 |  | 2019-07-30 | 2019-09-24 |  | 2019-06-11 | 2019-07-05
2019-08-01 | LY66A-BS-6A | 2018-06-28 |  | 2018-06-29 | 2018-07-05 |  | 2018-07-06 | 2018-07-12 |  | 2018-07-12 | 2018-08-13 |  | 2018-08-13 | 2018-10-25 |  | 2019-01-22 | 2018-11-01 |  | 2019-01-22 | 2018-11-08 |  | 2018-12-18 | 2018-11-15 |  | 2019-01-10 | 2018-11-22 |  | 2019-03-04 | 2018-11-29 |  | 2019-03-12 | 2019-10-19 | 2019-11-27
2019-08-01 | LY66A-BS-6A | 2018-06-28 |  | 2018-06-30 | 2018-07-05 |  | 2018-07-05 | 2018-07-12 |  | 2018-07-12 | 2018-08-13 |  | 2018-08-13 | 2018-10-25 |  | 2019-01-23 | 2018-11-01 |  | 2019-01-22 | 2018-11-08 |  | 2018-12-20 | 2018-11-15 |  | 2019-01-09 | 2018-11-22 |  | 2019-03-05 | 2018-11-29 |  | 2019-03-10 | 2019-08-22 | 2019-08-16
2019-08-01 | LY66B-BS-6A | 2018-07-02 |  | 2018-07-03 | 2018-07-05 |  | 2018-07-04 | 2018-07-12 |  | 2018-07-11 | 2018-08-13 |  | 2018-08-13 | 2018-10-25 |  | 2018-12-10 | 2018-11-01 |  | 2018-12-09 | 2018-11-08 |  | 2018-12-04 | 2018-11-15 |  | 2018-12-06 | 2018-11-22 |  | 2019-02-18 | 2018-11-29 |  | 2019-02-27 | 2019-11-10 | 2019-10-22
2019-08-01 | LY66B-BS-6A | 2018-07-02 |  | 2018-07-03 | 2018-07-05 |  | 2018-07-05 | 2018-07-12 |  | 2018-07-11 | 2018-08-13 |  | 2018-08-14 | 2018-10-25 |  | 2018-12-11 | 2018-11-01 |  | 2018-12-09 | 2018-11-08 |  | 2018-12-06 | 2018-11-15 |  | 2018-12-07 | 2018-11-22 |  | 2019-02-19 | 2018-11-29 |  | 2019-02-27 | 2019-06-07 | 2019-06-05
2019-08-01 | LY66B-BS-6A | 2018-07-03 |  | 2018-07-03 | 2018-07-05 |  | 2018-07-04 | 2018-07-12 |  | 2018-07-12 | 2018-08-13 |  | 2018-08-13 | 2018-10-25 |  | 2018-12-09 | 2018-11-01 |  | 2018-12-10 | 2018-11-08 |  | 2018-12-05 | 2018-11-15 |  | 2018-12-06 | 2018-11-22 |  | 2019-02-20 | 2018-11-29 |  | 2019-02-27 | 2019-12-10 | 2019-11-03
2019-08-01 | LY78A-BS-6A | 2018-06-10 |  | 2018-06-10 | 2018-06-27 |  | 2018-06-26 | 2018-07-03 |  | 2018-07-03 | 2018-08-02 |  | 2018-08-01 | 2018-10-18 |  | 2018-10-24 | 2018-10-11 |  | 2018-10-24 | 2018-11-22 |  | 2019-03-06 | 2018-11-29 |  | 2019-04-16 | 2019-07-12 | 2019-07-10 |  | 2019-07-19 | 2019-07-17 |  | 2019-08-20 | 2019-08-02
2019-08-01 | LY78B-BS-6A | 2018-06-10 |  | 2018-06-10 | 2018-06-12 |  | 2018-06-11 | 2018-07-03 |  | 2018-07-02 | 2018-07-27 |  | 2018-07-27 | 2018-10-11 |  | 2018-10-23 | 2018-10-11 |  | 2018-10-25 | 2018-11-22 |  | 2019-03-08 | 2018-11-29 |  | 2019-04-18 | 2019-07-12 | 2019-07-10 |  | 2019-07-19 | 2019-07-18 |  | 2019-06-24 | 2019-06-17
2019-08-01 | LY78C-BS-6A | 2019-02-27 | 2019-06-05 |  | 2019-03-07 | 2019-06-11 |  | 2019-03-14 | 2019-06-13 |  | 2019-04-29 | 2019-07-03 |  | 2019-06-19 | 2019-08-16 |  | 2019-06-26 | 2019-08-14 |  | 2019-07-03 | 2019-08-21 |  | 2019-07-10 | 2019-08-29 |  | 2019-07-17 | 2019-09-07 |  | 2019-07-24 | 2019-09-13 |  | 2019-08-03 | 2019-09-10
2019-08-01 | LY78C-BS-6A | 2019-02-27 | 2019-06-05 |  | 2019-03-07 | 2019-06-11 |  | 2019-03-14 | 2019-06-12 |  | 2019-04-29 | 2019-07-04 |  | 2019-06-19 | 2019-08-15 |  | 2019-06-26 | 2019-08-15 |  | 2019-07-03 | 2019-08-21 |  | 2019-07-10 | 2019-08-31 |  | 2019-07-17 | 2019-09-06 |  | 2019-07-24 | 2019-09-14 |  | 2019-06-22 | 2019-07-01
2019-08-01 | LY78D-BS-6A | 2019-02-28 | 2019-05-20 |  | 2019-03-07 | 2019-05-23 |  | 2019-03-14 | 2019-05-28 |  | 2019-04-29 | 2019-07-02 |  | 2019-06-19 | 2019-08-07 |  | 2019-06-26 | 2019-08-15 |  | 2019-07-03 | 2019-08-23 |  | 2019-07-10 | 2019-08-31 |  | 2019-07-17 | 2019-09-07 |  | 2019-07-24 | 2019-09-12 |  | 2019-09-27 | 2019-09-03
2019-08-01 | LY85A-BS-6A | 2019-10-08 | 2019-10-08 |  | 2019-10-15 | 2019-10-16 |  | 2019-10-22 | 2019-10-23 |  | 2019-12-03 | 2019-12-02 |  | 2020-01-29 | 2020-01-30 |  | 2020-02-05 | 2020-02-05 |  | 2020-02-12 | 2020-02-13 |  | 2020-02-19 | 2020-02-19 |  | 2020-02-26 | 2020-02-26 |  | 2020-03-04 | 2020-03-03 |  | 2019-12-25 | 2020-01-05
2019-08-01 | LY95A-BS-6A | 2018-12-01 |  | 2019-03-28 | 2018-12-07 |  | 2019-04-03 | 2018-12-14 |  | 2019-04-10 | 2019-01-21 | 2019-05-03 |  | 2019-02-25 | 2019-05-22 |  | 2019-03-04 | 2019-05-22 |  | 2019-03-11 | 2019-05-31 |  | 2019-04-24 | 2019-07-10 |  | 2019-04-24 | 2019-07-12 |  | 2019-05-01 | 2019-07-18 |  | 2019-09-22 | 2019-08-24
2019-08-01 | LY97A-BS-6A | 2019-02-05 | 2020-02-03 |  | 2019-02-11 | 2020-02-10 |  | 2019-02-18 | 2020-02-18 |  | 2019-04-01 | 2020-03-31 |  | 2019-05-23 | 2020-05-20 |  | 2019-05-31 | 2020-05-29 |  | 2019-06-07 | 2020-06-06 |  | 2019-06-14 | 2020-06-12 |  | 2019-06-21 | 2020-06-19 |  | 2019-06-28 | 2020-06-27 |  | 2019-10-03 | 2019-08-28
2019-08-01 | LY99A-BS-6A | 2019-08-09 | 2019-08-08 |  | 2019-08-16 | 2019-08-16 |  | 2019-08-23 | 2019-08-23 |  | 2019-10-07 | 2019-10-06 |  | 2019-11-25 | 2019-11-26 |  | 2019-12-02 | 2019-12-03 |  | 2019-12-09 | 2019-12-08 |  | 2019-12-16 | 2019-12-15 |  | 2019-12-23 | 2019-12-23 |  | 2020-01-07 | 2020-01-08 |  | 2019-08-20 | 2019-09-02
2019-08-01 | AL01A-BS-6A | 2018-05-30 |  | 2018-05-29 | 2018-05-31 |  | 2018-05-30 | 2018-06-07 |  | 2018-06-08 | 2018-08-13 |  | 2018-08-13 | 2018-11-14 |  | 2019-01-22 | 2018-11-21 |  | 2019-01-21 | 2018-11-28 |  | 2019-01-10 | 2018-12-05 |  | 2019-01-25 | 2018-12-12 |  | 2019-01-29 | 2018-12-19 |  | 2019-02-05 | 2019-10-09 | 2019-11-06
2019-08-01 | AL01A-BS-6A | 2018-05-29 |  | 2018-05-30 | 2018-05-31 |  | 2018-05-30 | 2018-06-07 |  | 2018-06-08 | 2018-08-13 |  | 2018-08-13 | 2018-11-14 |  | 2019-01-23 | 2018-11-21 |  | 2019-01-23 | 2018-11-28 |  | 2019-01-10 | 2018-12-05 |  | 2019-01-24 | 2018-12-12 |  | 2019-01-29 | 2018-12-19 |  | 2019-02-04 | 2019-06-24 | 2019-05-25
2019-08-01 | AL01A-BS-6A | 2018-05-28 |  | 2018-05-29 | 2018-05-31 |  | 2018-05-30 | 2018-06-07 |  | 2018-06-07 | 2018-08-13 |  | 2018-08-14 | 2018-11-14 |  | 2019-01-22 | 2018-11-21 |  | 2019-01-22 | 2018-11-28 |  | 2019-01-09 | 2018-12-05 |  | 2019-01-24 | 2018-12-12 |  | 2019-01-28 | 2018-12-19 |  | 2019-02-04 | 2019-10-17 | 2019-11-26
2019-08-01 | AL01A-BS-6A | 2018-05-29 |  | 2018-05-30 | 2018-05-31 |  | 2018-05-30 | 2018-06-07 |  | 2018-06-08 | 2018-08-13 |  | 2018-08-13 | 2018-11-14 |  | 2019-01-23 | 2018-11-21 |  | 2019-01-23 | 2018-11-28 |  | 2019-01-08 | 2018-12-05 |  | 2019-01-26 | 2018-12-12 |  | 2019-01-29 | 2018-12-19 |  | 2019-02-04 | 2019-11-29 | 2019-12-08
2019-08-01 | AL01A-BS-6A | 2018-05-29 |  | 2018-05-29 | 2018-05-31 |  | 2018-05-30 | 2018-06-07 |  | 2018-06-08 | 2018-08-13 |  | 2018-08-12 | 2018-11-14 |  | 2019-01-22 | 2018-11-21 |  | 2019-01-23 | 2018-11-28 |  | 2019-01-09 | 2018-12-05 |  | 2019-01-26 | 2018-12-12 |  | 2019-01-28 | 2018-12-19 |  | 2019-02-04 | 2019-12-16 | 2019-12-15
2019-08-01 | AL06A-BS-6A | 2018-04-03 |  | 2018-04-03 | 2018-04-04 |  | 2018-04-05 | 2018-05-17 |  | 2018-05-16 | 2018-07-19 |  | 2018-07-19 | 2018-10-24 |  | 2018-11-01 | 2018-10-31 |  | 2018-10-30 | 2018-11-07 |  | 2018-11-01 | 2018-11-14 |  | 2019-03-05 | 2018-11-21 |  | 2018-12-18 | 2019-01-09 |  | 2019-03-21 | 2019-08-03 | 2019-08-25
2019-08-01 | AL07A-BS-6A | 2019-10-10 | 2019-10-08 |  | 2019-10-16 | 2019-10-17 |  | 2019-10-23 | 2019-10-24 |  | 2019-12-04 | 2019-12-05 |  | 2020-01-30 | 2020-01-30 |  | 2020-02-06 | 2020-02-07 |  | 2020-02-13 | 2020-02-12 |  | 2020-02-20 | 2020-02-19 |  | 2020-02-27 | 2020-02-27 |  | 2020-03-05 | 2020-03-04 |  | 2019-08-28 | 2019-07-25
2019-08-01 | AL07A-BS-6A | 2019-10-10 | 2019-10-09 |  | 2019-10-16 | 2019-10-17 |  | 2019-10-23 | 2019-10-24 |  | 2019-12-04 | 2019-12-04 |  | 2020-01-30 | 2020-01-31 |  | 2020-02-06 | 2020-02-06 |  | 2020-02-13 | 2020-02-12 |  | 2020-02-20 | 2020-02-20 |  | 2020-02-27 | 2020-02-28 |  | 2020-03-05 | 2020-03-04 |  | 2019-06-12 | 2019-07-14
2019-08-01 | AL11A-BS-6A | 2018-07-12 |  | 2018-07-10 | 2018-07-12 |  | 2018-07-13 | 2018-07-18 |  | 2018-07-19 | 2018-08-22 |  | 2018-08-22 | 2018-11-16 |  | 2018-11-22 | 2018-11-28 |  | 2018-11-27 | 2018-12-05 |  | 2019-01-06 | 2018-12-12 |  | 2019-01-26 | 2019-01-16 |  | 2019-01-22 | 2019-01-23 |  | 2019-02-16 | 2019-08-21 | 2019-09-06
2019-08-01 | AL11A-BS-6A | 2018-07-11 |  | 2018-07-10 | 2018-07-12 |  | 2018-07-13 | 2018-07-18 |  | 2018-07-19 | 2018-08-22 |  | 2018-08-21 | 2018-11-16 |  | 2018-11-23 | 2018-11-28 |  | 2018-11-28 | 2018-12-05 |  | 2019-01-07 | 2018-12-12 |  | 2019-01-24 | 2019-01-16 |  | 2019-01-23 | 2019-01-23 |  | 2019-02-16 | 2019-06-14 | 2019-05-06
2019-08-01 | AL11A-BS-6A | 2018-07-11 |  | 2018-07-10 | 2018-07-12 |  | 2018-07-12 | 2018-07-18 |  | 2018-07-19 | 2018-08-22 |  | 2018-08-21 | 2018-11-16 |  | 2018-11-21 | 2018-11-28 |  | 2018-11-27 | 2018-12-05 |  | 2019-01-08 | 2018-12-12 |  | 2019-01-25 | 2019-01-16 |  | 2019-01-23 | 2019-01-23 |  | 2019-02-15 | 2019-11-22 | 2019-12-07
2019-08-01 | AL11A-BS-6A | 2018-07-10 |  | 2018-07-10 | 2018-07-12 |  | 2018-07-13 | 2018-07-18 |  | 2018-07-19 | 2018-08-22 |  | 2018-08-22 | 2018-11-16 |  | 2018-11-23 | 2018-11-28 |  | 2018-11-27 | 2018-12-05 |  | 2019-01-08 | 2018-12-12 |  | 2019-01-26 | 2019-01-16 |  | 2019-01-24 | 2019-01-23 |  | 2019-02-14 | 2019-09-18 | 2019-10-04
2019-08-01 | AL87A-BS-6A | 2018-11-12 |  | 2018-12-22 | 2018-11-16 |  | 2018-12-24 | 2018-11-20 |  | 2019-01-07 | 2018-12-04 |  | 2019-01-13 | 2018-12-13 |  | 2019-01-21 | 2018-12-18 |  | 2019-01-21 | [6 empty] | 2019-01-04 |  | 2019-02-20 | 2019-01-11 |  | 2019-02-25 | 2019-12-07 | 2019-12-10
2019-08-01 | AL88A-BS-6A | 2019-02-05 |  | 2019-02-25 | 2019-02-11 |  | 2019-02-26 | 2019-02-18 |  | 2019-02-27 | 2019-03-04 |  | 2019-03-17 | 2019-03-25 |  | 2019-03-21 | 2019-04-01 |  | 2019-03-25 | [6 empty] | 2019-04-08 | 2019-05-16 |  | 2019-04-15 | 2019-05-22 |  | 2019-11-02 | 2019-11-30
2019-08-01 | AL88A-BS-6A | 2019-02-03 |  | 2019-02-25 | 2019-02-11 |  | 2019-02-28 | 2019-02-18 |  | 2019-02-27 | 2019-03-04 |  | 2019-03-18 | 2019-03-25 |  | 2019-03-23 | 2019-04-01 |  | 2019-03-26 | [6 empty] | 2019-04-08 | 2019-05-16 |  | 2019-04-15 | 2019-05-22 |  | 2019-06-06 | 2019-07-02
2019-08-01 | AL89A-BS-6A | 2019-01-23 |  | 2019-02-26 | 2019-01-29 |  | 2019-02-26 | 2019-02-05 |  | 2019-03-01 | 2019-02-19 |  | 2019-03-08 | 2019-03-12 |  | 2019-03-16 | 2019-03-19 |  | 2019-03-15 | [6 empty] | 2019-03-26 |  | 2019-03-29 | 2019-04-02 |  | 2019-04-13 | 2019-10-09 | 2019-11-02
2019-08-01 | AL90A-BS-6A | 2018-11-22 |  | 2018-12-04 | 2018-11-30 |  | 2018-12-05 | 2018-12-07 |  | 2018-12-10 | 2019-02-11 |  | 2019-02-12 | 2019-04-15 | 2019-05-01 |  | 2019-04-24 | 2019-05-01 |  | 2019-05-01 | 2019-05-01 |  | 2019-05-09 | 2019-05-09 |  | 2019-05-16 | 2019-05-15 |  | 2019-05-23 | 2019-05-23 |  | 2019-11-22 | 2019-11-11
2019-08-01 | AL90A-BS-6A | 2018-11-24 |  | 2018-12-04 | 2018-11-30 |  | 2018-12-04 | 2018-12-07 |  | 2018-12-11 | 2019-02-11 |  | 2019-02-10 | 2019-04-15 | 2019-05-01 |  | 2019-04-24 | 2019-04-29 |  | 2019-05-01 | 2019-04-30 |  | 2019-05-09 | 2019-05-10 |  | 2019-05-16 | 2019-05-17 |  | 2019-05-23 | 2019-05-23 |  | 2019-09-27 | 2019-11-04
2019-08-01 | AL90A-BS-6A | 2018-11-24 |  | 2018-12-05 | 2018-11-30 |  | 2018-12-04 | 2018-12-07 |  | 2018-12-10 | 2019-02-11 |  | 2019-02-11 | 2019-04-15 | 2019-04-30 |  | 2019-04-24 | 2019-04-30 |  | 2019-05-01 | 2019-05-02 |  | 2019-05-09 | 2019-05-09 |  | 2019-05-16 | 2019-05-17 |  | 2019-05-23 | 2019-05-22 |  | 2019-11-02 | 2019-11-23
2019-08-01 | AL91A-BS-6A | 2018-05-20 |  | 2018-05-20 | 2018-05-31 |  | 2018-05-31 | 2018-06-07 |  | 2018-06-06 | 2018-08-13 |  | 2018-08-13 | 2018-11-14 |  | 2019-01-22 | 2018-11-21 |  | 2019-01-22 | [6 empty] | 2018-12-12 |  | 2019-01-30 | 2018-12-19 |  | 2019-02-06 | 2019-07-16 | 2019-08-12
2019-08-01 | AL91A-BS-6A | 2018-05-20 |  | 2018-05-21 | 2018-05-31 |  | 2018-05-30 | 2018-06-07 |  | 2018-06-08 | 2018-08-13 |  | 2018-08-13 | 2018-11-14 |  | 2019-01-21 | 2018-11-21 |  | 2019-01-21 | [6 empty] | 2018-12-12 |  | 2019-01-30 | 2018-12-19 |  | 2019-02-06 | 2019-10-01 | 2019-09-08
2019-08-01 | AL91A-BS-6A | 2018-05-22 |  | 2018-05-21 | 2018-05-31 |  | 2018-06-01 | 2018-06-07 |  | 2018-06-08 | 2018-08-13 |  | 2018-08-14 | 2018-11-14 |  | 2019-01-23 | 2018-11-21 |  | 2019-01-21 | [6 empty] | 2018-12-12 |  | 2019-01-30 | 2018-12-19 |  | 2019-02-08 | 2019-11-27 | 2019-10-20
2019-08-01 | PP01A-BS-6A | 2018-05-29 |  | 2018-05-31 | 2018-05-31 |  | 2018-06-01 | 2018-08-09 |  | 2018-08-08 | 2018-09-28 |  | 2018-09-28 | 2018-11-16 |  | 2019-01-22 | 2018-11-23 |  | 2019-01-25 | 2018-11-30 |  | 2019-01-31 | 2018-12-07 |  | 2019-02-22 | 2018-12-14 |  | 2019-03-13 | 2019-02-01 |  | 2019-03-28 | 2019-10-10 | 2019-10-08
2019-08-01 | PP01B-BS-6A | 2019-02-13 |  | 2019-02-21 | 2019-02-19 |  | 2019-03-12 | 2019-02-26 |  | 2019-03-21 | 2019-04-09 |  | 2019-04-24 | 2019-06-03 | 2019-05-30 |  | 2019-06-10 | 2019-06-05 |  | 2019-06-17 | 2019-06-12 |  | 2019-06-24 | 2019-06-19 |  | 2019-07-01 | 2019-06-26 |  | 2019-07-08 | 2019-07-03 |  | 2019-07-08 | 2019-07-24
2019-08-01 | VC01A-BS-6A | 2018-05-26 |  | 2018-05-25 | 2018-05-29 |  | 2018-05-29 | 2018-08-15 |  | 2018-08-15 | 2018-09-27 |  | 2018-09-26 | 2018-12-13 |  | 2019-01-21 | 2018-12-20 |  | 2019-01-20 | 2019-01-04 |  | 2019-03-12 | 2019-01-11 |  | 2019-03-26 | 2019-01-18 |  | 2019-04-01 | 2019-03-29 |  | 2019-04-04 | 2019-07-17 | 2019-06-24
2019-08-01 | VC01A-BS-6A | 2018-05-26 |  | 2018-05-26 | 2018-05-29 |  | 2018-05-29 | 2018-08-15 |  | 2018-08-15 | 2018-09-27 |  | 2018-09-26 | 2018-12-13 |  | 2019-01-21 | 2018-12-20 |  | 2019-01-22 | 2019-01-04 |  | 2019-03-11 | 2019-01-11 |  | 2019-03-27 | 2019-01-18 |  | 2019-03-31 | 2019-03-29 |  | 2019-04-04 | 2019-07-18 | 2019-07-22
2019-08-01 | VC02A-BS-6A | 2018-05-20 |  | 2018-05-20 | 2018-05-22 |  | 2018-05-21 | 2018-06-06 |  | 2018-06-06 | 2018-07-06 |  | 2018-07-07 | 2018-11-16 |  | 2018-12-08 | 2018-11-23 |  | 2018-12-08 | 2018-11-30 |  | 2018-12-11 | 2018-12-07 |  | 2019-01-31 | 2018-12-14 |  | 2019-01-03 | 2018-12-21 |  | 2019-02-12 | 2019-10-17 | 2019-10-04
2019-08-01 | VC02A-BS-6A | 2018-05-20 |  | 2018-05-22 | 2018-05-22 |  | 2018-05-22 | 2018-06-06 |  | 2018-06-06 | 2018-07-06 |  | 2018-07-06 | 2018-11-16 |  | 2018-12-08 | 2018-11-23 |  | 2018-12-07 | 2018-11-30 |  | 2018-12-13 | 2018-12-07 |  | 2019-02-01 | 2018-12-14 |  | 2019-01-02 | 2018-12-21 |  | 2019-02-14 | 2019-07-04 | 2019-06-23
2019-08-01 | VC03A-BS-6A | 2019-07-29 | 2019-07-28 |  | 2019-08-05 | 2019-08-05 |  | 2019-08-12 | 2019-08-12 |  | 2019-09-24 | 2019-09-23 |  | 2019-11-12 | 2019-11-13 |  | 2019-11-19 | 2019-11-19 |  | 2019-11-26 | 2019-11-27 |  | 2019-12-03 | 2019-12-02 |  | 2019-12-10 | 2019-12-10 |  | 2019-12-17 | 2019-12-16 |  | 2019-07-02 | 2019-06-26
2019-08-01 | NH01A-BS-6A | 2018-01-16 |  | 2018-01-14 | 2018-01-18 |  | 2018-01-18 | 2018-06-08 |  | 2018-06-08 | 2018-08-03 |  | 2018-08-02 | 2018-11-23 |  | 2018-12-19 | 2018-11-27 |  | 2019-01-21 | 2018-11-30 |  | 2019-01-23 | 2019-01-25 |  | 2019-04-11 | 2019-01-23 |  | 2019-04-11 | 2019-01-25 | 2019-04-29 |  | 2019-10-23 | 2019-09-22
2019-08-01 | NH02A-BS-6A | 2018-02-13 |  | 2018-02-14 | 2018-02-13 |  | 2018-02-14 | 2018-06-08 |  | 2018-06-07 | 2018-08-03 |  | 2018-08-04 | 2018-11-23 |  | 2019-02-18 | 2018-11-27 |  | 2019-02-19 | 2018-11-30 |  | 2019-01-30 | 2019-01-25 |  | 2019-04-11 | 2019-01-23 |  | 2019-04-11 | 2019-01-25 | 2019-04-30 |  | 2019-10-01 | 2019-11-05
2019-08-01 | NH03A-BS-6A | 2018-02-21 |  | 2018-02-19 | 2018-02-20 |  | 2018-02-19 | 2018-06-14 |  | 2018-06-15 | 2018-09-07 |  | 2018-09-06 | 2018-12-07 |  | 2019-02-04 | 2018-12-14 |  | 2018-11-27 | 2018-12-19 |  | 2018-12-02 | 2018-12-21 |  | 2018-12-07 | 2019-01-15 |  | 2019-03-21 | 2019-01-17 |  | 2019-03-28 | 2019-11-07 | 2019-10-18
2019-08-01 | NH04A-BS-6A | 2018-03-14 |  | 2018-03-12 | 2018-03-15 |  | 2018-03-15 | 2018-06-14 |  | 2018-06-14 | 2018-08-13 |  | 2018-08-12 | 2018-12-07 |  | 2018-11-26 | 2018-12-14 |  | 2018-11-26 | 2018-12-19 |  | 2018-12-03 | 2018-12-21 |  | 2018-12-06 | 2019-01-15 |  | 2019-03-09 | 2019-01-17 |  | 2019-03-27 | 2019-06-20 | 2019-06-25
2019-08-01 | NH06A-BS-6A | 2018-03-01 |  | 2018-02-27 | 2018-02-28 |  | 2018-03-01 | 2018-07-30 |  | 2018-07-29 | 2018-09-11 |  | 2018-09-11 | 2018-11-27 |  | 2019-02-20 | 2018-12-14 |  | 2019-03-05 | 2018-12-21 |  | 2019-03-04 | 2019-01-07 |  | 2019-03-25 | 2019-01-14 |  | 2019-03-16 | 2019-01-21 |  | 2019-04-01 | 2019-12-14 | 2020-01-13
2019-08-01 | NH06A-BS-6A | 2018-03-01 |  | 2018-02-27 | 2018-02-28 |  | 2018-02-27 | 2018-07-30 |  | 2018-07-30 | 2018-09-11 |  | 2018-09-12 | 2018-11-27 |  | 2019-02-18 | 2018-12-14 |  | 2019-03-04 | 2018-12-21 |  | 2019-03-06 | 2019-01-07 |  | 2019-03-26 | 2019-01-14 |  | 2019-03-14 | 2019-01-21 |  | 2019-04-03 | 2019-12-11 | 2020-03-06
2019-08-01 | NH06A-BS-6A | 2018-02-27 |  | 2018-02-28 | 2018-02-28 |  | 2018-02-27 | 2018-07-30 |  | 2018-07-31 | 2018-09-11 |  | 2018-09-10 | 2018-11-27 |  | 2019-02-18 | 2018-12-14 |  | 2019-03-04 | 2018-12-21 |  | 2019-03-04 | 2019-01-07 |  | 2019-03-26 | 2019-01-14 |  | 2019-03-15 | 2019-01-21 |  | 2019-04-02 | 2019-09-25 | 2019-09-27
2019-08-01 | NH06A-BS-6A | 2018-02-28 |  | 2018-03-01 | 2018-02-28 |  | 2018-03-01 | 2018-07-30 |  | 2018-07-30 | 2018-09-11 |  | 2018-09-10 | 2018-11-27 |  | 2019-02-20 | 2018-12-14 |  | 2019-03-05 | 2018-12-21 |  | 2019-03-05 | 2019-01-07 |  | 2019-03-26 | 2019-01-14 |  | 2019-03-14 | 2019-01-21 |  | 2019-04-01 | 2019-08-01 | 2019-08-03
2019-08-01 | NH07A-BS-6A | 2018-05-30 |  | 2018-06-01 | 2018-06-01 |  | 2018-06-02 | 2018-06-22 |  | 2018-06-22 | 2018-08-10 |  | 2018-08-09 | 2018-10-29 |  | 2019-01-08 | 2018-11-05 |  | 2019-01-08 | 2018-11-12 |  | 2019-01-06 | 2018-11-19 |  | 2019-01-31 | 2018-11-26 |  | 2019-02-26 | 2018-12-03 |  | 2019-03-22 | 2019-10-23 | 2019-10-31
2019-08-01 | NH07A-BS-6A | 2018-06-01 |  | 2018-05-30 | 2018-06-01 |  | 2018-05-31 | 2018-06-22 |  | 2018-06-21 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-06 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-08 | 2018-11-19 |  | 2019-02-01 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-20 | 2019-10-15 | 2019-09-06
2019-08-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-06-01 | 2018-06-01 |  | 2018-05-31 | 2018-06-22 |  | 2018-06-23 | 2018-08-10 |  | 2018-08-09 | 2018-10-29 |  | 2019-01-08 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-07 | 2018-11-19 |  | 2019-02-02 | 2018-11-26 |  | 2019-02-26 | 2018-12-03 |  | 2019-03-21 | 2019-06-13 | 2019-05-05
2019-08-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-05-30 | 2018-06-01 |  | 2018-05-31 | 2018-06-22 |  | 2018-06-21 | 2018-08-10 |  | 2018-08-11 | 2018-10-29 |  | 2019-01-06 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-06 | 2018-11-19 |  | 2019-01-31 | 2018-11-26 |  | 2019-02-26 | 2018-12-03 |  | 2019-03-20 | 2019-08-01 | 2019-09-05
2019-08-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-05-30 | 2018-06-01 |  | 2018-06-01 | 2018-06-22 |  | 2018-06-21 | 2018-08-10 |  | 2018-08-11 | 2018-10-29 |  | 2019-01-08 | 2018-11-05 |  | 2019-01-06 | 2018-11-12 |  | 2019-01-08 | 2018-11-19 |  | 2019-01-31 | 2018-11-26 |  | 2019-02-26 | 2018-12-03 |  | 2019-03-20 | 2019-12-05 | 2020-01-08
2019-08-01 | NH07A-BS-6A | 2018-06-01 |  | 2018-06-01 | 2018-06-01 |  | 2018-06-02 | 2018-06-22 |  | 2018-06-23 | 2018-08-10 |  | 2018-08-09 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-07 | 2018-11-19 |  | 2019-02-01 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-22 | 2019-06-08 | 2019-05-02
2019-08-01 | NH07A-BS-6A | 2018-05-30 |  | 2018-05-30 | 2018-06-01 |  | 2018-06-02 | 2018-06-22 |  | 2018-06-21 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-08 | 2018-11-12 |  | 2019-01-08 | 2018-11-19 |  | 2019-01-31 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-21 | 2019-08-30 | 2019-08-11
2019-08-01 | NH07A-BS-6A | 2018-05-31 |  | 2018-05-30 | 2018-06-01 |  | 2018-06-02 | 2018-06-22 |  | 2018-06-23 | 2018-08-10 |  | 2018-08-11 | 2018-10-29 |  | 2019-01-06 | 2018-11-05 |  | 2019-01-08 | 2018-11-12 |  | 2019-01-08 | 2018-11-19 |  | 2019-01-31 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-22 | 2019-06-27 | 2019-06-17
2019-08-01 | NH07A-BS-6A | 2018-05-30 |  | 2018-05-31 | 2018-06-01 |  | 2018-06-02 | 2018-06-22 |  | 2018-06-22 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-08 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-06 | 2018-11-19 |  | 2019-02-02 | 2018-11-26 |  | 2019-02-26 | 2018-12-03 |  | 2019-03-21 | 2019-11-11 | 2019-11-03
2019-08-01 | NH07A-BS-6A | 2018-05-30 |  | 2018-05-30 | 2018-06-01 |  | 2018-06-02 | 2018-06-22 |  | 2018-06-23 | 2018-08-10 |  | 2018-08-09 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-07 | 2018-11-12 |  | 2019-01-08 | 2018-11-19 |  | 2019-02-02 | 2018-11-26 |  | 2019-02-25 | 2018-12-03 |  | 2019-03-21 | 2019-12-24 | 2019-12-16
2019-08-01 | NH07A-BS-6A | 2018-06-01 |  | 2018-05-31 | 2018-06-01 |  | 2018-06-02 | 2018-06-22 |  | 2018-06-22 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-06 | 2018-11-05 |  | 2019-01-06 | 2018-11-12 |  | 2019-01-07 | 2018-11-19 |  | 2019-02-02 | 2018-11-26 |  | 2019-02-26 | 2018-12-03 |  | 2019-03-20 | 2019-10-17 | 2019-11-18
2019-08-01 | NH07A-BS-6A | 2018-05-30 |  | 2018-05-31 | 2018-06-01 |  | 2018-06-02 | 2018-06-22 |  | 2018-06-21 | 2018-08-10 |  | 2018-08-10 | 2018-10-29 |  | 2019-01-07 | 2018-11-05 |  | 2019-01-06 | 2018-11-12 |  | 2019-01-06 | 2018-11-19 |  | 2019-01-31 | 2018-11-26 |  | 2019-02-24 | 2018-12-03 |  | 2019-03-20 | 2019-08-21 | 2019-09-07
2019-08-01 | NH10A-BS-6A | 2018-05-15 |  | 2018-05-15 | 2018-05-15 |  | 2018-05-14 | 2018-06-22 |  | 2018-06-23 | 2018-07-30 |  | 2018-07-31 | 2018-11-22 |  | 2018-12-03 | 2018-11-29 |  | 2018-12-07 | 2018-12-06 |  | 2018-12-11 | 2018-12-13 |  | 2019-01-03 | 2018-12-20 |  | 2019-02-24 | 2019-01-04 |  | 2019-03-05 | 2019-11-17 | 2019-12-16
2019-08-01 | NH12A-BS-6A | 2018-03-06 |  | 2018-03-08 | 2018-03-08 |  | 2018-03-08 | 2018-04-17 |  | 2018-04-17 | 2018-08-10 |  | 2018-08-10 | 2018-10-26 |  | 2019-02-15 | 2018-10-26 |  | 2019-02-14 | 2018-11-01 |  | 2019-02-18 | 2018-11-08 |  | 2019-02-28 | 2018-11-13 |  | 2019-03-01 | 2018-11-14 |  | 2019-03-20 | 2019-09-21 | 2019-10-29
2019-08-01 | NH12A-BS-6A | 2018-03-08 |  | 2018-03-08 | 2018-03-08 |  | 2018-03-07 | 2018-04-17 |  | 2018-04-16 | 2018-08-10 |  | 2018-08-09 | 2018-10-26 |  | 2019-02-15 | 2018-10-26 |  | 2019-02-16 | 2018-11-01 |  | 2019-02-20 | 2018-11-08 |  | 2019-02-28 | 2018-11-13 |  | 2019-02-28 | 2018-11-14 |  | 2019-03-22 | 2019-09-01 | 2019-08-20
2019-08-01 | NH12A-BS-6A | 2018-03-06 |  | 2018-03-06 | 2018-03-08 |  | 2018-03-07 | 2018-04-17 |  | 2018-04-17 | 2018-08-10 |  | 2018-08-10 | 2018-10-26 |  | 2019-02-14 | 2018-10-26 |  | 2019-02-15 | 2018-11-01 |  | 2019-02-18 | 2018-11-08 |  | 2019-02-28 | 2018-11-13 |  | 2019-03-01 | 2018-11-14 |  | 2019-03-21 | 2019-06-04 | 2019-07-05
2019-08-01 | NH12A-BS-6A | 2018-03-07 |  | 2018-03-08 | 2018-03-08 |  | 2018-03-08 | 2018-04-17 |  | 2018-04-18 | 2018-08-10 |  | 2018-08-09 | 2018-10-26 |  | 2019-02-14 | 2018-10-26 |  | 2019-02-14 | 2018-11-01 |  | 2019-02-18 | 2018-11-08 |  | 2019-02-27 | 2018-11-13 |  | 2019-02-28 | 2018-11-14 |  | 2019-03-22 | 2019-11-09 | 2019-11-28
2019-08-01 | NH12A-BS-6A | 2018-03-06 |  | 2018-03-07 | 2018-03-08 |  | 2018-03-09 | 2018-04-17 |  | 2018-04-18 | 2018-08-10 |  | 2018-08-11 | 2018-10-26 |  | 2019-02-15 | 2018-10-26 |  | 2019-02-15 | 2018-11-01 |  | 2019-02-20 | 2018-11-08 |  | 2019-02-27 | 2018-11-13 |  | 2019-02-28 | 2018-11-14 |  | 2019-03-20 | 2019-11-16 | 2019-10-31
2019-08-01 | NH13A-BS-6A | 2018-08-11 |  | 2018-08-10 | 2018-08-13 |  | 2018-08-12 | 2018-08-17 |  | 2018-08-18 | 2018-09-24 |  | 2018-09-23 | 2018-11-26 |  | 2019-03-28 | 2018-12-03 |  | 2019-03-29 | 2018-12-10 |  | 2019-04-02 | 2018-12-17 |  | 2019-04-13 | 2018-12-19 |  | 2019-04-29 | 2018-12-21 | 2019-05-09 |  | 2019-08-23 | 2019-08-02
2019-08-01 | NH13A-BS-6A | 2018-08-09 |  | 2018-08-10 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-16 | 2018-09-24 |  | 2018-09-23 | 2018-11-26 |  | 2019-03-29 | 2018-12-03 |  | 2019-03-30 | 2018-12-10 |  | 2019-03-31 | 2018-12-17 |  | 2019-04-11 | 2018-12-19 |  | 2019-04-29 | 2018-12-21 | 2019-05-07 |  | 2019-10-22 | 2019-11-24
2019-08-01 | NH14A-BS-6A | 2018-11-09 |  | 2018-11-18 | 2018-11-16 |  | 2018-11-20 | 2018-11-23 |  | 2018-11-19 | 2019-01-18 |  | 2019-01-15 | 2019-03-07 | 2019-05-15 |  | 2019-03-15 | 2019-05-15 |  | 2019-03-22 | 2019-05-15 |  | 2019-03-29 | 2019-05-23 |  | 2019-04-02 | 2019-05-30 |  | 2019-04-04 | 2019-06-08 |  | 2019-10-14 | 2019-11-10
2019-08-01 | NH14A-BS-6A | 2018-11-08 |  | 2018-11-19 | 2018-11-16 |  | 2018-11-20 | 2018-11-23 |  | 2018-11-19 | 2019-01-18 |  | 2019-01-15 | 2019-03-07 | 2019-05-15 |  | 2019-03-15 | 2019-05-15 |  | 2019-03-22 | 2019-05-17 |  | 2019-03-29 | 2019-05-23 |  | 2019-04-02 | 2019-05-31 |  | 2019-04-04 | 2019-06-08 |  | 2019-08-01 | 2019-08-23
2019-08-01 | NH14A-BS-6A | 2018-11-08 |  | 2018-11-18 | 2018-11-16 |  | 2018-11-20 | 2018-11-23 |  | 2018-11-21 | 2019-01-18 |  | 2019-01-15 | 2019-03-07 | 2019-05-16 |  | 2019-03-15 | 2019-05-17 |  | 2019-03-22 | 2019-05-17 |  | 2019-03-29 | 2019-05-22 |  | 2019-04-02 | 2019-05-31 |  | 2019-04-04 | 2019-06-07 |  | 2019-11-30 | 2019-12-10
2019-08-01 | NH15A-BS-6A | 2018-08-11 |  | 2018-08-10 | 2018-08-13 |  | 2018-08-12 | 2018-08-14 |  | 2018-08-14 | 2018-09-25 |  | 2018-09-26 | 2018-11-27 |  | 2019-03-07 | 2018-11-30 |  | 2019-03-07 | 2018-12-07 |  | 2019-03-07 | 2018-12-14 |  | 2019-03-28 | 2018-12-21 |  | 2019-04-10 | 2019-01-07 |  | 2019-04-24 | 2019-09-09 | 2019-10-04
2019-08-01 | NH15A-BS-6A | 2018-08-09 |  | 2018-08-09 | 2018-08-13 |  | 2018-08-12 | 2018-08-14 |  | 2018-08-14 | 2018-09-25 |  | 2018-09-25 | 2018-11-27 |  | 2019-03-07 | 2018-11-30 |  | 2019-03-08 | 2018-12-07 |  | 2019-03-09 | 2018-12-14 |  | 2019-03-26 | 2018-12-21 |  | 2019-04-10 | 2019-01-07 |  | 2019-04-24 | 2019-12-03 | 2019-12-25
2019-08-01 | NH15A-BS-6A | 2018-08-09 |  | 2018-08-09 | 2018-08-13 |  | 2018-08-13 | 2018-08-14 |  | 2018-08-13 | 2018-09-25 |  | 2018-09-26 | 2018-11-27 |  | 2019-03-09 | 2018-11-30 |  | 2019-03-07 | 2018-12-07 |  | 2019-03-08 | 2018-12-14 |  | 2019-03-28 | 2018-12-21 |  | 2019-04-11 | 2019-01-07 |  | 2019-04-22 | 2019-11-15 | 2019-10-12
2019-08-01 | NH16A-BS-6A | 2018-03-14 |  | 2018-03-15 | 2018-03-16 |  | 2018-03-16 | 2018-07-04 |  | 2018-07-05 | 2018-08-30 |  | 2018-08-31 | 2018-11-15 |  | 2018-11-26 | 2018-11-29 |  | 2018-11-26 | 2018-12-06 |  | 2019-04-01 | 2018-12-13 |  | 2019-04-11 | 2018-12-20 |  | 2019-03-14 | 2019-03-08 |  | 2019-05-01 | 2019-10-06 | 2019-09-08
2019-08-01 | NH16A-BS-6A | 2018-03-15 |  | 2018-03-15 | 2018-03-16 |  | 2018-03-17 | 2018-07-04 |  | 2018-07-04 | 2018-08-30 |  | 2018-08-29 | 2018-11-15 |  | 2018-11-26 | 2018-11-29 |  | 2018-11-28 | 2018-12-06 |  | 2019-03-31 | 2018-12-13 |  | 2019-04-13 | 2018-12-20 |  | 2019-03-14 | 2019-03-08 |  | 2019-05-01 | 2019-11-12 | 2019-12-19
2019-08-01 | NH17A-BS-6A | 2018-06-21 |  | 2018-06-21 | 2018-06-25 |  | 2018-06-24 | 2018-07-31 |  | 2018-07-31 | 2018-09-27 |  | 2018-09-26 | 2018-11-22 |  | 2018-12-17 | 2018-11-29 |  | 2018-12-17 | 2018-12-06 |  | 2019-01-04 | 2018-12-13 |  | 2019-02-02 | 2018-12-20 |  | 2019-03-12 | 2019-01-04 |  | 2019-03-24 | 2019-10-18 | 2019-09-09
2019-08-01 | NH17A-BS-6A | 2018-06-20 |  | 2018-06-22 | 2018-06-25 |  | 2018-06-26 | 2018-07-31 |  | 2018-07-30 | 2018-09-27 |  | 2018-09-28 | 2018-11-22 |  | 2018-12-19 | 2018-11-29 |  | 2018-12-19 | 2018-12-06 |  | 2019-01-03 | 2018-12-13 |  | 2019-02-01 | 2018-12-20 |  | 2019-03-14 | 2019-01-04 |  | 2019-03-25 | 2019-10-07 | 2019-09-03
2019-08-01 | NH17A-BS-6A | 2018-06-22 |  | 2018-06-21 | 2018-06-25 |  | 2018-06-25 | 2018-07-31 |  | 2018-07-30 | 2018-09-27 |  | 2018-09-28 | 2018-11-22 |  | 2018-12-17 | 2018-11-29 |  | 2018-12-18 | 2018-12-06 |  | 2019-01-03 | 2018-12-13 |  | 2019-01-31 | 2018-12-20 |  | 2019-03-12 | 2019-01-04 |  | 2019-03-24 | 2019-07-27 | 2019-07-19
2019-08-01 | NH18A-BS-6A | 2018-08-15 |  | 2018-08-16 | 2018-08-16 |  | 2018-08-16 | 2018-08-17 |  | 2018-08-16 | 2018-10-16 |  | 2018-10-15 | 2018-12-14 |  | 2019-03-05 | 2018-12-14 |  | 2019-03-05 | 2019-01-07 |  | 2019-03-04 | 2019-01-14 |  | 2019-04-03 | 2019-01-16 |  | 2019-03-27 | 2019-01-17 |  | 2019-04-17 | 2019-08-01 | 2019-08-05
2019-08-01 | NH18A-BS-6A | 2018-08-16 |  | 2018-08-15 | 2018-08-16 |  | 2018-08-16 | 2018-08-17 |  | 2018-08-18 | 2018-10-16 |  | 2018-10-14 | 2018-12-14 |  | 2019-03-05 | 2018-12-14 |  | 2019-03-04 | 2019-01-07 |  | 2019-03-05 | 2019-01-14 |  | 2019-04-03 | 2019-01-16 |  | 2019-03-28 | 2019-01-17 |  | 2019-04-16 | 2019-09-03 | 2019-09-15
2019-08-01 | NH18A-BS-6A | 2018-08-14 |  | 2018-08-16 | 2018-08-16 |  | 2018-08-17 | 2018-08-17 |  | 2018-08-16 | 2018-10-16 |  | 2018-10-16 | 2018-12-14 |  | 2019-03-05 | 2018-12-14 |  | 2019-03-03 | 2019-01-07 |  | 2019-03-05 | 2019-01-14 |  | 2019-04-03 | 2019-01-16 |  | 2019-03-28 | 2019-01-17 |  | 2019-04-16 | 2019-11-11 | 2019-11-14
2019-08-01 | NH19A-BS-6A | 2019-08-15 | 2019-08-16 |  | 2019-08-22 | 2019-08-23 |  | 2019-08-30 | 2019-08-29 |  | 2019-10-11 | 2019-10-11 |  | 2019-11-29 | 2019-11-29 |  | 2019-12-06 | 2019-12-05 |  | 2019-12-13 | 2019-12-12 |  | 2019-12-20 | 2019-12-19 |  | 2020-01-06 | 2020-01-03 |  | 2020-01-13 | 2020-01-09 |  | 2019-12-05 | 2019-11-17
2019-08-01 | NH23A-BS-6A | 2018-05-18 |  | 2018-05-18 | 2018-05-21 |  | 2018-05-21 | 2018-06-21 |  | 2018-06-20 | 2018-09-07 |  | 2018-09-06 | 2018-11-29 |  | 2018-12-10 | 2018-12-06 |  | 2018-12-12 | 2018-12-13 |  | 2019-02-24 | 2018-12-20 |  | 2019-02-27 | 2019-01-04 |  | 2019-01-19 | 2019-01-11 |  | 2019-03-13 | 2019-06-24 | 2019-06-10
2019-08-01 | NH23A-BS-6A | 2018-05-17 |  | 2018-05-18 | 2018-05-21 |  | 2018-05-20 | 2018-06-21 |  | 2018-06-22 | 2018-09-07 |  | 2018-09-08 | 2018-11-29 |  | 2018-12-10 | 2018-12-06 |  | 2018-12-12 | 2018-12-13 |  | 2019-02-25 | 2018-12-20 |  | 2019-02-28 | 2019-01-04 |  | 2019-01-17 | 2019-01-11 |  | 2019-03-13 | 2019-12-21 | 2019-11-15
2019-08-01 | NH23A-BS-6A | 2018-05-19 |  | 2018-05-17 | 2018-05-21 |  | 2018-05-20 | 2018-06-21 |  | 2018-06-20 | 2018-09-07 |  | 2018-09-07 | 2018-11-29 |  | 2018-12-10 | 2018-12-06 |  | 2018-12-11 | 2018-12-13 |  | 2019-02-25 | 2018-12-20 |  | 2019-02-28 | 2019-01-04 |  | 2019-01-17 | 2019-01-11 |  | 2019-03-14 | 2019-07-13 | 2019-06-23
2019-08-01 | NH24A-BS-6A | 2018-03-19 |  | 2018-03-18 | 2018-03-19 |  | 2018-03-19 | 2018-05-31 |  | 2018-05-31 | 2018-07-06 |  | 2018-07-06 | 2018-11-01 |  | 2018-11-15 | 2018-11-09 |  | 2018-11-20 | 2018-11-16 |  | 2019-01-31 | 2018-11-23 |  | 2019-02-21 | 2018-11-30 |  | 2019-02-22 | 2018-12-07 |  | 2019-04-02 | 2019-12-22 | 2019-11-16
2019-08-01 | NH27A-BS-6A | 2018-04-23 |  | 2018-04-25 | 2018-04-25 |  | 2018-04-24 | 2018-06-28 |  | 2018-06-27 | 2018-08-09 |  | 2018-08-08 | 2018-11-09 |  | 2018-12-20 | 2018-11-16 |  | 2018-12-18 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-02 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-05 | 2019-11-21 | 2019-10-16
2019-08-01 | NH27A-BS-6A | 2018-04-23 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-26 | 2018-06-28 |  | 2018-06-29 | 2018-08-09 |  | 2018-08-10 | 2018-11-09 |  | 2018-12-20 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-01-31 | 2018-12-07 |  | 2019-02-26 | 2018-12-14 |  | 2019-03-05 | 2019-07-19 | 2019-08-07
2019-08-01 | NH27A-BS-6A | 2018-04-23 |  | 2018-04-25 | 2018-04-25 |  | 2018-04-26 | 2018-06-28 |  | 2018-06-27 | 2018-08-09 |  | 2018-08-10 | 2018-11-09 |  | 2018-12-20 | 2018-11-16 |  | 2018-12-20 | 2018-11-23 |  | 2019-01-16 | 2018-11-30 |  | 2019-02-02 | 2018-12-07 |  | 2019-02-26 | 2018-12-14 |  | 2019-03-07 | 2019-10-28 | 2019-11-17
2019-08-01 | NH27A-BS-6A | 2018-04-23 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-10 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-18 | 2018-11-23 |  | 2019-01-14 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-24 | 2018-12-14 |  | 2019-03-07 | 2019-12-13 | 2019-12-22
2019-08-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-23 | 2018-04-25 |  | 2018-04-26 | 2018-06-28 |  | 2018-06-29 | 2018-08-09 |  | 2018-08-10 | 2018-11-09 |  | 2018-12-18 | 2018-11-16 |  | 2018-12-18 | 2018-11-23 |  | 2019-01-14 | 2018-11-30 |  | 2019-02-02 | 2018-12-07 |  | 2019-02-26 | 2018-12-14 |  | 2019-03-07 | 2019-06-22 | 2019-06-27
2019-08-01 | NH27A-BS-6A | 2018-04-25 |  | 2018-04-23 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-18 | 2018-11-16 |  | 2018-12-18 | 2018-11-23 |  | 2019-01-14 | 2018-11-30 |  | 2019-02-02 | 2018-12-07 |  | 2019-02-26 | 2018-12-14 |  | 2019-03-07 | 2019-07-30 | 2019-08-05
2019-08-01 | NH27A-BS-6A | 2018-04-25 |  | 2018-04-25 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-10 | 2018-11-09 |  | 2018-12-18 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-01-31 | 2018-12-07 |  | 2019-02-26 | 2018-12-14 |  | 2019-03-06 | 2019-09-23 | 2019-09-03
2019-08-01 | NH27A-BS-6A | 2018-04-23 |  | 2018-04-23 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-10 | 2018-11-09 |  | 2018-12-18 | 2018-11-16 |  | 2018-12-18 | 2018-11-23 |  | 2019-01-14 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-25 | 2018-12-14 |  | 2019-03-07 | 2019-11-04 | 2019-10-03
2019-08-01 | NH27A-BS-6A | 2018-04-23 |  | 2018-04-23 | 2018-04-25 |  | 2018-04-24 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-09 | 2018-11-09 |  | 2018-12-20 | 2018-11-16 |  | 2018-12-18 | 2018-11-23 |  | 2019-01-16 | 2018-11-30 |  | 2019-01-31 | 2018-12-07 |  | 2019-02-26 | 2018-12-14 |  | 2019-03-06 | 2019-06-30 | 2019-07-09
2019-08-01 | NH27A-BS-6A | 2018-04-25 |  | 2018-04-25 | 2018-04-25 |  | 2018-04-24 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-08 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-02-02 | 2018-12-07 |  | 2019-02-24 | 2018-12-14 |  | 2019-03-05 | 2019-12-17 | 2019-11-20
2019-08-01 | NH27A-BS-6A | 2018-04-25 |  | 2018-04-25 | 2018-04-25 |  | 2018-04-24 | 2018-06-28 |  | 2018-06-29 | 2018-08-09 |  | 2018-08-08 | 2018-11-09 |  | 2018-12-18 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-16 | 2018-11-30 |  | 2019-02-02 | 2018-12-07 |  | 2019-02-26 | 2018-12-14 |  | 2019-03-06 | 2019-06-19 | 2019-06-13
2019-08-01 | NH27A-BS-6A | 2018-04-24 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-27 | 2018-08-09 |  | 2018-08-08 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-19 | 2018-11-23 |  | 2019-01-15 | 2018-11-30 |  | 2019-01-31 | 2018-12-07 |  | 2019-02-24 | 2018-12-14 |  | 2019-03-06 | 2019-11-23 | 2019-10-14
2019-08-01 | NH27A-BS-6A | 2018-04-25 |  | 2018-04-25 | 2018-04-25 |  | 2018-04-25 | 2018-06-28 |  | 2018-06-28 | 2018-08-09 |  | 2018-08-08 | 2018-11-09 |  | 2018-12-19 | 2018-11-16 |  | 2018-12-18 | 2018-11-23 |  | 2019-01-16 | 2018-11-30 |  | 2019-02-02 | 2018-12-07 |  | 2019-02-26 | 2018-12-14 |  | 2019-03-05 | 2019-07-12 | 2019-08-20
2019-08-01 | NH27A-BS-6A | 2018-04-23 |  | 2018-04-24 | 2018-04-25 |  | 2018-04-26 | 2018-06-28 |  | 2018-06-29 | 2018-08-09 |  | 2018-08-08 | 2018-11-09 |  | 2018-12-20 | 2018-11-16 |  | 2018-12-18 | 2018-11-23 |  | 2019-01-16 | 2018-11-30 |  | 2019-02-01 | 2018-12-07 |  | 2019-02-26 | 2018-12-14 |  | 2019-03-05 | 2019-10-05 | 2019-09-06
2019-08-01 | NH27B-BS-6A | 2019-02-26 |  | 2019-04-04 | 2019-03-06 |  | 2019-04-11 | 2019-03-13 |  | 2019-04-17 | 2019-05-13 | 2019-05-10 |  | 2019-07-16 | 2019-07-13 |  | 2019-07-23 | 2019-07-20 |  | 2019-07-30 | 2019-07-27 |  | 2019-08-06 | 2019-08-02 |  | 2019-08-13 | 2019-08-09 |  | 2019-08-20 | 2019-08-17 |  | 2019-12-30 | 2020-01-07
2019-08-01 | NH27C-BS-6A | 2019-06-06 | 2019-06-05 |  | 2019-06-13 | 2019-06-14 |  | 2019-06-20 | 2019-06-19 |  | 2019-07-18 | 2019-07-17 |  | 2019-08-22 | 2019-08-22 |  | 2019-08-30 | 2019-08-29 |  | 2019-09-06 | 2019-09-05 |  | 2019-09-13 | 2019-09-13 |  | 2019-09-20 | 2019-09-21 |  | 2019-09-27 | 2019-09-26 |  | 2019-07-21 | 2019-08-24
2019-08-01 | NH27C-BS-6A | 2019-06-06 | 2019-06-06 |  | 2019-06-13 | 2019-06-13 |  | 2019-06-20 | 2019-06-20 |  | 2019-07-18 | 2019-07-19 |  | 2019-08-22 | 2019-08-23 |  | 2019-08-30 | 2019-08-30 |  | 2019-09-06 | 2019-09-07 |  | 2019-09-13 | 2019-09-12 |  | 2019-09-20 | 2019-09-20 |  | 2019-09-27 | 2019-09-28 |  | 2019-07-05 | 2019-06-26
2019-08-01 | NH29A-BS-6A | 2018-11-29 |  | 2018-12-06 | 2018-12-07 |  | 2018-12-11 | 2018-12-14 |  | 2018-12-18 | 2019-01-21 |  | 2019-01-31 | 2019-02-25 |  | 2019-04-03 | 2019-03-04 |  | 2019-04-09 | 2019-03-11 |  | 2019-04-15 | 2019-03-18 | 2019-05-01 |  | 2019-03-25 | 2019-05-09 |  | 2019-04-01 | 2019-05-17 |  | 2019-07-25 | 2019-06-19
2019-08-01 | NH30A-BS-6A | 2019-03-15 |  | 2019-05-01 | 2019-03-21 |  | 2019-04-29 | 2019-03-28 | 2019-05-07 |  | 2019-05-14 | 2019-06-20 |  | 2019-07-03 | 2019-08-06 |  | 2019-07-10 | 2019-08-15 |  | 2019-07-17 | 2019-08-20 |  | 2019-07-24 | 2019-08-29 |  | 2019-07-31 | 2019-09-05 |  | 2019-08-07 | 2019-09-12 |  | 2019-12-26 | 2019-11-23
2019-08-01 | NH30A-BS-6A | 2019-03-14 |  | 2019-04-29 | 2019-03-21 |  | 2019-05-01 | 2019-03-28 | 2019-05-08 |  | 2019-05-14 | 2019-06-19 |  | 2019-07-03 | 2019-08-06 |  | 2019-07-10 | 2019-08-15 |  | 2019-07-17 | 2019-08-20 |  | 2019-07-24 | 2019-08-30 |  | 2019-07-31 | 2019-09-04 |  | 2019-08-07 | 2019-09-12 |  | 2019-07-18 | 2019-08-23
2019-08-01 | NH31A-BS-6A | 2018-02-07 |  | 2018-02-07 | 2018-02-12 |  | 2018-02-11 | 2018-03-07 |  | 2018-03-07 | 2018-04-17 |  | 2018-04-17 | 2018-08-17 |  | 2018-10-10 | 2018-10-16 |  | 2018-10-10 | 2018-10-23 |  | 2018-11-01 | 2018-10-30 |  | 2018-11-10 | 2018-11-06 |  | 2018-11-28 | 2018-11-13 |  | 2018-12-07 | 2019-09-15 | 2019-09-17
2019-08-01 | NH31A-BS-6A | 2018-02-07 |  | 2018-02-08 | 2018-02-12 |  | 2018-02-12 | 2018-03-07 |  | 2018-03-08 | 2018-04-17 |  | 2018-04-18 | 2018-08-17 |  | 2018-10-11 | 2018-10-16 |  | 2018-10-12 | 2018-10-23 |  | 2018-10-31 | 2018-10-30 |  | 2018-11-08 | 2018-11-06 |  | 2018-11-28 | 2018-11-13 |  | 2018-12-06 | 2019-09-22 | 2019-09-26
2019-08-01 | NH31A-BS-6A | 2018-02-09 |  | 2018-02-09 | 2018-02-12 |  | 2018-02-13 | 2018-03-07 |  | 2018-03-06 | 2018-04-17 |  | 2018-04-16 | 2018-08-17 |  | 2018-10-10 | 2018-10-16 |  | 2018-10-11 | 2018-10-23 |  | 2018-11-02 | 2018-10-30 |  | 2018-11-08 | 2018-11-06 |  | 2018-11-30 | 2018-11-13 |  | 2018-12-07 | 2019-09-15 | 2019-08-20
2019-08-01 | NH32A-BS-6A | 2018-02-22 |  | 2018-02-22 | 2018-02-26 |  | 2018-02-27 | 2018-03-20 |  | 2018-03-19 | 2018-05-30 |  | 2018-05-31 | 2018-10-10 |  | 2019-04-11 | 2018-10-17 |  | 2019-04-10 | 2018-10-24 |  | 2019-04-15 | 2018-10-31 |  | 2019-04-23 | 2018-11-07 |  | 2019-04-16 | 2018-11-14 | 2019-05-03 |  | 2019-11-27 | 2019-11-30
2019-08-01 | NH32A-BS-6A | 2018-02-23 |  | 2018-02-23 | 2018-02-26 |  | 2018-02-27 | 2018-03-20 |  | 2018-03-21 | 2018-05-30 |  | 2018-05-31 | 2018-10-10 |  | 2019-04-09 | 2018-10-17 |  | 2019-04-09 | 2018-10-24 |  | 2019-04-15 | 2018-10-31 |  | 2019-04-25 | 2018-11-07 |  | 2019-04-17 | 2018-11-14 | 2019-05-03 |  | 2019-09-08 | 2019-09-02
2019-08-01 | NH32A-BS-6A | 2018-02-22 |  | 2018-02-23 | 2018-02-26 |  | 2018-02-27 | 2018-03-20 |  | 2018-03-20 | 2018-05-30 |  | 2018-05-30 | 2018-10-10 |  | 2019-04-09 | 2018-10-17 |  | 2019-04-11 | 2018-10-24 |  | 2019-04-15 | 2018-10-31 |  | 2019-04-23 | 2018-11-07 |  | 2019-04-17 | 2018-11-14 | 2019-05-01 |  | 2019-09-22 | 2019-09-18
2019-08-01 | NH33A-BS-6A | 2018-09-11 |  | 2018-09-09 | 2018-09-11 |  | 2018-09-10 | 2018-09-11 |  | 2018-09-11 | 2018-10-08 |  | 2018-10-07 | 2018-12-10 |  | 2019-02-13 | 2018-12-17 |  | 2019-02-13 | 2018-12-24 |  | 2019-02-18 | 2019-01-08 |  | 2019-03-07 | 2019-01-15 |  | 2019-02-19 | 2019-01-22 |  | 2019-03-13 | 2019-09-18 | 2019-09-26
2019-08-01 | NH33A-BS-6A | 2018-09-10 |  | 2018-09-10 | 2018-09-11 |  | 2018-09-10 | 2018-09-11 |  | 2018-09-10 | 2018-10-08 |  | 2018-10-08 | 2018-12-10 |  | 2019-02-11 | 2018-12-17 |  | 2019-02-12 | 2018-12-24 |  | 2019-02-20 | 2019-01-08 |  | 2019-03-05 | 2019-01-15 |  | 2019-02-19 | 2019-01-22 |  | 2019-03-14 | 2019-08-24 | 2019-07-24
2019-08-01 | NH33A-BS-6A | 2018-09-09 |  | 2018-09-10 | 2018-09-11 |  | 2018-09-10 | 2018-09-11 |  | 2018-09-10 | 2018-10-08 |  | 2018-10-07 | 2018-12-10 |  | 2019-02-11 | 2018-12-17 |  | 2019-02-11 | 2018-12-24 |  | 2019-02-19 | 2019-01-08 |  | 2019-03-06 | 2019-01-15 |  | 2019-02-20 | 2019-01-22 |  | 2019-03-14 | 2019-10-17 | 2019-10-20
2019-08-01 | NH35A-BS-6A | 2018-09-12 |  | 2018-09-12 | 2018-09-12 |  | 2018-09-13 | 2018-09-14 |  | 2018-09-15 | 2018-10-18 |  | 2018-10-24 | 2018-12-06 |  | 2019-03-14 | 2018-12-13 |  | 2019-03-14 | 2018-12-20 |  | 2019-03-28 | 2019-01-04 |  | 2019-04-18 | 2019-01-10 |  | 2019-04-25 | 2019-01-11 | 2019-05-03 |  | 2019-08-14 | 2019-07-30
2019-08-01 | NH35A-BS-6A | 2018-09-11 |  | 2018-09-13 | 2018-09-12 |  | 2018-09-13 | 2018-09-14 |  | 2018-09-13 | 2018-10-18 |  | 2018-10-23 | 2018-12-06 |  | 2019-03-16 | 2018-12-13 |  | 2019-03-16 | 2018-12-20 |  | 2019-03-28 | 2019-01-04 |  | 2019-04-19 | 2019-01-10 |  | 2019-04-23 | 2019-01-11 | 2019-05-03 |  | 2019-09-26 | 2019-09-04
2019-08-01 | NH36A-BS-6A | 2019-02-20 | 2019-05-10 |  | 2019-02-28 | 2019-05-14 |  | 2019-03-07 | 2019-05-17 |  | 2019-04-04 | 2019-06-18 |  | 2019-05-14 | 2019-07-23 |  | 2019-05-21 | 2019-07-29 |  | 2019-05-29 | 2019-08-05 |  | 2019-07-10 | 2019-09-16 |  | 2019-07-10 | 2019-09-17 |  | 2019-07-17 | 2019-09-23 |  | 2019-09-19 | 2019-10-02
2019-08-01 | NH36A-BS-6A | 2019-02-21 | 2019-05-11 |  | 2019-02-28 | 2019-05-12 |  | 2019-03-07 | 2019-05-17 |  | 2019-04-04 | 2019-06-17 |  | 2019-05-14 | 2019-07-22 |  | 2019-05-21 | 2019-07-28 |  | 2019-05-29 | 2019-08-05 |  | 2019-07-10 | 2019-09-17 |  | 2019-07-10 | 2019-09-17 |  | 2019-07-17 | 2019-09-23 |  | 2019-06-16 | 2019-05-24
2019-08-01 | NH36A-BS-6A | 2019-02-20 | 2019-05-11 |  | 2019-02-28 | 2019-05-12 |  | 2019-03-07 | 2019-05-16 |  | 2019-04-04 | 2019-06-16 |  | 2019-05-14 | 2019-07-21 |  | 2019-05-21 | 2019-07-29 |  | 2019-05-29 | 2019-08-06 |  | 2019-07-10 | 2019-09-18 |  | 2019-07-10 | 2019-09-16 |  | 2019-07-17 | 2019-09-23 |  | 2019-10-02 | 2019-09-05
2019-08-01 | NH36A-BS-6A | 2019-02-20 | 2019-05-09 |  | 2019-02-28 | 2019-05-14 |  | 2019-03-07 | 2019-05-18 |  | 2019-04-04 | 2019-06-17 |  | 2019-05-14 | 2019-07-21 |  | 2019-05-21 | 2019-07-29 |  | 2019-05-29 | 2019-08-06 |  | 2019-07-10 | 2019-09-18 |  | 2019-07-10 | 2019-09-17 |  | 2019-07-17 | 2019-09-23 |  | 2019-10-11 | 2019-11-01
2019-08-01 | NH36B-BS-6A | 2019-01-30 | 2019-05-16 |  | 2019-02-07 | 2019-05-18 |  | 2019-02-14 | 2019-05-23 |  | 2019-03-14 | 2019-06-21 |  | 2019-04-18 | 2019-07-24 |  | 2019-04-29 | 2019-07-31 |  | 2019-05-07 | 2019-08-09 |  | 2019-06-19 | 2019-09-19 |  | 2019-06-19 | 2019-09-21 |  | 2019-06-26 | 2019-09-26 |  | 2019-11-30 | 2019-12-24
2019-08-01 | NH37A-BS-6A | 2018-08-03 |  | 2018-08-05 | 2018-08-06 |  | 2018-08-05 | 2018-08-07 |  | 2018-08-08 | 2018-11-06 |  | 2018-10-29 | 2019-01-07 |  | 2019-04-26 | 2019-01-10 |  | 2019-04-30 | 2019-01-17 | 2019-05-01 |  | 2019-01-24 | 2019-05-07 |  | 2019-02-07 |  | 2019-05-02 | 2019-02-21 | 2019-05-08 |  | 2019-07-07 | 2019-06-10
2019-08-01 | NH43A-BS-6A | 2018-05-23 |  | 2018-05-23 | 2018-05-24 |  | 2018-05-23 | 2018-06-22 |  | 2018-06-22 | 2018-09-09 |  | 2018-09-10 | 2018-11-23 |  | 2018-12-19 | 2018-12-07 |  | 2018-12-19 | 2018-12-14 |  | 2019-02-25 | 2018-12-21 |  | 2019-03-19 | 2019-01-07 |  | 2019-02-25 | 2019-01-14 |  | 2019-04-01 | 2019-09-12 | 2019-10-16
2019-08-01 | NH49A-BS-6A | 2018-06-13 |  | 2018-06-11 | 2018-06-12 |  | 2018-06-13 | 2018-06-13 |  | 2018-06-12 | 2018-08-03 |  | 2018-08-02 | 2018-10-01 |  | 2018-11-22 | 2018-10-08 |  | 2018-11-22 | 2018-10-15 |  | 2018-11-28 | 2018-11-26 |  | 2019-02-19 | 2018-11-26 |  | 2019-01-20 | 2018-12-03 |  | 2019-03-10 | 2019-12-05 | 2019-11-13
2019-08-01 | NH50A-BS-6A | 2018-02-24 |  | 2018-02-24 | 2018-02-27 |  | 2018-02-28 | 2018-03-14 |  | 2018-03-14 | 2018-04-17 |  | 2018-04-17 | 2018-09-26 |  | 2018-09-26 | 2018-09-13 |  | 2018-09-13 | 2018-09-26 |  | 2018-09-27 | 2018-10-12 |  | 2018-10-19 | 2018-10-19 |  | 2018-11-08 | 2018-10-22 |  | 2018-11-16 | 2019-08-29 | 2019-09-08
2019-08-01 | NH58A-BS-6A | 2018-07-04 |  | 2018-07-06 | 2018-07-05 |  | 2018-07-04 | 2018-08-01 |  | 2018-08-01 | 2018-09-12 |  | 2018-09-12 | 2018-12-05 |  | 2019-02-23 | 2018-12-12 |  | 2019-02-22 | 2018-12-19 |  | 2019-02-27 | 2019-01-03 |  | 2019-03-20 | 2019-01-10 |  | 2019-03-14 | 2019-01-10 |  | 2019-04-01 | 2019-06-15 | 2019-05-19
2019-08-01 | NH58A-BS-6A | 2018-07-05 |  | 2018-07-05 | 2018-07-05 |  | 2018-07-06 | 2018-08-01 |  | 2018-08-02 | 2018-09-12 |  | 2018-09-13 | 2018-12-05 |  | 2019-02-21 | 2018-12-12 |  | 2019-02-22 | 2018-12-19 |  | 2019-02-26 | 2019-01-03 |  | 2019-03-18 | 2019-01-10 |  | 2019-03-13 | 2019-01-10 |  | 2019-04-01 | 2019-11-11 | 2019-12-18
2019-08-01 | NH72A-BS-6A | 2018-09-26 |  | 2018-09-26 | 2018-09-25 |  | 2018-09-24 | 2018-09-28 |  | 2018-09-29 | 2018-10-31 |  | 2018-10-30 | 2018-12-19 |  | 2019-02-12 | 2019-01-03 |  | 2019-02-12 | 2019-01-10 |  | 2019-03-20 | 2019-01-17 |  | 2019-04-11 | 2019-01-24 |  | 2019-03-13 | 2019-01-31 |  | 2019-04-26 | 2019-10-09 | 2019-09-02
2019-08-01 | NH91A-BS-6A | 2018-03-21 |  | 2018-03-22 | 2018-03-22 |  | 2018-03-21 | 2018-05-17 |  | 2018-05-16 | 2018-07-18 |  | 2018-07-19 | 2018-10-27 |  | 2018-10-26 | 2018-10-27 |  | 2018-10-24 | 2018-11-05 |  | 2018-11-29 | 2018-11-12 |  | 2018-12-12 | 2018-11-19 |  | 2019-02-08 | 2018-11-26 |  | 2019-03-12 | 2019-10-26 | 2019-10-24
2019-08-01 | NH92A-BS-6A | 2020-02-26 | 2020-02-25 |  | 2020-03-03 | 2020-03-04 |  | 2020-03-10 | 2020-03-09 |  | 2020-04-23 | 2020-04-23 |  | 2020-06-15 | 2020-06-14 |  | 2020-06-22 | 2020-06-22 |  | 2020-06-29 | 2020-06-29 |  | 2020-07-06 | 2020-07-07 |  | 2020-07-13 | 2020-07-12 |  | 2020-07-20 | 2020-07-20 |  | 2019-11-07 | 2019-11-14
2019-08-01 | MI01A-BS-6A | 2018-10-03 |  | 2018-10-04 | 2018-10-04 |  | 2018-10-05 | 2018-10-11 |  | 2018-10-12 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-04-07 | 2019-01-04 |  | 2019-04-09 | 2019-01-11 |  | 2019-02-27 | 2019-01-18 |  | 2019-04-01 | 2019-01-25 |  | 2019-04-16 | 2019-02-01 |  | 2019-05-02 | 2019-07-28 | 2019-08-27
2019-08-01 | MI01A-BS-6A | 2018-10-04 |  | 2018-10-05 | 2018-10-04 |  | 2018-10-04 | 2018-10-11 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-04-09 | 2019-01-04 |  | 2019-04-08 | 2019-01-11 |  | 2019-02-26 | 2019-01-18 |  | 2019-04-02 | 2019-01-25 |  | 2019-04-14 | 2019-02-01 |  | 2019-05-01 | 2019-07-01 | 2019-06-18
2019-08-01 | MI01A-BS-6A | 2018-10-05 |  | 2018-10-05 | 2018-10-04 |  | 2018-10-03 | 2018-10-11 |  | 2018-10-10 | 2018-11-08 |  | 2018-11-18 | 2019-01-04 |  | 2019-04-07 | 2019-01-04 |  | 2019-04-08 | 2019-01-11 |  | 2019-02-26 | 2019-01-18 |  | 2019-04-02 | 2019-01-25 |  | 2019-04-16 | 2019-02-01 |  | 2019-05-01 | 2019-09-08 | 2019-08-10
2019-08-01 | MI01A-BS-6A | 2018-10-04 |  | 2018-10-03 | 2018-10-04 |  | 2018-10-03 | 2018-10-11 |  | 2018-10-12 | 2018-11-08 |  | 2018-11-18 | 2019-01-04 |  | 2019-04-08 | 2019-01-04 |  | 2019-04-09 | 2019-01-11 |  | 2019-02-26 | 2019-01-18 |  | 2019-04-01 | 2019-01-25 |  | 2019-04-16 | 2019-02-01 |  | 2019-05-01 | 2019-10-30 | 2019-12-03
2019-08-01 | MI08A-BS-6A | 2018-10-09 |  | 2018-10-16 | 2018-10-10 |  | 2018-10-16 | 2018-10-17 |  | 2018-10-17 | 2018-11-14 |  | 2018-11-19 | 2018-12-19 | 2019-05-08 |  | 2019-01-03 | 2019-05-09 |  | 2019-01-10 | 2019-05-09 |  | 2019-02-21 | 2019-05-14 |  | 2019-02-21 | 2019-05-21 |  | 2019-02-28 | 2019-05-30 |  | 2019-12-23 | 2019-12-26
2019-08-01 | MI08A-BS-6A | 2018-10-09 |  | 2018-10-14 | 2018-10-10 |  | 2018-10-15 | 2018-10-17 |  | 2018-10-16 | 2018-11-14 |  | 2018-11-20 | 2018-12-19 | 2019-05-08 |  | 2019-01-03 | 2019-05-08 |  | 2019-01-10 | 2019-05-09 |  | 2019-02-21 | 2019-05-15 |  | 2019-02-21 | 2019-05-21 |  | 2019-02-28 | 2019-05-30 |  | 2019-06-22 | 2019-06-02
2019-08-01 | MI08A-BS-6A | 2018-10-11 |  | 2018-10-14 | 2018-10-10 |  | 2018-10-14 | 2018-10-17 |  | 2018-10-16 | 2018-11-14 |  | 2018-11-19 | 2018-12-19 | 2019-05-07 |  | 2019-01-03 | 2019-05-07 |  | 2019-01-10 | 2019-05-09 |  | 2019-02-21 | 2019-05-14 |  | 2019-02-21 | 2019-05-23 |  | 2019-02-28 | 2019-05-29 |  | 2019-07-17 | 2019-07-11
2019-08-01 | MI11A-BS-6A | 2018-10-13 |  | 2018-10-23 | 2018-10-18 |  | 2018-10-24 | 2018-10-25 |  | 2018-10-23 | 2018-11-01 |  | 2018-11-02 | 2018-12-06 |  | 2019-01-17 | 2018-11-29 |  | 2019-01-16 | 2018-12-06 |  | 2019-01-26 | 2019-01-25 | 2019-05-10 |  | 2019-01-25 |  | 2019-03-24 | 2019-02-01 | 2019-05-09 |  | 2019-06-30 | 2019-05-29
2019-08-01 | MI16A-BS-6A | 2018-10-26 |  | 2018-10-27 | 2018-10-26 |  | 2018-10-25 | 2018-10-29 |  | 2018-10-30 | 2018-11-22 |  | 2018-11-23 | 2019-01-31 |  | 2019-04-02 | 2019-01-31 |  | 2019-04-01 | 2019-01-28 |  | 2019-02-19 | 2019-02-04 |  | 2019-04-04 | 2019-02-14 |  | 2019-04-03 | 2019-02-21 |  | 2019-04-07 | 2019-08-22 | 2019-08-07
2019-08-01 | MI16A-BS-6A | 2018-10-26 |  | 2018-10-25 | 2018-10-26 |  | 2018-10-27 | 2018-10-29 |  | 2018-10-29 | 2018-11-22 |  | 2018-11-23 | 2019-01-31 |  | 2019-04-01 | 2019-01-31 |  | 2019-04-01 | 2019-01-28 |  | 2019-02-21 | 2019-02-04 |  | 2019-04-04 | 2019-02-14 |  | 2019-04-04 | 2019-02-21 |  | 2019-04-07 | 2019-12-21 | 2019-11-16
2019-08-01 | MI17A-BS-6A | 2018-11-05 |  | 2018-11-05 | 2018-11-05 |  | 2018-11-04 | 2018-11-05 |  | 2018-11-06 | 2018-12-06 |  | 2019-04-11 | 2019-02-15 |  | 2019-04-28 | 2019-02-22 |  | 2019-04-30 | 2019-03-01 |  | 2019-04-25 | 2019-03-08 | 2019-05-06 |  | 2019-03-15 | 2019-05-09 |  | 2019-03-22 | 2019-05-16 |  | 2019-11-27 | 2019-12-16
2019-08-01 | MI17A-BS-6A | 2018-11-04 |  | 2018-11-06 | 2018-11-05 |  | 2018-11-04 | 2018-11-05 |  | 2018-11-05 | 2018-12-06 |  | 2019-04-12 | 2019-02-15 |  | 2019-04-30 | 2019-02-22 |  | 2019-04-28 | 2019-03-01 |  | 2019-04-25 | 2019-03-08 | 2019-05-08 |  | 2019-03-15 | 2019-05-11 |  | 2019-03-22 | 2019-05-16 |  | 2019-11-28 | 2019-10-19
2019-08-01 | MI18A-BS-6A | 2018-10-29 |  | 2018-11-05 | 2018-10-29 |  | 2018-11-06 | 2018-10-29 |  | 2018-11-05 | 2018-11-19 |  | 2018-11-22 | 2018-12-14 |  | 2019-03-27 | 2018-12-17 |  | 2019-03-25 | 2018-12-24 |  | 2019-03-21 | 2019-01-08 |  | 2019-04-05 | 2019-01-15 |  | 2019-04-04 | 2019-01-22 |  | 2019-04-11 | 2019-08-01 | 2019-08-13
2019-08-01 | MI18A-BS-6A | 2018-10-30 |  | 2018-11-06 | 2018-10-29 |  | 2018-11-06 | 2018-10-29 |  | 2018-11-07 | 2018-11-19 |  | 2018-11-21 | 2018-12-14 |  | 2019-03-27 | 2018-12-17 |  | 2019-03-25 | 2018-12-24 |  | 2019-03-22 | 2019-01-08 |  | 2019-04-05 | 2019-01-15 |  | 2019-04-03 | 2019-01-22 |  | 2019-04-09 | 2019-08-01 | 2019-07-18
2019-08-01 | MI19A-BS-6A | 2018-09-14 |  | 2018-09-15 | 2018-09-14 |  | 2018-09-15 | 2018-09-17 |  | 2018-09-18 | 2018-11-26 |  | 2018-11-27 | 2019-02-05 |  | 2019-03-05 | 2019-02-12 |  | 2019-03-03 | 2019-02-19 |  | 2019-02-28 | 2019-02-26 |  | 2019-03-19 | 2019-03-05 |  | 2019-04-03 | 2019-03-12 |  | 2019-04-09 | 2019-09-09 | 2019-08-14
2019-08-01 | MI20A-BS-6A | 2018-09-21 |  | 2018-09-20 | 2018-09-20 |  | 2018-09-21 | 2018-09-24 |  | 2018-09-24 | 2018-12-17 |  | 2019-01-14 | 2019-02-26 |  | 2019-04-16 | 2019-03-05 |  | 2019-04-15 | 2019-03-12 | 2019-04-29 |  | 2019-03-19 | 2019-05-09 |  | 2019-03-26 |  | 2019-04-30 | 2019-04-02 | 2019-05-09 |  | 2019-08-03 | 2019-08-11
2019-08-01 | MI20A-BS-6A | 2018-09-19 |  | 2018-09-21 | 2018-09-20 |  | 2018-09-21 | 2018-09-24 |  | 2018-09-25 | 2018-12-17 |  | 2019-01-16 | 2019-02-26 |  | 2019-04-14 | 2019-03-05 |  | 2019-04-16 | 2019-03-12 | 2019-04-29 |  | 2019-03-19 | 2019-05-07 |  | 2019-03-26 |  | 2019-04-29 | 2019-04-02 | 2019-05-09 |  | 2019-08-28 | 2019-08-19
2019-08-01 | MI20A-BS-6A | 2018-09-20 |  | 2018-09-21 | 2018-09-20 |  | 2018-09-19 | 2018-09-24 |  | 2018-09-24 | 2018-12-17 |  | 2019-01-15 | 2019-02-26 |  | 2019-04-14 | 2019-03-05 |  | 2019-04-15 | 2019-03-12 | 2019-05-01 |  | 2019-03-19 | 2019-05-07 |  | 2019-03-26 |  | 2019-04-29 | 2019-04-02 | 2019-05-08 |  | 2019-08-04 | 2019-07-20
2019-08-01 | MI21A-BS-6A | 2018-09-29 |  | 2018-09-27 | 2018-10-02 |  | 2018-10-01 | 2018-10-02 |  | 2018-10-02 | 2018-12-18 |  | 2019-01-14 | 2019-01-17 |  | 2019-04-03 | 2019-03-06 |  | 2019-04-05 | 2019-03-13 |  | 2019-03-21 | 2019-03-20 |  | 2019-04-02 | 2019-03-27 |  | 2019-04-09 | 2019-04-03 |  | 2019-04-17 | 2019-10-16 | 2019-10-05
2019-08-01 | MI22A-BS-6A | 2018-11-01 |  | 2018-11-04 | 2018-11-09 |  | 2018-11-04 | 2018-11-16 |  | 2018-11-05 | 2019-01-21 |  | 2018-12-21 | 2019-03-25 | 2019-04-30 |  | 2019-04-01 | 2019-05-01 |  | 2019-04-08 |  | 2019-04-28 | 2019-04-15 | 2019-05-05 |  | 2019-04-24 | 2019-05-13 |  | 2019-05-01 | 2019-05-22 |  | 2019-12-21 | 2020-01-12
2019-08-01 | MI23A-BS-6A | 2018-10-12 |  | 2018-10-23 | 2018-10-19 |  | 2018-10-22 | 2018-10-26 |  | 2018-10-26 | 2018-12-21 |  | 2018-12-07 | 2019-03-04 |  | 2019-04-03 | 2019-03-11 |  | 2019-04-02 | 2019-03-18 | 2019-04-30 |  | 2019-03-25 | 2019-05-07 |  | 2019-04-01 |  | 2019-05-01 | 2019-04-08 | 2019-05-08 |  | 2019-07-27 | 2019-06-28
2019-08-01 | MI23A-BS-6A | 2018-10-11 |  | 2018-10-23 | 2018-10-19 |  | 2018-10-24 | 2018-10-26 |  | 2018-10-26 | 2018-12-21 |  | 2018-12-07 | 2019-03-04 |  | 2019-04-02 | 2019-03-11 |  | 2019-04-03 | 2019-03-18 | 2019-04-29 |  | 2019-03-25 | 2019-05-08 |  | 2019-04-01 |  | 2019-05-01 | 2019-04-08 | 2019-05-09 |  | 2019-12-27 | 2020-01-01
2019-08-01 | MI25A-BS-6A | 2019-06-12 |  | 2019-04-18 | 2019-06-19 |  | 2019-04-29 | 2019-06-26 | 2019-05-04 |  | 2019-07-24 | 2019-06-03 |  | 2019-08-29 | 2019-07-08 |  | 2019-09-05 | 2019-07-17 |  | 2019-09-12 | 2019-07-22 |  | 2019-09-19 | 2019-07-29 |  | 2019-09-26 | 2019-08-07 |  | 2019-10-03 | 2019-08-14 |  | 2019-06-24 | 2019-07-31
2019-08-01 | MI26A-BS-6A | 2019-07-19 |  | 2019-04-19 | 2019-07-26 |  | 2019-04-28 | 2019-08-02 | 2019-05-02 |  | 2019-09-02 | 2019-06-05 |  | 2019-10-07 | 2019-07-08 |  | 2019-10-14 | 2019-07-16 |  | 2019-10-21 | 2019-07-23 |  | 2019-10-28 | 2019-07-29 |  | 2019-11-04 | 2019-08-05 |  | 2019-11-11 | 2019-08-13 |  | 2019-08-09 | 2019-07-29
2019-08-01 | MI27A-BS-6A | 2019-05-23 | 2019-05-24 |  | 2019-06-03 | 2019-05-31 |  | 2019-06-10 | 2019-06-06 |  | 2019-07-08 | 2019-07-05 |  | 2019-08-12 | 2019-08-08 |  | 2019-08-19 | 2019-08-16 |  | 2019-08-27 | 2019-08-22 |  | 2019-09-03 | 2019-09-01 |  | 2019-09-10 | 2019-09-09 |  | 2019-09-17 | 2019-09-16 |  | 2019-08-07 | 2019-08-30
2019-08-01 | MI30A-BS-6A | 2018-10-23 |  | 2018-11-02 | 2018-10-23 |  | 2018-10-31 | 2018-10-24 |  | 2018-11-02 | 2018-12-04 |  | 2018-12-13 | 2019-02-05 |  | 2019-04-05 | 2019-02-12 |  | 2019-04-03 | 2019-02-14 |  | 2019-04-18 | 2019-02-21 |  | 2019-04-30 | 2019-02-28 |  | 2019-04-17 | 2019-03-05 | 2019-05-02 |  | 2019-06-10 | 2019-06-09
2019-08-01 | MI30A-BS-6A | 2018-10-22 |  | 2018-11-02 | 2018-10-23 |  | 2018-11-01 | 2018-10-24 |  | 2018-10-31 | 2018-12-04 |  | 2018-12-14 | 2019-02-05 |  | 2019-04-05 | 2019-02-12 |  | 2019-04-04 | 2019-02-14 |  | 2019-04-18 | 2019-02-21 |  | 2019-05-01 | 2019-02-28 |  | 2019-04-16 | 2019-03-05 | 2019-05-01 |  | 2019-12-02 | 2019-11-02
2019-08-01 | MI30B-BS-6A |  |  | 2018-11-01 |  |  | 2018-11-01 |  |  | 2018-11-01 |  |  | 2018-12-14 | [18 empty] | 2019-10-08 | 2019-11-02
2019-08-01 | MI31A-BS-6A | 2018-10-18 |  | 2018-11-15 | 2018-10-25 |  | 2018-11-15 | 2018-11-01 |  | 2018-11-15 | 2019-01-04 |  | 2018-12-06 | 2019-03-08 |  | 2019-04-01 | 2019-03-15 |  | 2019-04-01 | 2019-03-22 |  | 2019-04-01 | 2019-03-29 |  | 2019-04-12 | 2019-04-05 |  | 2019-04-12 | 2019-04-12 |  | 2019-04-15 | 2019-08-14 | 2019-07-18
2019-08-01 | MI32A-BS-6A | 2019-03-28 | 2019-05-13 |  | 2019-04-04 | 2019-05-20 |  | 2019-04-11 | 2019-05-28 |  | 2019-05-14 | 2019-06-25 |  | 2019-06-19 | 2019-07-30 |  | 2019-06-26 | 2019-08-06 |  | 2019-07-03 | 2019-08-13 |  | 2019-07-10 | 2019-08-20 |  | 2019-07-17 | 2019-08-28 |  | 2019-07-24 | 2019-09-04 |  | 2019-06-04 | 2019-06-28
2019-08-01 | MI33A-BS-6A | 2019-05-17 | 2019-05-16 |  | 2019-05-24 | 2019-05-23 |  | 2019-06-03 | 2019-05-31 |  | 2019-07-15 | 2019-07-12 |  | 2019-09-03 | 2019-09-02 |  | 2019-09-10 | 2019-09-09 |  | 2019-09-17 | 2019-09-16 |  | 2019-09-24 | 2019-09-23 |  | 2019-10-01 | 2019-09-30 |  | 2019-10-08 | 2019-10-07 |  | 2019-06-07 | 2019-06-22
2019-08-01 | MI34A-BS-6A | 2019-06-25 | 2019-06-25 |  | 2019-07-02 | 2019-07-02 |  | 2019-07-09 | 2019-07-09 |  | 2019-08-06 | 2019-08-06 |  | 2019-09-11 | 2019-09-11 |  | 2019-09-18 | 2019-09-18 |  | 2019-09-25 | 2019-09-25 |  | 2019-10-02 | 2019-10-02 |  | 2019-10-09 | 2019-10-09 |  | 2019-10-16 | 2019-10-16 |  | 2019-08-30 | 2019-10-07
2019-08-01 | MI35A-BS-6A | 2019-07-11 | 2019-07-11 |  | 2019-07-18 | 2019-07-18 |  | 2019-07-25 | 2019-07-25 |  | 2019-09-06 | 2019-09-05 |  | 2019-10-25 | 2019-10-24 |  | 2019-11-01 | 2019-10-31 |  | 2019-11-08 | 2019-11-07 |  | 2019-11-15 | 2019-11-14 |  | 2019-11-22 | 2019-11-21 |  | 2019-11-29 | 2019-11-28 |  | 2019-06-13 | 2019-06-01
2019-08-01 | MI37A-BS-6A | 2019-07-16 | 2019-07-16 |  | 2019-07-23 | 2019-07-23 |  | 2019-07-30 | 2019-07-30 |  | 2019-08-28 | 2019-08-28 |  | 2019-10-02 | 2019-10-02 |  | 2019-10-09 | 2019-10-09 |  | 2019-10-16 | 2019-10-16 |  | 2019-10-23 | 2019-10-23 |  | 2019-10-30 | 2019-10-30 |  | 2019-11-06 | 2019-11-06 |  | 2019-08-29 | 2019-09-08
2019-08-01 | MI45A-BS-6A | 2019-04-29 | 2019-05-28 |  | 2019-05-07 | 2019-06-04 |  | 2019-05-14 | 2019-06-11 |  | 2019-06-12 | 2019-07-09 |  | 2019-07-17 | 2019-08-13 |  | 2019-07-24 | 2019-08-20 |  | 2019-07-31 | 2019-08-28 |  | 2019-08-07 | 2019-09-04 |  | 2019-08-14 | 2019-09-11 |  | 2019-08-21 | 2019-09-18 |  | 2019-06-30 | 2019-06-01
2019-08-01 | MI48A-BS-6A | 2018-08-13 |  | 2018-08-13 | 2018-08-23 |  | 2018-08-23 | 2018-08-28 |  | 2018-08-28 | 2018-09-27 |  | 2018-09-27 | 2018-11-01 |  | 2019-01-16 | 2018-11-08 |  | 2018-12-12 | 2018-11-15 |  | 2018-12-12 | 2019-01-04 |  | 2019-04-26 | 2019-01-04 |  | 2019-04-03 | 2019-01-11 |  | 2019-04-26 | 2019-12-18 | 2019-11-11
2019-08-01 | MI48A-BS-6A | 2018-08-13 |  | 2018-08-13 | 2018-08-23 |  | 2018-08-23 | 2018-08-28 |  | 2018-08-28 | 2018-09-27 |  | 2018-09-27 | 2018-11-01 |  | 2019-01-16 | 2018-11-08 |  | 2018-12-12 | 2018-11-15 |  | 2018-12-12 | 2019-01-04 |  | 2019-04-26 | 2019-01-04 |  | 2019-04-03 | 2019-01-11 |  | 2019-04-26 | 2019-07-24 | 2019-06-20
2019-08-01 | MI48A-BS-6A | 2018-08-13 |  | 2018-08-13 | 2018-08-23 |  | 2018-08-23 | 2018-08-28 |  | 2018-08-28 | 2018-09-27 |  | 2018-09-27 | 2018-11-01 |  | 2019-01-16 | 2018-11-08 |  | 2018-12-12 | 2018-11-15 |  | 2018-12-12 | 2019-01-04 |  | 2019-04-26 | 2019-01-04 |  | 2019-04-03 | 2019-01-11 |  | 2019-04-26 | 2019-09-05 | 2019-10-12
2019-08-01 | MI48A-BS-6A | 2018-08-13 |  | 2018-08-13 | 2018-08-23 |  | 2018-08-23 | 2018-08-28 |  | 2018-08-28 | 2018-09-27 |  | 2018-09-27 | 2018-11-01 |  | 2019-01-16 | 2018-11-08 |  | 2018-12-12 | 2018-11-15 |  | 2018-12-12 | 2019-01-04 |  | 2019-04-26 | 2019-01-04 |  | 2019-04-03 | 2019-01-11 |  | 2019-04-26 | 2019-08-04 | 2019-07-13
2019-08-01 | MI48A-BS-6A | 2018-08-13 |  | 2018-08-13 | 2018-08-23 |  | 2018-08-23 | 2018-08-28 |  | 2018-08-28 | 2018-09-27 |  | 2018-09-27 | 2018-11-01 |  | 2019-01-16 | 2018-11-08 |  | 2018-12-12 | 2018-11-15 |  | 2018-12-12 | 2019-01-04 |  | 2019-04-26 | 2019-01-04 |  | 2019-04-03 | 2019-01-11 |  | 2019-04-26 | 2019-09-18 | 2019-08-26
2019-08-01 | MI61A-BS-6A | 2018-08-31 |  | 2018-08-31 | 2018-08-31 |  | 2018-08-31 | 2018-09-05 |  | 2018-09-05 | 2018-10-24 |  | 2018-10-17 | 2018-12-07 | 2019-05-01 |  | 2018-12-14 | 2019-05-01 |  | 2018-12-20 | 2019-04-30 |  | 2019-02-15 | 2019-06-13 |  | 2019-02-19 | 2019-06-04 |  | 2019-02-21 | 2019-06-13 |  | 2019-11-09 | 2019-11-26
2019-08-01 | MI61A-BS-6A | 2018-08-31 |  | 2018-08-31 | 2018-08-31 |  | 2018-08-31 | 2018-09-05 |  | 2018-09-05 | 2018-10-24 |  | 2018-10-17 | 2018-12-07 | 2019-05-01 |  | 2018-12-14 | 2019-05-01 |  | 2018-12-20 | 2019-04-30 |  | 2019-02-15 | 2019-06-13 |  | 2019-02-19 | 2019-06-04 |  | 2019-02-21 | 2019-06-13 |  | 2019-11-07 | 2019-12-03
2019-08-01 | MI61A-BS-6A | 2018-08-31 |  | 2018-08-31 | 2018-08-31 |  | 2018-08-31 | 2018-09-05 |  | 2018-09-05 | 2018-10-24 |  | 2018-10-17 | 2018-12-07 | 2019-05-01 |  | 2018-12-14 | 2019-05-01 |  | 2018-12-20 | 2019-04-30 |  | 2019-02-15 | 2019-06-13 |  | 2019-02-19 | 2019-06-04 |  | 2019-02-21 | 2019-06-13 |  | 2019-10-03 | 2019-09-22
2019-08-01 | MI63A-BS-6A | 2018-11-29 |  | 2018-12-18 | 2018-12-06 |  | 2018-12-18 | 2019-01-10 |  | 2019-01-10 | 2019-02-01 |  | 2019-04-18 | 2019-03-08 | 2019-06-05 |  | 2019-03-01 | 2019-06-05 |  | 2019-03-08 | 2019-06-12 |  | 2019-03-15 | 2019-06-19 |  | 2019-03-22 | 2019-06-26 |  | 2019-03-29 | 2019-07-03 |  | 2019-11-08 | 2019-12-09
2019-08-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-09-24 | 2019-09-12
2019-08-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-09-12 | 2019-09-22
2019-08-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-11-10 | 2019-11-30
2019-08-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-11-26 | 2019-10-21
2019-08-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-07-09 | 2019-08-16
2019-08-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-10-15 | 2019-09-29
2019-08-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-10-15 | 2019-10-18
2019-08-01 | LP01A-BS-6A | 2018-03-29 |  | 2018-03-29 | 2018-03-29 |  | 2018-03-29 | 2018-04-12 |  | 2018-04-12 | 2018-05-15 |  | 2018-05-15 | 2018-06-26 |  | 2018-06-26 | 2018-06-26 |  | 2018-06-26 | 2018-07-25 |  | 2018-07-25 | 2018-08-02 |  | 2018-08-02 | 2018-08-13 |  | 2018-08-13 | 2018-08-17 |  | 2018-08-17 | 2019-07-26 | 2019-07-30
2019-08-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-08-27 | 2019-09-02
2019-08-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-09-17 | 2019-09-09
2019-08-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-08-30 | 2019-09-08
2019-08-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-08-05 | 2019-08-20
2019-08-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-12-07 | 2019-11-02
2019-08-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-06-15 | 2019-06-06
2019-08-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-06-17 | 2019-07-24
2019-08-01 | LP02A-BS-6A | 2018-08-17 |  | 2018-08-17 | 2018-08-20 |  | 2018-08-20 | 2018-08-22 |  | 2018-08-22 | 2018-09-14 |  | 2018-09-14 | 2018-11-02 |  | 2018-11-09 | 2018-11-09 |  | 2018-11-12 | 2018-11-19 |  | 2018-12-13 | 2018-11-26 |  | 2018-12-18 | 2018-12-03 |  | 2018-12-07 | 2018-12-10 |  | 2019-01-07 | 2019-09-01 | 2019-09-12
2019-08-01 | LP42A-BS-6A | 2018-03-14 |  | 2018-03-14 | 2018-03-21 |  | 2018-03-21 | 2019-11-08 | 2019-11-07 |  | 2020-01-13 | 2020-01-10 |  | 2020-03-16 | 2020-03-13 |  | 2020-03-23 | 2020-03-20 |  | 2020-03-30 | 2020-03-27 |  | 2020-04-06 | 2020-04-03 |  | 2020-04-15 | 2020-04-14 |  | 2020-04-22 | 2020-04-21 |  | 2019-09-04 | 2019-08-07
2019-08-01 | LP50A-BS-6A | 2019-05-06 | 2019-05-06 |  | 2019-05-14 | 2019-05-14 |  | 2019-05-21 | 2019-05-21 |  | 2019-07-03 | 2019-07-03 |  | 2019-08-21 | 2019-08-21 |  | 2019-08-29 | 2019-08-29 |  | 2019-09-05 | 2019-09-05 |  | 2019-09-12 | 2019-09-12 |  | 2019-09-19 | 2019-09-19 |  | 2019-09-26 | 2019-09-26 |  | 2019-07-29 | 2019-07-24
2019-08-01 | LY93A-DC-6J | [7 empty] | 2020-01-05 | [20 empty] | 2020-04-01 |  | 2019-08-11 | 2019-09-06
2019-08-01 | MI25A-DC-6J | 2019-01-15 |  | 2019-05-02 | 2019-01-22 |  | 2019-01-29 | 2019-01-29 |  | 2019-02-10 | 2019-02-19 |  | 2019-03-08 | 2019-03-26 |  | 2019-05-01 | 2019-03-26 | 2019-05-16 |  | 2019-04-02 | 2019-05-22 |  | 2019-05-10 | 2019-05-29 |  | 2019-05-02 | 2019-06-05 |  | 2019-05-10 | 2019-06-12 |  | 2019-11-06 | 2019-10-24
2019-08-01 | MI25A-DC-6J | 2019-01-15 |  | 2019-05-02 | 2019-01-22 |  | 2019-01-29 | 2019-01-29 |  | 2019-02-10 | 2019-02-19 |  | 2019-03-08 | 2019-03-26 |  | 2019-05-01 | 2019-03-26 | 2019-05-16 |  | 2019-04-02 | 2019-05-22 |  | 2019-05-10 | 2019-05-29 |  | 2019-05-02 | 2019-06-05 |  | 2019-05-10 | 2019-06-12 |  | 2019-08-17 | 2019-08-24
2019-08-01 | MI25A-DC-6J | 2019-01-15 |  | 2019-05-02 | 2019-01-22 |  | 2019-01-29 | 2019-01-29 |  | 2019-02-10 | 2019-02-19 |  | 2019-03-08 | 2019-03-26 |  | 2019-05-01 | 2019-03-26 | 2019-05-16 |  | 2019-04-02 | 2019-05-22 |  | 2019-05-10 | 2019-05-29 |  | 2019-05-02 | 2019-06-05 |  | 2019-05-10 | 2019-06-12 |  | 2019-06-04 | 2019-07-03
2019-08-01 | MI26A-DC-6J | 2019-03-25 |  | 2019-03-08 | 2019-04-01 |  | 2019-03-25 | 2019-04-08 |  | 2019-03-26 | 2019-05-09 | 2019-05-13 |  | 2019-06-14 | 2019-05-30 |  | 2019-06-21 | 2019-06-06 |  | 2019-06-28 | 2019-06-13 |  | 2019-07-05 | 2019-06-20 |  | 2019-07-12 | 2019-06-27 |  | 2019-07-19 | 2019-07-04 |  | 2019-07-07 | 2019-07-29
2019-08-01 | MI26A-DC-6J | 2019-03-25 |  | 2019-03-08 | 2019-04-01 |  | 2019-03-25 | 2019-04-08 |  | 2019-03-26 | 2019-05-09 | 2019-05-13 |  | 2019-06-14 | 2019-05-30 |  | 2019-06-21 | 2019-06-06 |  | 2019-06-28 | 2019-06-13 |  | 2019-07-05 | 2019-06-20 |  | 2019-07-12 | 2019-06-27 |  | 2019-07-19 | 2019-07-04 |  | 2019-09-30 | 2019-08-29
2019-08-01 | MI26A-DC-6J | 2019-03-25 |  | 2019-03-08 | 2019-04-01 |  | 2019-03-25 | 2019-04-08 |  | 2019-03-26 | 2019-05-09 | 2019-05-13 |  | 2019-06-14 | 2019-05-30 |  | 2019-06-21 | 2019-06-06 |  | 2019-06-28 | 2019-06-13 |  | 2019-07-05 | 2019-06-20 |  | 2019-07-12 | 2019-06-27 |  | 2019-07-19 | 2019-07-04 |  | 2019-07-06 | 2019-06-09
2019-08-01 | MI59A-DC-6J | 2018-11-14 |  | 2018-12-17 | 2018-11-21 |  | 2018-12-17 | 2018-11-28 |  | 2018-12-17 | 2019-01-31 |  | 2019-01-31 | 2019-04-04 |  | 2019-03-15 | 2019-04-11 |  | 2019-03-19 | 2019-04-18 |  | 2019-04-02 | 2019-04-29 |  | 2019-04-05 | 2019-05-07 |  | 2019-04-15 | 2019-05-14 |  | 2019-04-17 | 2019-10-02 | 2019-10-18
2019-08-01 | RR01A-DC-6J | 2018-06-29 |  | 2018-07-16 | 2018-07-06 |  | 2018-07-17 | 2018-07-13 |  | 2018-07-20 | 2018-09-06 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-05 | 2018-11-05 |  | 2018-12-10 | 2018-11-12 |  | 2019-02-11 | 2018-11-19 |  | 2019-02-13 | 2018-11-26 |  | 2019-02-11 | 2018-12-03 |  | 2019-03-11 | 2019-09-15 | 2019-09-09
2019-08-01 | RR01A-DC-6J | 2018-06-29 |  | 2018-07-16 | 2018-07-06 |  | 2018-07-17 | 2018-07-13 |  | 2018-07-20 | 2018-09-06 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-05 | 2018-11-05 |  | 2018-12-10 | 2018-11-12 |  | 2019-02-11 | 2018-11-19 |  | 2019-02-13 | 2018-11-26 |  | 2019-02-11 | 2018-12-03 |  | 2019-03-11 | 2019-11-10 | 2019-10-28
2019-08-01 | RR01A-DC-6J | 2018-06-29 |  | 2018-07-16 | 2018-07-06 |  | 2018-07-17 | 2018-07-13 |  | 2018-07-20 | 2018-09-06 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-05 | 2018-11-05 |  | 2018-12-10 | 2018-11-12 |  | 2019-02-11 | 2018-11-19 |  | 2019-02-13 | 2018-11-26 |  | 2019-02-11 | 2018-12-03 |  | 2019-03-11 | 2019-09-20 | 2019-10-26
2019-08-01 | RR01A-DC-6J | 2018-06-29 |  | 2018-07-16 | 2018-07-06 |  | 2018-07-17 | 2018-07-13 |  | 2018-07-20 | 2018-09-06 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-05 | 2018-11-05 |  | 2018-12-10 | 2018-11-12 |  | 2019-02-11 | 2018-11-19 |  | 2019-02-13 | 2018-11-26 |  | 2019-02-11 | 2018-12-03 |  | 2019-03-11 | 2019-09-19 | 2019-11-02
2019-08-01 | RR01B-DC-6J | 2018-11-06 |  | 2018-03-16 | 2018-11-13 |  | 2018-03-22 | 2018-07-13 |  | 2018-07-20 | 2018-08-03 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-07 | 2018-11-05 |  | 2018-12-11 | 2018-11-12 |  | 2019-02-20 | 2018-11-19 |  | 2019-02-21 | 2018-11-26 |  | 2019-02-27 | 2018-12-03 |  | 2019-03-14 | 2019-07-13 | 2019-08-18
2019-08-01 | RR01B-DC-6J | 2018-11-06 |  | 2018-03-16 | 2018-11-13 |  | 2018-03-22 | 2018-07-13 |  | 2018-07-20 | 2018-08-03 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-07 | 2018-11-05 |  | 2018-12-11 | 2018-11-12 |  | 2019-02-20 | 2018-11-19 |  | 2019-02-21 | 2018-11-26 |  | 2019-02-27 | 2018-12-03 |  | 2019-03-14 | 2019-06-15 | 2019-06-30
2019-08-01 | RR01B-DC-6J | 2018-11-06 |  | 2018-03-16 | 2018-11-13 |  | 2018-03-22 | 2018-07-13 |  | 2018-07-20 | 2018-08-03 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-07 | 2018-11-05 |  | 2018-12-11 | 2018-11-12 |  | 2019-02-20 | 2018-11-19 |  | 2019-02-21 | 2018-11-26 |  | 2019-02-27 | 2018-12-03 |  | 2019-03-14 | 2019-08-22 | 2019-09-04
2019-08-01 | RR01B-DC-6J | 2018-11-06 |  | 2018-03-16 | 2018-11-13 |  | 2018-03-22 | 2018-07-13 |  | 2018-07-20 | 2018-08-03 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-07 | 2018-11-05 |  | 2018-12-11 | 2018-11-12 |  | 2019-02-20 | 2018-11-19 |  | 2019-02-21 | 2018-11-26 |  | 2019-02-27 | 2018-12-03 |  | 2019-03-14 | 2019-12-21 | 2019-11-16
2019-08-01 | RR01B-DC-6J | 2018-11-06 |  | 2018-03-16 | 2018-11-13 |  | 2018-03-22 | 2018-07-13 |  | 2018-07-20 | 2018-08-03 |  | 2018-08-28 | 2018-10-29 |  | 2018-12-07 | 2018-11-05 |  | 2018-12-11 | 2018-11-12 |  | 2019-02-20 | 2018-11-19 |  | 2019-02-21 | 2018-11-26 |  | 2019-02-27 | 2018-12-03 |  | 2019-03-14 | 2019-12-01 | 2019-11-06
2019-08-01 | RR04A-DC-6J | 2018-06-15 |  | 2018-06-26 | 2018-06-22 |  | 2018-07-03 | 2018-06-29 |  | 2018-07-06 | 2018-07-20 |  | 2018-07-31 | 2018-09-19 |  | 2018-10-25 | 2018-09-26 |  | 2018-10-29 | 2018-10-03 |  | 2018-11-12 | 2018-10-10 |  | 2019-01-03 | 2018-10-17 |  | 2018-12-04 | 2018-10-24 |  | 2019-04-03 | 2019-11-27 | 2019-11-17
2019-08-01 | RR04A-DC-6J | 2018-06-15 |  | 2018-06-26 | 2018-06-22 |  | 2018-07-03 | 2018-06-29 |  | 2018-07-06 | 2018-07-20 |  | 2018-07-31 | 2018-09-19 |  | 2018-10-25 | 2018-09-26 |  | 2018-10-29 | 2018-10-03 |  | 2018-11-12 | 2018-10-10 |  | 2019-01-03 | 2018-10-17 |  | 2018-12-04 | 2018-10-24 |  | 2019-04-03 | 2019-06-29 | 2019-07-04
2019-08-01 | RR04A-DC-6J | 2018-06-15 |  | 2018-06-26 | 2018-06-22 |  | 2018-07-03 | 2018-06-29 |  | 2018-07-06 | 2018-07-20 |  | 2018-07-31 | 2018-09-19 |  | 2018-10-25 | 2018-09-26 |  | 2018-10-29 | 2018-10-03 |  | 2018-11-12 | 2018-10-10 |  | 2019-01-03 | 2018-10-17 |  | 2018-12-04 | 2018-10-24 |  | 2019-04-03 | 2019-08-11 | 2019-08-19
2019-08-01 | RR04A-DC-6J | 2018-06-15 |  | 2018-06-26 | 2018-06-22 |  | 2018-07-03 | 2018-06-29 |  | 2018-07-06 | 2018-07-20 |  | 2018-07-31 | 2018-09-19 |  | 2018-10-25 | 2018-09-26 |  | 2018-10-29 | 2018-10-03 |  | 2018-11-12 | 2018-10-10 |  | 2019-01-03 | 2018-10-17 |  | 2018-12-04 | 2018-10-24 |  | 2019-04-03 | 2019-09-28 | 2019-09-17
2019-08-01 | RR06A-DC-6J | 2017-12-11 |  | 2018-01-12 | 2017-12-18 |  | 2018-01-18 | 2018-01-02 |  | 2018-01-26 | 2018-01-30 |  | 2018-03-02 | 2018-03-13 |  | 2018-03-23 | 2018-03-13 |  | 2018-04-17 | 2018-03-20 |  | 2018-07-31 | 2018-04-26 |  | 2018-08-02 | 2018-04-19 |  | 2018-07-23 | 2018-04-26 |  | 2018-08-06 | 2019-06-26 | 2019-06-14
2019-08-01 | RR06A-DC-6J | 2017-12-11 |  | 2018-01-12 | 2017-12-18 |  | 2018-01-18 | 2018-01-02 |  | 2018-01-26 | 2018-01-30 |  | 2018-03-02 | 2018-03-13 |  | 2018-03-23 | 2018-03-13 |  | 2018-04-17 | 2018-03-20 |  | 2018-07-31 | 2018-04-26 |  | 2018-08-02 | 2018-04-19 |  | 2018-07-23 | 2018-04-26 |  | 2018-08-06 | 2019-09-09 | 2019-09-25
2019-08-01 | RR10A-DC-6J | 2018-03-07 |  | 2018-02-28 | 2018-03-14 |  | 2018-03-01 | 2018-03-21 |  | 2018-03-15 | 2018-04-13 |  | 2018-04-09 | 2018-08-02 |  | 2018-08-18 | 2018-11-16 |  | 2018-11-23 | 2018-12-07 |  | 2018-12-19 | 2018-12-14 |  | 2018-12-21 | 2018-12-21 |  | 2019-01-21 | 2019-01-07 |  | 2019-02-06 | 2019-11-07 | 2019-11-17
2019-08-01 | RR10A-DC-6J | 2018-03-07 |  | 2018-02-28 | 2018-03-14 |  | 2018-03-01 | 2018-03-21 |  | 2018-03-15 | 2018-04-13 |  | 2018-04-09 | 2018-08-02 |  | 2018-08-18 | 2018-11-16 |  | 2018-11-23 | 2018-12-07 |  | 2018-12-19 | 2018-12-14 |  | 2018-12-21 | 2018-12-21 |  | 2019-01-21 | 2019-01-07 |  | 2019-02-06 | 2019-12-18 | 2020-01-01
2019-08-01 | RR16A-DC-6J |  |  | 2019-04-02 |  |  |  |  | 2019-06-06 | [20 empty] | 2019-09-26 |  | 2019-06-30 | 2019-06-27
2019-08-01 | RR17A-DC-6J | [8 empty] | 2019-01-18 | [20 empty] | 2019-05-09 | 2019-07-08 | 2019-07-15
2019-08-01 | RR20A-DC-6J | 2018-08-23 |  | 2018-07-27 | 2018-08-31 |  | 2018-08-03 | 2018-09-07 |  | 2018-08-09 | 2018-09-28 |  | 2018-09-21 | 2018-11-30 |  | 2019-01-07 | 2018-12-07 |  | 2019-01-17 | 2018-12-14 |  | 2019-02-13 | 2018-12-21 |  | 2019-02-25 | 2019-01-07 |  | 2019-01-23 | 2019-01-14 |  | 2019-03-04 | 2019-08-10 | 2019-09-12
2019-08-01 | RR20A-DC-6J | 2018-08-23 |  | 2018-07-27 | 2018-08-31 |  | 2018-08-03 | 2018-09-07 |  | 2018-08-09 | 2018-09-28 |  | 2018-09-21 | 2018-11-30 |  | 2019-01-07 | 2018-12-07 |  | 2019-01-17 | 2018-12-14 |  | 2019-02-13 | 2018-12-21 |  | 2019-02-25 | 2019-01-07 |  | 2019-01-23 | 2019-01-14 |  | 2019-03-04 | 2019-11-23 | 2019-10-25
2019-08-01 | RR20A-DC-6J | 2018-08-23 |  | 2018-07-27 | 2018-08-31 |  | 2018-08-03 | 2018-09-07 |  | 2018-08-09 | 2018-09-28 |  | 2018-09-21 | 2018-11-30 |  | 2019-01-07 | 2018-12-07 |  | 2019-01-17 | 2018-12-14 |  | 2019-02-13 | 2018-12-21 |  | 2019-02-25 | 2019-01-07 |  | 2019-01-23 | 2019-01-14 |  | 2019-03-04 | 2019-10-05 | 2019-10-29
2019-08-01 | RR20A-DC-6J | 2018-08-23 |  | 2018-07-27 | 2018-08-31 |  | 2018-08-03 | 2018-09-07 |  | 2018-08-09 | 2018-09-28 |  | 2018-09-21 | 2018-11-30 |  | 2019-01-07 | 2018-12-07 |  | 2019-01-17 | 2018-12-14 |  | 2019-02-13 | 2018-12-21 |  | 2019-02-25 | 2019-01-07 |  | 2019-01-23 | 2019-01-14 |  | 2019-03-04 | 2019-10-23 | 2019-10-23
2019-08-01 | RR47A-DC-6J | 2018-12-13 |  | 2018-09-26 | 2018-12-20 |  | 2018-10-02 | 2019-01-04 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-01-31 | 2019-01-11 |  | 2019-01-31 | 2019-01-18 |  | 2019-03-29 | 2019-01-25 |  | 2019-04-12 | 2019-02-01 |  | 2019-03-26 | 2019-02-08 |  | 2019-04-16 | 2019-07-08 | 2019-06-20
2019-08-01 | RR47A-DC-6J | 2018-12-13 |  | 2018-09-26 | 2018-12-20 |  | 2018-10-02 | 2019-01-04 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-01-31 | 2019-01-11 |  | 2019-01-31 | 2019-01-18 |  | 2019-03-29 | 2019-01-25 |  | 2019-04-12 | 2019-02-01 |  | 2019-03-26 | 2019-02-08 |  | 2019-04-16 | 2019-11-23 | 2020-01-02
2019-08-01 | RR47A-DC-6J | 2018-12-13 |  | 2018-09-26 | 2018-12-20 |  | 2018-10-02 | 2019-01-04 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-01-31 | 2019-01-11 |  | 2019-01-31 | 2019-01-18 |  | 2019-03-29 | 2019-01-25 |  | 2019-04-12 | 2019-02-01 |  | 2019-03-26 | 2019-02-08 |  | 2019-04-16 | 2019-06-08 | 2019-05-11
2019-08-01 | RR47A-DC-6J | 2018-12-13 |  | 2018-09-26 | 2018-12-20 |  | 2018-10-02 | 2019-01-04 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-01-31 | 2019-01-11 |  | 2019-01-31 | 2019-01-18 |  | 2019-03-29 | 2019-01-25 |  | 2019-04-12 | 2019-02-01 |  | 2019-03-26 | 2019-02-08 |  | 2019-04-16 | 2019-10-10 | 2019-11-02
2019-08-01 | RR47A-DC-6J | 2018-12-13 |  | 2018-09-26 | 2018-12-20 |  | 2018-10-02 | 2019-01-04 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-01-31 | 2019-01-11 |  | 2019-01-31 | 2019-01-18 |  | 2019-03-29 | 2019-01-25 |  | 2019-04-12 | 2019-02-01 |  | 2019-03-26 | 2019-02-08 |  | 2019-04-16 | 2019-11-03 | 2019-11-01
2019-08-01 | RR47A-DC-6J | 2018-12-13 |  | 2018-09-26 | 2018-12-20 |  | 2018-10-02 | 2019-01-04 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-01-31 | 2019-01-11 |  | 2019-01-31 | 2019-01-18 |  | 2019-03-29 | 2019-01-25 |  | 2019-04-12 | 2019-02-01 |  | 2019-03-26 | 2019-02-08 |  | 2019-04-16 | 2019-10-30 | 2019-11-17
2019-08-01 | RR47A-DC-6J | 2018-12-13 |  | 2018-09-26 | 2018-12-20 |  | 2018-10-02 | 2019-01-04 |  | 2018-10-11 | 2018-11-08 |  | 2018-11-19 | 2019-01-04 |  | 2019-01-31 | 2019-01-11 |  | 2019-01-31 | 2019-01-18 |  | 2019-03-29 | 2019-01-25 |  | 2019-04-12 | 2019-02-01 |  | 2019-03-26 | 2019-02-08 |  | 2019-04-16 | 2019-07-07 | 2019-07-26
2019-08-01 | RR58A-DC-6J | 2019-08-20 | 2019-08-20 |  | 2019-08-28 | 2019-08-28 |  | 2019-09-04 | 2019-09-04 |  | 2019-10-02 | 2019-10-02 |  | 2019-11-06 | 2019-11-06 |  | 2019-11-13 | 2019-11-13 |  | 2019-11-20 | 2019-11-20 |  | 2019-11-27 | 2019-11-27 |  | 2019-12-04 | 2019-12-04 |  | 2019-12-11 | 2019-12-11 |  | 2019-11-16 | 2019-12-25
2019-08-01 | LP01A-DC-6J | 2018-11-08 |  | 2018-10-29 | 2018-11-15 |  | 2018-10-29 | 2018-11-22 |  | 2018-10-31 | 2018-12-20 |  | 2018-11-28 | 2019-02-01 |  | 2019-01-29 | 2019-02-08 |  | 2019-02-18 | 2019-02-15 |  | 2019-02-26 | 2019-02-22 |  | 2019-04-02 | 2019-03-01 |  | 2019-03-18 | 2019-03-08 |  | 2019-04-05 | 2019-10-27 | 2019-10-24
2019-08-01 | LP02A-DC-6J | 2018-09-20 |  | 2018-09-21 | 2018-09-27 |  | 2018-09-25 | 2018-10-04 |  | 2018-10-31 | 2018-11-01 |  | 2018-12-03 | 2018-12-06 |  | 2019-01-29 | 2018-12-13 |  | 2019-02-18 | 2018-12-20 |  | 2019-03-11 | 2019-01-04 |  | 2019-04-02 | 2019-01-11 |  | 2019-03-19 | 2019-01-18 |  | 2019-04-03 | 2019-11-19 | 2019-10-26
2019-08-01 | LP02A-DC-6J | 2018-09-20 |  | 2018-09-21 | 2018-09-27 |  | 2018-09-25 | 2018-10-04 |  | 2018-10-31 | 2018-11-01 |  | 2018-12-03 | 2018-12-06 |  | 2019-01-29 | 2018-12-13 |  | 2019-02-18 | 2018-12-20 |  | 2019-03-11 | 2019-01-04 |  | 2019-04-02 | 2019-01-11 |  | 2019-03-19 | 2019-01-18 |  | 2019-04-03 | 2019-08-26 | 2019-09-04
2019-08-01 | LP04A-DC-6J | [30 empty] | 2019-08-02 | 2019-07-27
2019-08-01 | LP08A-DC-6J | 2019-06-06 | 2019-06-06 |  | 2019-06-13 | 2019-06-13 |  | 2019-06-20 | 2019-06-20 |  | 2019-07-18 | 2019-07-18 |  | 2019-08-22 | 2019-08-22 |  | 2019-08-30 | 2019-08-30 |  | 2019-09-06 | 2019-09-06 |  | 2019-09-13 | 2019-09-13 |  | 2019-09-20 | 2019-09-20 |  | 2019-09-27 | 2019-09-27 |  | 2019-09-25 | 2019-09-26
2019-08-01 | LP67A-DC-6J | 2019-10-07 | 2019-10-07 |  | 2019-10-14 | 2019-10-14 |  | 2019-10-21 | 2019-10-21 |  | 2019-11-18 | 2019-11-18 |  | 2019-12-23 | 2019-12-23 |  | 2020-01-07 | 2020-01-07 |  | 2020-01-14 | 2020-01-14 |  | 2020-01-21 | 2020-01-21 |  | 2020-01-28 | 2020-01-28 |  | 2020-02-04 | 2020-02-04 |  | 2019-08-16 | 2019-07-09

## Stages
Stage | Person Responsible | Order
Design Docs to be issued | France Barbeau | 1
Design Docs Complete | Angelita Palos | 2
Complete RFI | Yvonne Greenawalt | 3
Issue RFP | France Barbeau | 4
Bid Return | Norine Guerriero | 5
Technical Evaluation | Michal Haase | 6
Commercial Evaluation | Walton Habib | 7
RFQ Issue | Remedios Mata | 8
RFQ Approved | Dan Ducan | 9
Complete RFT | Leona Woodby | 10
Issue PO | Andrew Smith | 11

## Activities
Activity Code | Activity Description
BS | Concrete Base
BW | Brickwork
EC | Electrical Cabling
PL | Plumbing
IN | Insulation
DC | Decoration
QW | Digging

## Workpackages
Workpackage No. | Activity Type | Cost (£) | Title
LY38A-BS-XX | BS | 5137 | Concrete Base Activity No 1
NH07A-BS-XX | BS | 5662 | Concrete Base Activity No 2
LY03A-BS-YY | BS | 8372 | Concrete Base Activity No 3
LY26A-BS-YY | BS | 5821 | Concrete Base Activity No 4
LY33A-BS-YY | BS | 6320 | Concrete Base Activity No 5
LY35A-BS-YY | BS | 4959 | Concrete Base Activity No 6
LY38B-BS-YY | BS | 3608 | Concrete Base Activity No 7
LY41A-BS-YY | BS | 7591 | Concrete Base Activity No 8
LY42A-BS-YY | BS | 2645 | Concrete Base Activity No 9
LY45A-BS-YY | BS | 5804 | Concrete Base Activity No 10
LY49A-BS-YY | BS | 3451 | Concrete Base Activity No 11
LY50B-BS-YY | BS | 1302 | Concrete Base Activity No 12
LY66B-BS-YY | BS | 6456 | Concrete Base Activity No 13
LY66C-BS-YY | BS | 7907 | Concrete Base Activity No 14
AL88A-BS-YY | BS | 3420 | Concrete Base Activity No 15
NH07B-BS-YY | BS | 1715 | Concrete Base Activity No 16
NH07C-BS-YY | BS | 6731 | Concrete Base Activity No 17
NH18A-BS-YY | BS | 8726 | Concrete Base Activity No 18
NH18B-BS-YY | BS | 1799 | Concrete Base Activity No 19
NH49A-BS-YY | BS | 5451 | Concrete Base Activity No 20
MI01A-BS-YY | BS | 6077 | Concrete Base Activity No 21
MI16A-BS-YY | BS | 7800 | Concrete Base Activity No 22
MI20A-BS-YY | BS | 3754 | Concrete Base Activity No 23
MI21A-BS-YY | BS | 4897 | Concrete Base Activity No 24
MI23A-BS-YY | BS | 1805 | Concrete Base Activity No 25
MI23B-BS-YY | BS | 6399 | Concrete Base Activity No 26
MI25A-BS-YY | BS | 5884 | Concrete Base Activity No 27
MI26A-BS-YY | BS | 3807 | Concrete Base Activity No 28
MI27A-BS-YY | BS | 3710 | Concrete Base Activity No 29
MI32A-BS-YY | BS | 8748 | Concrete Base Activity No 30
MI35A-BS-YY | BS | 3262 | Concrete Base Activity No 31
MI37A-BS-YY | BS | 3691 | Concrete Base Activity No 32
MI45A-BS-YY | BS | 8905 | Concrete Base Activity No 33
MI67A-BS-YY | BS | 7493 | Concrete Base Activity No 34
LP99A-BS-1F | BS | 5932 | Concrete Base Activity No 35
LY03A-BS-2E | BS | 4995 | Concrete Base Activity No 36
LY26A-BS-2E | BS | 2034 | Concrete Base Activity No 37
AL19A-BS-2E | BS | 5070 | Concrete Base Activity No 38
AL87A-BS-2E | BS | 2195 | Concrete Base Activity No 39
LP98A-BS-2E | BS | 7348 | Concrete Base Activity No 40
ZA01A-BW-6A | BW | 13823 | Brickwork Activity No 1
ZA01B-BW-6A | BW | 26154 | Brickwork Activity No 2
ZA04A-BW-6A | BW | 13139 | Brickwork Activity No 3
ZA08A-BW-6A | BW | 19394 | Brickwork Activity No 4
ZA09A-BW-6A | BW | 23890 | Brickwork Activity No 5
ZA10A-BW-6A | BW | 22543 | Brickwork Activity No 6
ZA12A-BW-6A | BW | 19304 | Brickwork Activity No 7
LY02A-BW-6A | BW | 11141 | Brickwork Activity No 8
LY03A-BW-6A | BW | 15930 | Brickwork Activity No 9
LY04A-BW-6A | BW | 22259 | Brickwork Activity No 10
LY05A-BW-6A | BW | 26864 | Brickwork Activity No 11
LY48A-BW-6A | BW | 11948 | Brickwork Activity No 12
LY49A-BW-6A | BW | 12626 | Brickwork Activity No 13
LY78A-BW-6A | BW | 29409 | Brickwork Activity No 14
LY78B-BW-6A | BW | 25636 | Brickwork Activity No 15
LY78C-BW-6A | BW | 21776 | Brickwork Activity No 16
LY78D-BW-6A | BW | 19446 | Brickwork Activity No 17
QW10A-QW-6A | QW | 76938 | Digging Activity No 1
QW60A-QW-6A | QW | 79913 | Digging Activity No 2
QW65A-QW-6A | QW | 78568 | Digging Activity No 3
QW67A-QW-6A | QW | 60133 | Digging Activity No 4
QW70A-QW-6A | QW | 56361 | Digging Activity No 5
AL91A-BW-6A | BW | 29984 | Brickwork Activity No 18
VC02A-BW-6A | BW | 23793 | Brickwork Activity No 19
VC03A-BW-6A | BW | 28803 | Brickwork Activity No 20
NH19A-BW-6A | BW | 27657 | Brickwork Activity No 21
MI01A-BW-6A | BW | 20123 | Brickwork Activity No 22
MI01B-BW-6A | BW | 17917 | Brickwork Activity No 23
MI08A-BW-6A | BW | 23675 | Brickwork Activity No 24
MI08B-BW-6A | BW | 23131 | Brickwork Activity No 25
MI11A-BW-6A | BW | 24960 | Brickwork Activity No 26
MI16A-BW-6A | BW | 24230 | Brickwork Activity No 27
MI16B-BW-6A | BW | 11238 | Brickwork Activity No 28
MI17A-BW-6A | BW | 12236 | Brickwork Activity No 29
MI17B-BW-6A | BW | 12338 | Brickwork Activity No 30
MI18A-BW-6A | BW | 18944 | Brickwork Activity No 31
MI18B-BW-6A | BW | 29375 | Brickwork Activity No 32
MI19A-BW-6A | BW | 21641 | Brickwork Activity No 33
MI19B-BW-6A | BW | 28850 | Brickwork Activity No 34
MI20A-BW-6A | BW | 26881 | Brickwork Activity No 35
MI20B-BW-6A | BW | 22557 | Brickwork Activity No 36
MI21A-BW-6A | BW | 29097 | Brickwork Activity No 37
MI21B-BW-6A | BW | 18091 | Brickwork Activity No 38
MI23A-BW-6A | BW | 11396 | Brickwork Activity No 39
MI23B-BW-6A | BW | 21831 | Brickwork Activity No 40
MI25A-BW-6A | BW | 11982 | Brickwork Activity No 41
MI25B-BW-6A | BW | 24472 | Brickwork Activity No 42
MI25C-BW-6A | BW | 21660 | Brickwork Activity No 43
MI26A-BW-6A | BW | 11023 | Brickwork Activity No 44
MI26B-BW-6A | BW | 28969 | Brickwork Activity No 45
MI27A-BW-6A | BW | 12938 | Brickwork Activity No 46
MI27B-BW-6A | BW | 22957 | Brickwork Activity No 47
MI35A-BW-6A | BW | 12865 | Brickwork Activity No 48
MI48A-BW-6A | BW | 11362 | Brickwork Activity No 49
MI61A-BW-6A | BW | 14078 | Brickwork Activity No 50
MI62A-BW-6A | BW | 24387 | Brickwork Activity No 51
LP01A-BW-6A | BW | 26008 | Brickwork Activity No 52
LP02A-BW-6A | BW | 18832 | Brickwork Activity No 53
LP04A-BW-6A | BW | 26796 | Brickwork Activity No 54
NT01A-BW-6A | BW | 23437 | Brickwork Activity No 55
AX13A-EC-6A | EC | 66435 | Electrical Cabling Activity No 1
AX36A-EC-6A | EC | 51547 | Electrical Cabling Activity No 2
MI01A-EC-6A | EC | 61335 | Electrical Cabling Activity No 3
MI08A-EC-6A | EC | 62800 | Electrical Cabling Activity No 4
MI25A-EC-6A | EC | 53408 | Electrical Cabling Activity No 5
MI26A-EC-6A | EC | 67676 | Electrical Cabling Activity No 6
MI48A-EC-6A | EC | 51048 | Electrical Cabling Activity No 7
RR01A-EC-6A | EC | 53358 | Electrical Cabling Activity No 8
RR20B-EC-6A | EC | 61941 | Electrical Cabling Activity No 9
LP01A-EC-6A | EC | 52703 | Electrical Cabling Activity No 10
LP02A-EC-6A | EC | 53020 | Electrical Cabling Activity No 11
LP06A-EC-6A | EC | 65679 | Electrical Cabling Activity No 12
LP08A-EC-6A | EC | 51490 | Electrical Cabling Activity No 13
LP10A-EC-6A | EC | 60157 | Electrical Cabling Activity No 14
LP11A-EC-6A | EC | 64604 | Electrical Cabling Activity No 15
LP12A-EC-6A | EC | 52548 | Electrical Cabling Activity No 16
LP32A-EC-6A | EC | 65698 | Electrical Cabling Activity No 17
LP34A-EC-6A | EC | 53558 | Electrical Cabling Activity No 18
LP35A-EC-6A | EC | 61282 | Electrical Cabling Activity No 19
LP48A-EC-6A | EC | 66984 | Electrical Cabling Activity No 20
LP49A-EC-6A | EC | 54411 | Electrical Cabling Activity No 21
LP51A-EC-6A | EC | 52338 | Electrical Cabling Activity No 22
LP62A-EC-6A | EC | 60947 | Electrical Cabling Activity No 23
LP65A-EC-6A | EC | 63521 | Electrical Cabling Activity No 24
LP66A-EC-6A | EC | 55334 | Electrical Cabling Activity No 25
AL88A-PL-6A | PL | #NUM! | Plumbing Activity No 1
NT01A-PL-6A | PL | #NUM! | Plumbing Activity No 2
AX26A-IN-6A | IN | 189392 | Insulation Activity No 1
LP01A-IN-6A | IN | 129216 | Insulation Activity No 2
LP02A-IN-6A | IN | 131361 | Insulation Activity No 3
LP10A-IN-6A | IN | 102485 | Insulation Activity No 4
LP38A-IN-6A | IN | 139214 | Insulation Activity No 5
LP40A-IN-6A | IN | 107609 | Insulation Activity No 6
ZA01A-BS-6A | BS | 8477 | Concrete Base Activity No 41
ZA01B-BS-6A | BS | 3664 | Concrete Base Activity No 42
ZA04A-BS-6A | BS | 3597 | Concrete Base Activity No 43
ZA08A-BS-6A | BS | 5059 | Concrete Base Activity No 44
ZA09A-BS-6A | BS | 2020 | Concrete Base Activity No 45
ZA10A-BS-6A | BS | 2263 | Concrete Base Activity No 46
LY02A-BS-6A | BS | 6977 | Concrete Base Activity No 47
LY03A-BS-6A | BS | 1973 | Concrete Base Activity No 48
LY04A-BS-6A | BS | 6926 | Concrete Base Activity No 49
LY04B-BS-6A | BS | 1168 | Concrete Base Activity No 50
LY05A-BS-6A | BS | 9492 | Concrete Base Activity No 51
LY26A-BS-6A | BS | 3742 | Concrete Base Activity No 52
LY29A-BS-6A | BS | 2570 | Concrete Base Activity No 53
LY30A-BS-6A | BS | 9390 | Concrete Base Activity No 54
LY31A-BS-6A | BS | 1826 | Concrete Base Activity No 55
LY32A-BS-6A | BS | 1680 | Concrete Base Activity No 56
LY33A-BS-6A | BS | 9730 | Concrete Base Activity No 57
LY33B-BS-6A | BS | 7793 | Concrete Base Activity No 58
LY35A-BS-6A | BS | 6519 | Concrete Base Activity No 59
LY36A-BS-6A | BS | 5198 | Concrete Base Activity No 60
LY38A-BS-6A | BS | 4745 | Concrete Base Activity No 61
LY41A-BS-6A | BS | 8765 | Concrete Base Activity No 62
LY42A-BS-6A | BS | 9651 | Concrete Base Activity No 63
LY44A-BS-6A | BS | 4969 | Concrete Base Activity No 64
LY48A-BS-6A | BS | 9681 | Concrete Base Activity No 65
LY49A-BS-6A | BS | 7714 | Concrete Base Activity No 66
LY50A-BS-6A | BS | 4071 | Concrete Base Activity No 67
LY52A-BS-6A | BS | 1850 | Concrete Base Activity No 68
LY66A-BS-6A | BS | 4229 | Concrete Base Activity No 69
LY66B-BS-6A | BS | 2880 | Concrete Base Activity No 70
LY78A-BS-6A | BS | 4029 | Concrete Base Activity No 71
LY78B-BS-6A | BS | 2999 | Concrete Base Activity No 72
LY78C-BS-6A | BS | 2444 | Concrete Base Activity No 73
LY78D-BS-6A | BS | 5065 | Concrete Base Activity No 74
LY85A-BS-6A | BS | 8379 | Concrete Base Activity No 75
LY95A-BS-6A | BS | 5902 | Concrete Base Activity No 76
LY97A-BS-6A | BS | 8282 | Concrete Base Activity No 77
LY99A-BS-6A | BS | 6296 | Concrete Base Activity No 78
AL01A-BS-6A | BS | 6481 | Concrete Base Activity No 79
AL06A-BS-6A | BS | 4992 | Concrete Base Activity No 80
AL07A-BS-6A | BS | 3592 | Concrete Base Activity No 81
AL11A-BS-6A | BS | 7595 | Concrete Base Activity No 82
AL87A-BS-6A | BS | 4196 | Concrete Base Activity No 83
AL88A-BS-6A | BS | 6541 | Concrete Base Activity No 84
AL89A-BS-6A | BS | 2306 | Concrete Base Activity No 85
AL90A-BS-6A | BS | 8681 | Concrete Base Activity No 86
AL91A-BS-6A | BS | 1150 | Concrete Base Activity No 87
PP01A-BS-6A | BS | 6856 | Concrete Base Activity No 88
PP01B-BS-6A | BS | 7608 | Concrete Base Activity No 89
VC01A-BS-6A | BS | 3216 | Concrete Base Activity No 90
VC02A-BS-6A | BS | 1129 | Concrete Base Activity No 91
VC03A-BS-6A | BS | 6414 | Concrete Base Activity No 92
NH01A-BS-6A | BS | 8903 | Concrete Base Activity No 93
NH02A-BS-6A | BS | 4644 | Concrete Base Activity No 94
NH03A-BS-6A | BS | 7190 | Concrete Base Activity No 95
NH04A-BS-6A | BS | 8251 | Concrete Base Activity No 96
NH06A-BS-6A | BS | 4631 | Concrete Base Activity No 97
NH07A-BS-6A | BS | 7138 | Concrete Base Activity No 98
NH10A-BS-6A | BS | 1475 | Concrete Base Activity No 99
NH12A-BS-6A | BS | 4786 | Concrete Base Activity No 100
NH13A-BS-6A | BS | 2211 | Concrete Base Activity No 101
NH14A-BS-6A | BS | 4027 | Concrete Base Activity No 102
NH15A-BS-6A | BS | 2320 | Concrete Base Activity No 103
NH16A-BS-6A | BS | 9832 | Concrete Base Activity No 104
NH17A-BS-6A | BS | 1890 | Concrete Base Activity No 105
NH18A-BS-6A | BS | 6043 | Concrete Base Activity No 106
NH19A-BS-6A | BS | 1402 | Concrete Base Activity No 107
NH23A-BS-6A | BS | 2284 | Concrete Base Activity No 108
NH24A-BS-6A | BS | 3022 | Concrete Base Activity No 109
NH27A-BS-6A | BS | 9732 | Concrete Base Activity No 110
NH27B-BS-6A | BS | 3239 | Concrete Base Activity No 111
NH27C-BS-6A | BS | 2731 | Concrete Base Activity No 112
NH29A-BS-6A | BS | 8858 | Concrete Base Activity No 113
NH30A-BS-6A | BS | 5424 | Concrete Base Activity No 114
NH31A-BS-6A | BS | 5173 | Concrete Base Activity No 115
NH32A-BS-6A | BS | 9237 | Concrete Base Activity No 116
NH33A-BS-6A | BS | 6691 | Concrete Base Activity No 117
NH35A-BS-6A | BS | 6624 | Concrete Base Activity No 118
NH36A-BS-6A | BS | 9541 | Concrete Base Activity No 119
NH36B-BS-6A | BS | 2282 | Concrete Base Activity No 120
NH37A-BS-6A | BS | 9314 | Concrete Base Activity No 121
NH43A-BS-6A | BS | 5628 | Concrete Base Activity No 122
NH49A-BS-6A | BS | 5801 | Concrete Base Activity No 123
NH50A-BS-6A | BS | 5183 | Concrete Base Activity No 124
NH58A-BS-6A | BS | 1940 | Concrete Base Activity No 125
NH72A-BS-6A | BS | 5862 | Concrete Base Activity No 126
NH91A-BS-6A | BS | 5714 | Concrete Base Activity No 127
NH92A-BS-6A | BS | 4233 | Concrete Base Activity No 128
MI01A-BS-6A | BS | 6829 | Concrete Base Activity No 129
MI08A-BS-6A | BS | 6209 | Concrete Base Activity No 130
MI11A-BS-6A | BS | 7033 | Concrete Base Activity No 131
MI16A-BS-6A | BS | 1716 | Concrete Base Activity No 132
MI17A-BS-6A | BS | 9116 | Concrete Base Activity No 133
MI18A-BS-6A | BS | 7330 | Concrete Base Activity No 134
MI19A-BS-6A | BS | 4105 | Concrete Base Activity No 135
MI20A-BS-6A | BS | 5354 | Concrete Base Activity No 136
MI21A-BS-6A | BS | 5486 | Concrete Base Activity No 137
MI22A-BS-6A | BS | 1912 | Concrete Base Activity No 138
MI23A-BS-6A | BS | 8668 | Concrete Base Activity No 139
MI25A-BS-6A | BS | 2009 | Concrete Base Activity No 140
MI26A-BS-6A | BS | 3435 | Concrete Base Activity No 141
MI27A-BS-6A | BS | 5741 | Concrete Base Activity No 142
MI30A-BS-6A | BS | 3122 | Concrete Base Activity No 143
MI30B-BS-6A | BS | 2113 | Concrete Base Activity No 144
MI31A-BS-6A | BS | 5317 | Concrete Base Activity No 145
MI32A-BS-6A | BS | 5582 | Concrete Base Activity No 146
MI33A-BS-6A | BS | 1998 | Concrete Base Activity No 147
MI34A-BS-6A | BS | 2337 | Concrete Base Activity No 148
MI35A-BS-6A | BS | 9995 | Concrete Base Activity No 149
MI37A-BS-6A | BS | 7220 | Concrete Base Activity No 150
MI45A-BS-6A | BS | 4205 | Concrete Base Activity No 151
MI48A-BS-6A | BS | 9462 | Concrete Base Activity No 152
MI61A-BS-6A | BS | 2236 | Concrete Base Activity No 153
MI63A-BS-6A | BS | 5101 | Concrete Base Activity No 154
LP01A-BS-6A | BS | 4247 | Concrete Base Activity No 155
LP02A-BS-6A | BS | 4519 | Concrete Base Activity No 156
LP42A-BS-6A | BS | 6917 | Concrete Base Activity No 157
LP50A-BS-6A | BS | 1313 | Concrete Base Activity No 158
LY93A-DC-6J | DC | 396335 | Decoration Activity No 1
MI25A-DC-6J | DC | 386602 | Decoration Activity No 2
MI26A-DC-6J | DC | 301705 | Decoration Activity No 3
MI59A-DC-6J | DC | 330189 | Decoration Activity No 4
RR01A-DC-6J | DC | 334766 | Decoration Activity No 5
RR01B-DC-6J | DC | 317611 | Decoration Activity No 6
RR04A-DC-6J | DC | 399814 | Decoration Activity No 7
RR06A-DC-6J | DC | 387194 | Decoration Activity No 8
RR10A-DC-6J | DC | 330337 | Decoration Activity No 9
RR16A-DC-6J | DC | 326738 | Decoration Activity No 10
RR17A-DC-6J | DC | 312545 | Decoration Activity No 11
RR20A-DC-6J | DC | 308825 | Decoration Activity No 12
RR47A-DC-6J | DC | 379946 | Decoration Activity No 13
RR58A-DC-6J | DC | 342165 | Decoration Activity No 14
LP01A-DC-6J | DC | 362909 | Decoration Activity No 15
LP02A-DC-6J | DC | 333909 | Decoration Activity No 16
LP04A-DC-6J | DC | 316023 | Decoration Activity No 17
LP08A-DC-6J | DC | 327489 | Decoration Activity No 18
LP67A-DC-6J | DC | 304456 | Decoration Activity No 19